## Implementation Plan Guidance
IMPLEMENTATION PLAN
INSTRUCTIONS FOR COMPLETING THE IMPLEMENTATION PLAN NOTE: Prepared in 8.5 x 14
1. Save the IMPLEMENTATION PLAN Excel as: Your Provider Name-State Priority [EX: Alpha/Omega Center-Priority 1]
2. There are THREE Parts to the IMPLEMENTATION PLAN:
Part 1 - Project Management Plan (PMP)
Part 2 - Detailed Action Plan (DAP)
Part 3 - At-A-Glance Milestone Timeline
3. The IMPLEMENTATION PLAN is informed by your APPROVED Strategic Plan. Each plan should have at least 3 strategies , otherwise known as your Prevention Portfolio. To start, replace each PMP Strategy Tab and each Strategy DAP name with the name of your specific APPROVED strategies - one strategy per tab.
Part 1 - Project Management Plan (PMP) (one per strategy)
There are two primary sections that you will be required to complete:
I. SCOPE Considerations
II. Community Readiness
1.1 Although the questions are the same under each PMP Strategy tab, your responses are specific to the strategy.
1.2 Please provide as much detail as possible for all questions. For Excel 2007 users, adjust your cell to accommodate your narrative responses by doing the following: Home/Cells/Format/AutoFit Row Height.
1.3 To ensure that questions were not omitted, please note NA (not applicable) or zero (0) when appropriate.
The PMP will also introduce two areas for you to review and begin thinking about in preparation for the Evaluation Training. NOTE: There are only a few cells to complete in these sections. Do not attempt to address the blackened sections at this time.
III. Fidelity
IV. Evaluation & Data Collection
Part 2 - Detailed Action Plan (DAP) (one per strategy)
The Detailed Action Plan is designed to outline all of the core activities and action steps necessary to successfully implement your APPROVED strategy. Also use this tab to outline any capacity efforts associated with the Approved Strategy (See EXAMPLE Tab).
Part 3 - At-a-Glance Milestone Timeline (one per prevention portfolio)
This Gannt-style timeline is designed to outline the approximate start and completion of major activities, otherwise referred to as the milestones, assocated with each strategy. Please note this timeline is not intended to capture all of the multiple action steps detailed in column D of the Detailed Action Plan tabs. Instead, Providers should refer to column A in their Detailed Action Plan tabs to guide them in this process.
When printing out your Implementation Plan or sections of the plan:
1) Highlight the section(s) to be printed.
2) Go to the Page Layout Tab and select Print Area
3) Under Print Area, select Set Print Area.
4) Print
The IMPLEMENTATION PLAN to include all three parts will be due two weeks from the date of your Regional Training.
If you have any questions or need additional assistance completing the Implementation Plan, please submit your questions via ECCO..

## Provider & CPAW Info
Provider Information
Provider Name | CETPA Inc.
Project Coordinator | Veronica Melara (Region 3)
State Priority | Reduce the Early onset of alcohol use among 9-20 year olds
Approved IV/CF | IV: Social Community Norms/Social Availability - CF: Cultural Acceptability and Youth Preception of Parental Acceptance/Provision to Minors and Availability of Unsupervised Places to Drink
Assigned Communities & Community Readiness Score (CRS) | Norcross (30093 in Gwinnett County), Sandy Springs (30342 in Fulton County), Doraville (30340 in DeKalb County)
Community 1/CRS | Norcross: Initiation (6)
Community 2/CRS | Sandy Springs: Initiation (6)
Community 3/CRS | Doraville: Preplanning (4)
Memorandum of Agreement Information
Partner/Consultant Information | Role | Pending | Confirmed
Irma Walker | CPAW member, Planning workgroup |  | x
Camila Ramirez | CPAW member, Media Workgroup |  | x
Mahuli Jakubek | CPAW member, Planning workgroup |  | x
Clara Herrera | CPAW member, Epidemiology workgroup |  | x
Felix Lora | CPAW member, Planning workgroup |  | x
Gladys Coreas | CPAW member, Planning workgroup |  | x
Katie Buell | CPAW member, Media Workgroup |  | x
Molly Vance | CPAW member, Planning workgroup |  | x
Michelle Baroni | CPAW member, Planning workgroup |  | x
Note on A14: In addition to indicating that they are on the CPAW, please list their role on the CPAW (i.e. which workgroup do they serve on?)

## PMP Strengthening Families Prog
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Strengthening Famlies Program
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | IV: Social Community Norms - CF: Cultural Acceptability, Youth Perception of Parental Acceptance
Strategy Intent: | Create family conditions that promote responsibilities and life skills in youth and parents to reduce the consumption of alcohol.
Target Audience: | Hispanic Parents and their 9-14 year old children
IOM Category | Selected
Estimated Reach: | 75 Families in total (30 families in Sandy Springs, 45 families between Norcross and Doraville)
What is the dosage for this strategy? | Each cycle includes 7 sessions (7 weeks) 2.5 hours each. Sandy Springs is expected to receive 2 cycles. Between Norcross and Doraville we will have another 3 cycles.
How frequent will the strategy be implemented? | 2 Cycles in Norcross, 2 Cycles in Sandy Springs, 1 Cycle in Doraville. Once class a week for 7 weeks.
Necessary Resources for Successful Implementation | Staff, Trainings, Curriculum, Handbooks, Translation Services, Evaluator, Supplies and Materials.
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: Veronica Melara (Project Coordinator) |  | Veronica Melara (Project Coordinator).
Number of staff to be hired/contracted: We already have a contract with Ser Familia Inc. They provide 3 facilitators, 1 assistant, 1 child care. | CETPA hired this staff like contractors just to facilitate the classes. They are bilingual (English - Spanish) and have experience facilitating this program. | Jeniffer Manon, APP Director | October 1st, 2016 | MOU and/or Contract. | Hire qualified facilitators certified to conduct the Strengthening Families Program.
Staff/Consultant Recruitment Strategy | We will continue using the services offered by Ser Familia Inc. | Jeniffer Manon, APP Director | October 1st, 2016 | MOU and/or Contract. | Hire qualified facilitators certified to conduct the Strengthening Families Program. They need to be bilingual and have experience working with youth.
Staff/Consultant Training: APP Director, APP Coordinator, R3 Project Coordintor, Project Assistant, and facilitators already received the Strengthening Families Program Training. Participants learned about the background, evaluation, goals, and content of the program and to take part in session activities. Training also included information on practical considerations for implementing the SFP 10-14, such as recruiting families and handling challenging parents and youth during program sessions. The Iowa State University certifided trainers to conduct the program. | APP Staff and facilitators from Ser Familia Inc. already received the Strengthening Families Program Training. | Jeniffer Manon, APP Director. SFP Trainers. | October 1st, 2016 | Facilitators completed 21 hours of training by sign in. This is a theorical and practical training where participants can show what they have learned in front of the trainers and the rest of the group. During the program, the APP Staff will be present in some of the sessions in order to monitor the facilitators' work. | 100% of the facilitators have to be certified from the Iowa State University to conduct the program.
Staff Retention Strategy | Project Coordinator and the Assistant are full time employees. Facilitators and/or contractors will be paid for each class that is going to conduct. We are going to have constant communication to share information and give support and feedback on the ongoing development with us. | Jeniffer Manon, APP Director | Ongoing | After each class there will be a meeting to discuss / evaluate the development of the program and the performance of each facilitator. Between classes facilitators will receive the necessary support in order to improve their work. | Retaining 100% of staff/contractors.
Additional Training: It is not necessary to have additional training. | None | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies: Our goal is to work with schools in each community to recruit the families that will participate in the program. If we can’t recruit all the families with the schools we will find a community organization and/or church that work in the community to conduct the program with their help.They will be in charge of the recruitment of the families. We are planning to work with the same schools that hosted the program in the first year of implementation. | We will ask the schools/organizations to recruit the same families that they serve already in their programs, such as the parent’s center and/or PTA’s. They will recruit families with Latino children between 10-14 years old with no history of substance abuse. Parents will fill out a registration form. It will not be necessary to use a screener for the recruitment of families whose children are at risk because they have very limited options towards overcoming their daily obstacles of inadequate at-home support, language barriers, lack of resources, acclimating to American culture, and the stress of life as an immigrant teenagers or children of immigrants, amongst other things. | School/organization staff. | First Phase: 11/18/15 Second Phase: 3/25/16 Third Phase: 6/29/16 | Parents registration form. | To have 18 families registered before the initiation of each cycle.
Retention Strategies | Schools will sign a MOU that guarantees their commitment with the implementation of the program. For the families the program requires the provision of food among other incentives as a instrument to maintain their participation. Also building relationships with them, sharing information, giving them support on their ongoing development with us, giving them positive feedback on their efforts. Each week before the class we will call each family to remind them to attend the program. In each class we are going to have a sign in sheet where each parent will confirm their contact information. | Veronica Melara, Project Coordinator. | Ongoing | *Recording meetings by signing in. *MOU | To end every cycle with at least 15 families.
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Present information at local community events. | Inform and reinforce awareness about the underage drinking problem with flyers, posters and brochures. | APP staff | Ongoing | * Keeping record on how many people attend the events, number of flyers distributed. | 150 Flyers to be distributed in each community.
Begin to initiate our own events to present information on the issue. | Inform and reinforce awareness about the underage drinking problem with workshops, presentations. | APP Staff | Ongoing | * Recording events by signing in. * To use evaluation forms to aquire information about their perception of the issue. * People will be asked to sign pledge cards with their compromise not to provide alcohol to minors. | To create awareness among 150 people within the 3 communities. 90% of the participants considered that the underage drinking is a problem.
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations: It is not necessary to do adaptations to the curriculum. The material is already translated in Spanish and has been used for several years. | Facilitators completed a three-day certification training, which includes use of post-test for youth and parents, curriculum activities to be well-prepared to teach the program, and recruitment and retention, among others. | APP staff | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2015-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on B8: good job -Tiffiany Aholou
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions. ---- You have included good information. However, it should be noted in column B with the other related notes.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A32: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A34: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A38: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP Be The Wall
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Be The Wall
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | IV: Social Availability - CF: Availability of Unsupervised Places to Drink
Strategy Intent: | Increase knowledge about underage drinking and promote responsabibilities in adults to monitor youth activities and restrict access.
Target Audience: | Hispanic parents and adults in general.
IOM Category | Universal and Selective
Estimated Reach: | 50% of Hispanic parents and adults in each community would recognize the Be The Wall logo.
What is the dosage for this strategy? | This information will be determined during the planning step with the advice of the CPAW, and developers of the strategy.
How frequent will the strategy be implemented? | This information will be determined during the planning step with the advice of the CPAW, and developers of the strategy.
Necessary Resources for Successful Implementation | Staff, Trainings, Survey, material.
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: Alejandro Calderon (Project Coordinator), Veronica Melara (Project Assistant) |  | Veronica Melara (APP Coordinator)
Number of staff to be hired/contracted: To evaluate the data we have a contract with Eval Group. | CETPA had worked with Eval Group in the past. | Veronica Melara (APP Coordinator) | Ongoing | Contracts | Contracts signed.
Staff/Consultant Recruitment Strategy | CETPA had worked with Eval Group in the past and have a contract agreement with them since the beginning of the project. | Veronica Melara (APP Coordinator) | Ongoing | Contracts | Contracts signed.
Staff/Consultant Training | Project Coordinator, Project Assistant, and evaluators received training about the strategy. | Veronica Melara (APP Coordinator) | July 14th, 2014 | The strategy just require to watch a pre-recorded webinar. In our case, we also attend a webinar hosted by the state. | Staff and evaluators understand the strategy and the "do's" and "don’t's".
Staff Retention Strategy | Contracts and payment. | CETPA's administration department. | Ongoing | Contracts | Contracts signed.
Additional Training | NA | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies: We will look for the help of volunteers that have experience in the marketing field to assist us in the planning and implementation of the strategy in the first phase. | *To contact strategy's developers to ask their support. *We already have a partnership with a marketing professor from Georgia Gwinnett College who is working with his students in the creating of a basic marketing plan for this strategy. | App Staff | 2014-10-31 | *Agreement of collaboration with marketing professor. *Copy of the student's final reports. *Sign in form of class attendance. | To count on the support of at least one marketing expert/student during the implementation of phase one.
Retention Strategies: | *To invite marketing professor to CPAW meetings. *To invite students to present their projects to CPAW members. *To send progress reports to students during the implementation of the strategy. | App Staff | Ongoing | *Sign in forms. | To count on the particcipation of the marketing professor/students in at least two CPAW meetings or Media Committee.
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Make one on one visits with the community stakeholders and members. | Create and/or reinforce partnerships with different groups in the community who serve Hispanic/Latino population (Including CPAW members) to encourage them to involve the underage drinking problem and prevention efforts to their agendas. Provide them information and/or materials. | APP Staff | Ongoing | * Recording meetings with parents, youth, and stakeholders by signing in. * To use evaluation forms to aquire information about their perception of the issue. | Participants considered that the underage drinking is a problem.
Begin to initiate our own events to present information on the issue. | Inform and create awareness about the underage drinking problem with workshops, presentations. | APP Staff | Ongoing | * Recording events by signing in. * To use evaluation forms to aquire information about their perception of the issue. | To create awareness among 150 people within the 3 communities. 90% of the participants considered that the underage drinking is a problem.
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | NA | NA | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2015-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A34: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A36: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A40: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP Sticker Shock Camp
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Sticker Shock Campaign (MADD Model)
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | IV: Social Avalilability - CF: Provision to Minors
Strategy Intent: | Increase the knowledge in adults about the laws and penalties regarding the provision to minors.
Target Audience: | Adults
IOM Category | Universal/ Selected
Estimated Reach: | 20 Retail Establishments (10 in Norcross, 5 in Sandy Springs, and 5 in Doraville. CPACS will cover other 10 stores between Sandy Springs and Doraville)
What is the dosage for this strategy? | 6400 Stickers distributed among the 20 Retail Establishments within 2 cycles. (10 in Norcross, 5 in Doraville, 5 in Sandy Springs. CPACS will cover other 10 stores between Sandy Springs and Doraville)
How frequent will the strategy be implemented? | 2 Cycles in Norcross, 2 Cycles in Sandy Springs, 2 Cycles in Doraville
Necessary Resources for Successful Implementation | Staff, Design, Printing, Transportation, Newspaper Article. Collaboration agreement with CPACS to cover 20 retail stores in the cities of Sandy Springs and Doraville)
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: Alejandro Calderon (Project Coordinator), Veronica Melara (Project Assistant) |  | Veronica Melara, Project Coordinator
Number of staff to be hired/contracted: No need to hire new staff to conduct this strategy. We will count with the help of the members of the Youth Advisory Team (Heroes) | HEROES already has a group of young volunteers that will help to conduct the strategy. | Veronica Melara, Project Coordinator | Ongoing | NA | NA
Staff/Consultant Recruitment Strategy | HEROES already has a group of young volunteers that will help to conduct the strategy. | Veronica Melara, Project Coordinator | Ongoing | Parent permission forms. | At least three in each cycle.
Staff/Consultant Training | Volunteers will receive a training about the implementation of the strategy. | Veronica Melara, Project Coordinator | 2015-05-29 | Recording the workshop by signing in. | All volunteers understand the MADD model and the "do's and don’t's"
Staff Retention Strategy | NA | NA | NA | NA | NA
Additional Training | NA | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies: We will recruit at least 20 retail stores (10 in Norcross, 5 in Doraville, 5 in Sandy Springs) to distribute the stickers. | Project coordinator will visit retail stores to involve them in the strategy. We will ask CPAW members to assist in this task. Each retail store owner and/or manager will receive a formal invitation letter to support the strategy. This letter will explain the facts about underage drinking and how their involvement could help to decrease the problem. On the other hand, if is necessary CPAW members and the Youth Advisory Team HEROES will help in the changes in the design of the stickers and posters in order to be adequate for the population we are trying to reach. HEROES members will support in the distribution of the stickers. | Veronica Melara, Project Coordinator | 2015-05-25 | Picture during the implementation in each retail store. Form to keep record of the number of stickers distributed. | Recruit 20 retail stores in the three communities. 6400 stickers distributed. Having 20 Evaluation forms from the retail store owners.
Retention Strategies | During the first visit at the retail store, each owner and/or manager will receive a certificate of appreciation for their support. We also are going to publish a newspaper article with the names of the retail stores that will participate in the strategy. | Veronica Melara, Project Coordinator | 2015-05-25 | Picture of each owner and/or manager with their certificate. Copy of the newspaper article. | Retaining 90% of retail stores.
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Continue one on one visits and encourage those you have spoken to assist. | Invite owners and/or managers to be involve in the different prevention activities that CETPA and/or other organizations could have in the community. For example they could provide donations or they could allow for flyers, posters and other materials to be display in their stores. | Veronica Melara, Project Coordinator | Ongoing | * Recording number of visits with the retail stores. | 90% of the participants with sign the pledge.
Post flyers and posters related with the Sticker Shock message. | As well as the stickers, we will also be distributing posters and glass clings in the retail stores indicating that it is against the law to provide alcohol to minors and that underage drinking is illegal. | Veronica Melara, Project Coordinator | 2015-07-28 | * Keeping record on the number of posters distributed and also pictures of the posters in the stores. | 90% of the stores allow us to distribute the glass clings in the stores.
To point out media articles to describe the underage drinking and the provision to minors issue. | We are going to publish a newspaper article discussing the facts about the provision to minors within the Latino/Hispanic community and the consequences of the problem. Contact other media (Radio and TV) to ask them their support and create opportunities to present the information to the community. | Veronica Melara, Project Coordinator | 2015-07-28 | *Copy of the actual article. *Copy of the interviews. | *For the articles to be pubished in the newspapers within the three communities. *To have at least one interview in a Latino radio sttion and one interview in a TV newsbroadcast.
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | NA | NA | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2015-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on B3: Which sticker shock model will you be implementing?
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on E29: Do you mean, "their commitment... : )
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## Modified EXAMPLE DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Run 1st of 4 PSAs in newspaper by January 2014 | Spread the word about the dangers of underage drinking. | Parent | 1. Draft a 'catchy' announcement |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-14 | 2013-12-01 | 2013-12-20 | Activity started after the PC and CPAW attended a social marketing training offered at the local university on 11/23/13.Despite the delay, we implemented the activity as planned.
|  |  | 2. Identify 10 parents to participate in 2 focus groups to elicit input on PSA |  | Lisa Smith and John Williams - Partners | 2013-11-20 | 2013-11-30 | 2013-12-15 | 2013-12-30
|  |  | 3. Contract with newspaper outlets to run first PSA |  | Anita Conley | 2013-12-01 | 2013-12-10 | 2013-12-01 | 2013-12-07
Host 1st of 4 Lunch & Learn programs by March 2014 | To raise awareness about underage drinking and social host liability among community stakeholders. | Stakeholders | 1. Put together a powerpoint that explains the purposed of SPF, the implications of youth possession in the community, and the need for community involvement. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-07 | 2013-11-01 | 2013-11-07
|  |  | 2. Identify a donor and/or inkind support to provide the food for the L & L. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 3. Secure a venue in collaboration with a community partner to host the L & L in a location convenient to stakeholders. |  | Anita Conley - Administrative Asst. | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 4. Host first L & L |  | Kimberly Jones - Project Coordinator | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01
Poll community to gather data concerning communities view of underage drinking/social hosting | Gather data to determine the communities responsiveness to a social host ordinance | Parents of youth 9 to 20 and community members | Develop 4 to 5 questions concering underage drinking and social hosting to gather data | Provider Office | Evaluator | 2014-03-01 | 2014-04-30 | 2014-03-10 | 2014-04-15 | Our projected dates were delayed to include student involvment and input throughout this activity. We started after spring break and continued after the students returned to campus.
|  | Law Enforcement, Workgroup and community members | Attend community events and visit various community locations where polls can be distributed and collected | [Local Community] | CPAW Workgroup, Kimberly Jones - Project Coordinator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-15
|  | Law Enforcement, Workgroup and community members | Analyze poll data as received to determine communities receptiveness towards social host ordinance | Provider Office | Evaluator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-30
Present report of community poll to City Council during 2014 calendar year | To educate and inform the City Council about the community's views about social host ordinance. | City Council | Contact the appropriate office to get on the 2014 4th quarter City Council calendar. | [Local Community] | Kimberly Jones - Project Coordinator | 2014-08-01 | 2014-09-30 | 2014-09-20 | 2014-12-22 | We were advised by the CPAW to wait until the data was compiled and report drafted before pursuing a date. Unfortunately, due to the political climate in our community, 1) Social Host Liability is not a priority at this time; 2) we were informed that the 2015 City Council calendar has already been set as well.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
SHADED FOR EXAMPLE ONLY3

## SFP- DAP (2015-2016)
Approved Strategy Name: |  | Strengthening Families Program
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Recruitment of Families (Phase 1) | Recruit 15 families from each community who will participate in the first two cycles | Hispanic Parents and their Children | Prepare and distribute flyers with the information of the program. | Schools/ Community Partner Facilities | APP Staff | 2015-08-10 | 2015-09-14 | 2015-10-05 | 2015-11-10 | October 2015- Flyers and registration forms have been prepared and have been distributed among families in school and in the Catholic Center. PC has been going to several events in Sandy Springs and meeting with Catholic Center and Sandy Springs Mission to recruit families.
|  |  | Provide Registration form to schools or community organization | Schools/ Community Partner Facilities | APP Staff | 2015-08-10 | 2015-09-14 | 2015-10-05 | 2015-11-10 | October 2015- Flyers and registration forms have been prepared and have been distributed among families in school and in the Catholic Center. PC has been going to several events in Sandy Springs and meeting with Catholic Center and Sandy Springs Mission to recruit families.
|  |  | Identify 15 Families for each school/Community Partners and recruit them. | Schools/ Community Partner Facilities | Schools/ Community Partners staff | 2015-08-10 | 2015-09-14 | 2015-10-05 | 2015-11-10 | October 2015- Still in the process of recruiting the families. PC has been going to several events in Sandy Springs and meeting with Catholic Center and Sandy Springs Mission to recruit families.
Implementating Phase 1 | Completing the first of 5 Cycles | Hispanic Parents and their Children | Teach the seven classes of the program to the families that will participate in the first cycle of the strategy. | Schools/ Community Partner Facilities | APP staff & Schools/ Community Partners staff | 2015-09-28 | 2015-11-18 | 2015-11-10 | 2015-12-17 | December 2015- Session 4, December 1st and 8 families participated. Session 5, December 8th and 8 families showed. Only 4 families participated on the 6th session, December 15th. There was a Christmas event for the church down the street and the majority of the families go to Church of the Atonement. Fianlly on December 17th, 11 families graduated from the Strengthening Families Program. The families shared their testimonies. Yoneiby and I distributed the certificates of completion and made sure that all students took the post tests, which are required for evaluation. Transportation has always been an option for the Sandy Springs community, but unfortunately the driver has been very ill and is not able to support us this time. Many of the families walk to the school, considering the cold weather they are very dedicated to the program and the attendance has been constant. November 2015- Session 1 took place on the 10th and 11 families participated. Session 2 took place on November 12. We decided to have the first two sessions the same week bacause it conflicts with the school holiday vacations. Session 3 took place on Tuesday November 17th and we had the same 11 families. Transportation has always been an option for the Sandy Springs community, but unfortunately the driver has been very ill and is not able to support us this time. Many of the families walk to the school, considering the cold weather they are very dedicated to the program and the attendance has been constant. Ser Familia has been facilitating the program. October 2015- There were many obstacles why we didn't start the program on the projected dates. The Parent Liaison from Ridgeview Charter School backed out at the last minute; parents were not recruited in time and also the facilitarors were not available at that time.
Recruitment of Families (Phase 2) | Recruit 15 families from each community who will participate in the second, and third cycles of the program | Hispanic Parents and their Children | Prepare and distribute flyers with the information of the program. | Schools/ Community Partner Facilities | APP Staff | 2016-01-06 | 2016-02-05 | 2015-12-15 | 2016-01-31 | January 2016- PC has made contact with the parent liaisons from Rockbridge Elementary, Kyla Ramsey and Marcelo Rodriguez. PC also made contact with the lead counselor, Jeannie Damrich from Sequoyah Middle Schooland distributed flyers with the information of the program. December 2015- PC has made contact with Lilburn Middle School and Rockbridge Elementary School from Norcross. Sequoyah Middle School in Doraville is also interested in implementing the program.
|  |  | Provide Registration form to schools or community organization | Schools/ Community Partner Facilities | APP Staff | 2016-01-06 | 2016-02-05 | 2016-01-06 | 2016-02-12 | February 2016- Registration forms and flyers were distributed. January 2016- PC has made contact with the parent liaisons from Rockbridge Elementary, Kyla Ramsey and Marcelo Rodriguez. PC also made contact with the lead counselor, Jeannie Damrich from Sequoyah Middle Schooland distributed flyers with the information and the registration forms will be distributed and filled out on the day of the orientation.
|  |  | Identify 15 Families for each school/Community Partners and recruit them. | Schools/ Community Partner Facilities | Schools/ Community Partners staff | 2016-01-06 | 2016-02-05 | 2016-01-06 | 2016-04-22 | February 2016-Orientations were held the second week of the month and it was a success. At this point we've recruited 45 families n both Sequoyah Middle School and in Rockbridge Elementary school and they have been identified. January 2016- The family liaisons from Rockbridge Elementary and the lead couselor from Sequoyah Middle School are actively recruitng the families for the program.
Implementating Phase 2 | Completing the second, and third Cycles of the program | Parents and their Children | Teach the seven classes of the program to the families that will participate in the second, and third cycles of the strategy. | Schools/ Community Partner Facilities | APP Staff | 2016-02-08 | 2016-03-25 | 2016-02-16 | 2016-04-29 | March 2016- For the Doraville location in Sequoyah Middle School, the third session was held on March 1st and 20 families attended. On March 8th, the fourth session was held and 22 families attended. The fifth session, March 15th, 24 families attended and on March 22nd, 18 families attended. On March 29th is the Sequoyah Middle School Graduation Ceremony. For the Norcross location in Rockbridge Elementary School, the third session on March 4th and 20 families attended. On March 11th, the Gwinnett county schools were closed. Session 4 was on March 18th and 21 families attended.On March 25th, the program was posponed because its a religios holiday for the Catholic Church. The majority if not all the families wouldn't be able to attend. February 2016- The first session was held on February 16th and we had 7 families attend. On the second session was held on February 23, and 22 families attended. We have closed the recruitment and no longer taking new participants. For the Norcross location, PC met with the Parent Liaisons from Rockbridge Elementary School, Kyla Ramsey and Marcelo Rodriguez. We have worked with them in the past and looking forward to a successful cycle. The orientation was on February 12th. Session 1 for SFP in Rockbridge Elementary was on February 19th at 5:00pm-7:30pm. The second session was held on the 26th and we had 23 families attended. The individual strategy's surveys were distributed for both schools.
Recruitment of Families (Phase 3) | Recruit 15 families from the community who will participate in each, the fourth, and fifth cycle of the program | Hispanic Parents and their Children | Contact perspective schools or community organizations where we can implement the strategy in the community and making appointments. | Schools/ Community Partner Facilities | APP Staff | 2016-04-04 | 2016-05-09 | 2016-04-04 | 2016-05-25 | On May 6th, PC attended a meeting with program coordinator, priest and deacon from Centro Catolico. PC explained the program to them in depth and they loved the idea. After many meetings it was decided that we are to implement a summer cycle at the Catholic Center. Ser Familia will be collaborating with us again.
|  |  | Prepare and distribute flyers with the information of the program. | Schools/ Community Partner Facilities | APP Staff | 2016-04-04 | 2016-05-09 | 2016-04-04 | 2016-05-09 | May 2016- PC has distributed flyers and registration forms in different community events. PC hosted Town Hall meetings in Norcross, Sandy Springs, and Doraville. PC collected 35 registration forms at the Norcross location.
|  |  | Provide Registration form to schools or community organization | Schools/ Community Partner Facilities | APP Staff | 2016-04-04 | 2016-05-09 | 2016-04-04 | 2016-05-09 | May 2016- PC has distributed flyers and registration forms in different community events. PC hosted Town Hall meetings in Norcross, Sandy Springs, and Doraville. PC collected 35 registration forms at the Norcross location.
|  |  | Identify 15 Families from the Community Partner and recruit them. | Schools/ Community Partner Facilities | Schools/ Community Partners staff | 2016-04-04 | 2016-05-09 | 2016-04-09 | 2016-05-09 | May 2016- The first session will take place on June 9th from 6:00pm to 8:30pm. PC has been recruting families in community events and at the church. The parent liaisons from Fulton County have been very helpful with the recruitment process. Norcross First United Methodist Church's pastor, Joel Rodriguez agreed for us to implement the program. The first session will take place on June 6th. This is the first time we are having the program in the morning, from 9:00AM to 11:30AM. A cycle in Doraville is still to be determined.
Implementating Phase 3 | Completing the last 2 Cycles of the program | Parents and their Children | Teach the seven classes of the program to the families that will participate in the last 2 cycles of the strategy. (4th/5th cycles. 15 families/7classes each cycle). Please break this down by cycles | Schools/ Community Partner Facilities | APP Staff | 2016-05-16 | 2016-06-29 | 2016-06-06 |  | June 2016- Norcross First United Methodist Church Mondays 9:00am- 11:30am. This is the first time we implement in the morning and to our surprise the attendance has been off the charts. This will be the second time we are to implement the program in this location. Monday, June 6th, we had 36 families and the second session on 13th we over 60 youth. We had to contact the developer to see what is the best action to take. PC contacted some of the families and put them on a waiting list for the next cycle, they were very understanding. On the third session, June 20th there were 28 families. PC is serving as the third facilitator on the youth session. Holy Spirit Catholic Center In Sandy Springs Thursdays 6:00pm- 8:30pm. This is will be the second time we implemented in this location. Thursday, June 9th, we had 13 families participated. The second session on the 16th, we had 7 families. The third session on the 23rd, 9 families attended. Ser Familia is facilitating the sessions in both locations. Its been a challenging cycle so far but again its always rewarding when the families are dedicated to program and want to have a positive relationship at home and ultimately giving the parents the tools on how to speak to their children about the prevention of alcohol use at a younger age. Reaching the parents is the key. May 2016- The first session will take place on June 9th from 6:00pm to 8:30pm. PC has been recruting families in community events and at the church. The parent liaisons from Fulton County have been very helpful with the recruitment process. Norcross First United Methodist Church's pastor, Joel Rodriguez agreed for us to implement the program. The first session will take place on June 6th. This is the first time we are having the program in the morning, from 9:00AM to 11:30AM. A cycle in Doraville is still to be determined.
Note on C1: T A: Type in the name of your Approvied Strategy. ---- Overall, this DAP is prepared very well. -Tiffiany Aholou
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## SSC- DAP (2015-2016)
Approved Strategy Name: |  | Sticker Shock Campaign
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Coordinate with CPACS to plan Sticker Shock for 2016 | Come up with a SS strategy for 2016 so that it's mutually beneficial to CETPA and CPACS in its efforts | CETPA and CPACS APP coordinators | Meet with CPACS to discuss how to implement the campaign for 2016 | CETPA Prevention | CETPA | 2015-10-01 | 2015-10-07 | 2015-10-14 | 2015-10-14 | November 2015- PC made contact with CPACS on November 23rd to discuss implementation for Doraville and Sandy Springs. It was discussed that we are not going to change the sticker design because there was a lot of positive feedback in terms of the color and message according to the retail evaluation forms. October 2015- It was discussed with both PCs from CPACS and CETPA that the sticker design from both organizations will not be changed because of the positive feedback from business owners and customers.
|  |  | Create a sticker/cling design that both providers will use in the implementation | CPACS | CETPA/CPACS | 2015-10-01 | 2015-10-16 | 2015-10-14 | 2015-10-14 | November 2015- PC made contact with CPACS on November 23rd to discuss implementation for Doraville and Sandy Springs. It was discussed that we are not going to change the sticker design because there was a lot of positive feedback in terms of the color and message according to the retail evaluation forms. October 2015- It was discussed with both PCs from CPACS and CETPA that the stickerdesign from both organizations will not be changed.
|  |  | Check on price for paper bags with SS message and if stores will use for single serve products | Community | CETPA | 2015-10-01 | 2015-10-16 | 2015-10-14 | 2015-10-14 | November 2015-At this time it is not necessary to purchase paper bags because we still have a good amount left for us to use for the campaign.October 2015- CETPA PC has been researching the pricing on the paper bags, but still has extra from previous implementation year.
Re-evaluate the strategy | Revise the evaluation of 2015 and re-evaluate if is necessary to do any change to the steps and/or the design. | Hispanic parents and adult in general | 1. Revise Merchant Evaluations for 2015 strategy and analyze the possible changes that are necessary in order to have better results. | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-01-18 | 2016-01-22 | 2016-01-25 | 2016-01-25 | January 2016- PC has been analyzing the Merchant Evaluations for 2015.
|  |  | 2. Make any necessary changes acording to the feedback received (stickers & posters; volunteers ID, door stickers) | Graphic design office | APP Staff, CPAW | 2016-01-18 | 2016-01-22 | 2016-01-25 | 2016-01-25 | January 2016- PC and PC from CPACS met and came to the conclusion tha the first cycle should be implemented in April instead of March, due to the fact that Alcohol Awareness Month is in April.
|  |  | 3.Having the design approved by State | CETPA Prevention | APP Staff | 2016-01-18 | 2016-01-22 | 2016-02-01 | 2016-02-29 | March 2016- It is not necessary to make any changes at this time. February 2016- It is not necessary to make any changes at this time.
Printing the material | To have all the materials ready for the implementation of the strategy in the stores. | Hispanic parents and adult in general | 4. Print the material | Graphic design office | APP Staff | 2016-01-18 | 2016-01-18 | 2016-02-01 | 2016-02-29 | March 2016- It is not necessary to make any changes at this time. February 2016- It is not necessary to make any changes at this time.
Partnerships with retail stores | Owners of the retail establishments to agree on the distribution of the stickers and posters | Retail Stores Owners/managers | 1. Contact retail stores managers/owners that participated in 2015 strategy. Invite them to support the strategy again. | Shopping centers and stores in each community | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-01 | 2016-03-31 | March 2016- PC made contact with the retail store owners who participated on the campaign asking if they are willing to participate again for 2016. It was decided that the campain will begin in April 2016 because it was alcohol awareness month and it would be more appropriate for the cause.
|  |  | 2. If is necessary, contact new stores. | Shopping centers and stores in each community | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-01 | 2016-03-18 | March 2016- PC made created a partnership wth Dekalb Chamber of Commerce and are willing to support the startegy.
|  |  | 3. If is necessary prepare an invitation letter for new stores. | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-28 | 2016-04-01 | March 2016- PC has prepared an invitation letter for the new stores to distribute.
|  |  | 4. Visiting the new retail stores to personally meet owners/managers and provide them the invitation. Explaining the goal of the campaign. | Stores in the community | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-28 | 2016-04-01 | March 2016- PC has a plan to visit new and previous stores explaining the goal of the campaign.
|  |  | 5. Contact and confirm with the new retail stores owners/managers the agreement to participate in the strategy. | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-28 | 2016-04-01 | March 2016- PC made contact with the retail store owners who participated on the campaign asking if they are willing to participate again for 2016. It was decided that the campain will begin in April 2016 because it was alcohol awareness month and it would be more appropriate for the cause.
|  |  | 6. Coordinate with all retail stores owners/ managers the schedule for distribution of the stickers and other material. | Stores in the community | Veronica Melara, Project Coordinator | 2016-01-25 | 2016-02-12 | 2016-03-28 | 2016-04-01 | March 2016- PC made contact with the retail store owners who participated on the campaign asking if they are willing to participate again for 2016. It was decided that the campain will begin in April 2016 because it was alcohol awareness month and it would be more appropriate for the cause.
Contact and Invite Local Media to cover the implementtion of the program in the retail stores. | To have the local media to agree in covering the event | Media | 1. Prepare press release with information of the strategy and invititation to cover the event. | CETPA Prevention | APP Staff | 2016-02-22 | 2016-02-25 | 2016-03-28 | 2016-04-01 | March 2016- PC has contacted Mundo Hispanico to cover the campaign.
Conduct the first phase of the strategy | Distribuite 3,000 stickers in 20 retail stores within the three communities. | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | Veronica Melara, Project Coordinator | 2016-04-04 | 2016-04-29 | 2016-03-15 | 2016-04-01 | March 2016- PC made contact with the retail store owners who participated on the campaign asking if they are willing to participate again for 2016. It was decided that the campain will begin in April 2016 because it was alcohol awareness month and it would be more appropriate for the cause.
|  |  | 2. Prepare an appreciation certificate for the stores that will participate in the strategy. | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-04-04 | 2016-04-29 | 2016-03-01 | 2016-03-31 | March 2016- PC has prepared an invitation letter for the new stores to distribute.
|  |  | 3. Contacting volunteers to confirm dates of the implementation | CETPA Prevention | APP Staff | 2016-04-04 | 2016-04-29 | 2016-03-31 | 2016-04-01 | March 2016- PC met with HEROES director to plan the sticker shock campaign while they are in spring break the first week of April.
|  |  | 4. Distribute the stickers and posters in the three communities. Present the certificate to the store owners/managers. | Stores in the community | APP Staff | 2016-04-04 | 2016-04-29 | 2016-04-08 | 2016-05-27 | May 2016- PC implemented the Sticker Shock Campaign in Norcross on April 8th. Alongside the Director of CETPA's Prevention Clubhouse, Michelle Baroni, Sergio Lozano and the HEROES youth members who helped support the campaign. The morning of the event, the PC trained the HEROES on how to place the stickers, making sure they don't cover bar codes or labels. It was explained that they are not allowed to handle the alcohol. PC explained why this campaign is to be implemented; to raise awareness and educate the adults on the consequences if they were to provide alcohol to minors. 10 Stores were visited and the store owners were very welcoming. 2000 stickers were placed among all 10 retail establishments. The customers were very curious of the HEROES members placing the stickers on the boxes of alcohol. Students from Georgia Highlands College participated in the campaign. In Sandy Springs 1500 stickers were placedin 6 stores. In Doraville, 400 stickers were placed in 3 stores. . Again, they are not allowed to handle the alcohol, only those of age can pick them up and move them while the youth place the stickers. The youth would explain to the adults why they are raising awareness on undeage drinking. The adults were very pleased that the youth are making a difference in the community.
Conduct the second phase of the strategy | Distribuite 700 stickers in 30 retail stores | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | Veronica Melara, Project Coordinator | 2016-05-02 | 2016-05-16 | 2016-05-02 | 2016-05-27 | June 2016- PC contacted the students from Georgia Highlands College informing them that we are to implement the last cycles in Doraville and Sandy Springs. For the Norcross location PC had a meeting with the Prevention Clubhouse Director, Michelle Baroni and she has agreed to support our strategy and the HEROES members will be will be helping us. The store owners were contacted as well and they were very welcoming and the Merchant Evaluations will be distributed in all locations. . May 2016- Since the PC started the campaign very late, she decided to inform all retail establishments that her team will be coming back for a second phase within a month or so.
|  |  | 2. Contacting volunteers to confirm dates of the implementation | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-05-16 | 2016-05-27 | 2016-05-27 | 2016-05-27 | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled. May 2016- While implementing the remaining retail establishments in Doraville cycle, PC informed the volunteers that the second cycle will be implemented in the next month or so.
|  |  | 3. Distribute the stickers and posters in the three communities. | Stores in the community | APP Staff | 2016-05-30 | 2016-06-10 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
Recruiting volunteers/ CPAW members | To have enough volunteers and staff to complete the strategy | Volunteers | Having a meeting with Youth Advisory Team HEROES directors and CPAW members to explaining to them the strategy and confirm their participation. | CETPA Prevention | Veronica Melara, Project Coordinator | 2016-05-16 | 2016-05-27 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
Training volunteers | To explain to them the process of the implementation | Volunteers | Having a meeting with volunteers and explaining to them step by step how to conduct the strategy. | CETPA Prevention | APP Staff | 2016-05-16 | 2016-05-27 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
Publish a newspaper article with the results of the strategy | Inform the community the results of the implementation and give a public appreciation to the retail stores that support the strategy. | Hispanic parents and adult in general | 1. Prepare an article with pictures of the implementation of the strategy and names of retailo stores. Publish sticker shock article with pictures in newspaper. | CETPA Prevention | APP Staff | 2016-05-23 | 2016-05-26 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
|  |  | 2. Publish the article in one newspaper. | Newspaper | APP Staff | 2016-05-26 | 2016-05-26 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
Evaluation | Evaluate the results of the strategy and the feedback from the store owners/managers | Store owners/managers | 1. Distribute and collect the Merchant Evaluation form to the store owners/managers. | Stores in the community | APP Staff | 2016-05-30 | 2016-06-10 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
|  |  | 2. Revise the feedback and analyze the changes that will be necessary to implement in the future. | CETPA Prevention | APP Staff/CPAW | 2016-06-13 | 2016-06-24 |  |  | June 2016- In July all cycles will be implemented. On July 5th the Doraville location is scheduled, July 8th Sandy Springs, July 13th Norcross is scheduled.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## BTW-DAP (2015-2016_
Approved Strategy Name: |  | Be The Wall
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Continue with Marketing Campaign |  |  | Continue to disseminate message. Detemine activities, time frames, and marketing mediums to continue to reach the target population. | CETPA Prevention | APP Staff, CPAW, Marketing Coach. | 2015-10-01 | 2016-04-11 | 2015-10-01 | Ongoing | December 2015- On December 2nd, I attended a Parent/Teacher Conference at Oakcliff Elementary School in Doraville and collected intercept surveys and pledges. On December 3rd and 4th, I went to clinics in Sandy Springs and Doravlle to collect intecept surveys. There was a Parent/Teacher Conference in Lake Forest Elementary School and many intecept surveys were collected. HIgh Point Elementary School also held a conferce and interceot surveys were collected there as well. On December 17th, CIMA hosted a Babyshower event for first time mothers, and I gave a mini workshops on dangers of drinking while pregnant and also on the "be the wall" Campaign and they signed the pledge. Its been a challenge trying to get the principals to be on board with placing the spanish banners in the schools. We just received the new banners in English and Spanish. Sequoyah Middle school is the first school that approved for us to place a large banner at the entrance of the school, thanks to the Lead School Counselor, Jean Damrich and she also welcomed for us to place more items if need be. For the campaign, I attend community fairs, schools gatherings and events to promote the message and has parents sign pledges. PC visits clinics and organization and collects pledges and intercept surveys. As of right now, I've collected 121 surveys in Sandy Springs, 96 in Doraville and 68 in Norcross. Its also been a challenge collecting the surveys, especially during the holiday season and with the many obligations with the other strategies. November 2015- PC has been attending several fairs and events throughout the month. On November 13th, PC attended the Health Fair Event in Meadowcreek High School. On November 14th, there was another Health Fair in Lake Forest Elementary School and many promotional items were distributed. It was very successful and many pledges were signed. On November 19th, In Sequoyah Middle school there were Parent/Teacher conferences that took place and over 200 parents attended. Promotional items were distributed to all. Sequoyah Middle school is the first school that approved for us to place a large banner at the entrance of the school, thanks to the Lead School Counselor, Jean Damrich and she also welcomed for us to place more items if need be. A supply list of "Be the Wall' items were ordered. October 2015- PC has been attending several fairs and events throughout the month. On October 1st, PC attended the Mulicultural Event in Meadowcreek High School. On October 8th, CETPA's Dreamers Clubhouse held a healthfair and many promotional items were distributed. On October 10th, PC attended the 11th annual Tea Walk in CPACS. Not many Latinos attended, but it was a great event. On October 16th, Families First hosted a healthfair at the Norcross First United Methodist Church. It was very successful and many pledges were signed. On On October 27th, CPACS collaborated with us on a workshop talking about how to speak to your children about drugs and alcohol, in Sequoyah Middle School in Doraville and promoted the BTW message.
Continue with the collection of data | Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Collect Intercept surveys | Community Partner Facilities | APP Staff | 2015-10-01 | 2015-11-01 | 2015-10-19 | 2016-03-10 | April-It was decided to only conduct one set of intercept surveys and then the post tests. Because for evaluation purposes, they didn't see it as necessary. January 2016- Sequoyah Middle school is the first school that approved for us to place a large banner at the entrance of the school, thanks to the Lead School Counselor, Jean Damrich and she also welcomed for us to place more items if need be. For the campaign, PC attends community fairs, schools gatherings and events to promote the message and has parents sign pledges. PC visits clinics and organization and collects pledges and intercept surveys. PC has made a partnership with the CIMA. December 2015- On December 2nd, I attended a Parent/Teacher Conference at Oakcliff Elementary School in Doraville and collected intercept surveys and pledges. On December 3rd and 4th, I went to clinics in Sandy Springs and Doravlle to collect intecept surveys. There was a Parent/Teacher Conference in Lake Forest Elementary School and many intecept surveys were collected. HIgh Point Elementary School also held a conferce and interceot surveys were collected there as well. On December 17th, CIMA hosted a Babyshower event for first time mothers, and I gave a mini workshops on dangers of drinking while pregnant and also on the "be the wall" Campaign and they signed the pledge. Its been a challenge trying to get the principals to be on board with placing the spanish banners in the schools. We just received the new banners in English and Spanish. Sequoyah Middle school is the first school that approved for us to place a large banner at the entrance of the school, thanks to the Lead School Counselor, Jean Damrich and she also welcomed for us to place more items if need be. For the campaign, I attend community fairs, schools gatherings and events to promote the message and has parents sign pledges. PC visits clinics and organization and collects pledges and intercept surveys. As of right now, I've collected 121 surveys in Sandy Springs, 96 in Doraville and 68 in Norcross. Its also been a challenge collecting the surveys, especially during the holiday season and with the many obligations with the other strategies. November 2015- The PC made contact with agencies within the three communities, Norcross, Doraville, and Sandy Springs, to participate in the “Be the Wall” campaign. The PC has visited agencies and clinics collecting intercept surveys. Not many intercept surveys were collected because of the lack of attendance at the fairs. They couldn't be collected in the parent teacher conferences because they were very strict on timing of the meetings. October 19th, PC started collecting intercept surveys in Sandy Springs. Georgia Tech hosted an event in Meadowcreek High School and there wasn't a good turn out, but the population that attended were very greatful and appreciated our attendance.
|  |  | Submit 2nd set of Intercept surveys to evaluators | CETPA Prevention | APP Staff | 2015-11-03 | 2015-11-07 | 2016-03-10 | 2016-03-10 | April 16-It was decided to only conduct one set of intercept surveys and then the post tests. Because for evaluation purposes, they didn't see it as necessary. March 2016- The first set of intercept surveys was sent to the evaluators. February 2016- PC has collected the intercept surveys. Its also been a challenge collecting the surveys, especially during the difficult weather and with the many obligations with the other strategies. We hope to turn in the intercept surveys in the month of March. Its been challenging to collect the surveys due to other obligations for the other strategies.January 2016- As of right now, I've collected 130 surveys in Sandy Springs, 105 in Doraville and 77 in Norcross. Its also been a challenge collecting the surveys, especially during the difficult weather and with the many obligations with the other strategies. We hope to turn in the intercept surveys in the month of February. December 2015-The intecept surveys havent been sent. November 2015- We are in the process of collecting intercept surveys and have not yet submitted them to the evaluators. November 2015- We are in the process of collecting intercept surveys and have not yet submitted them to the evaluators.
|  |  | Evaluator develops Intercept survey results | Evaluators office | Evaluator | 2015-11-07 | 2015-11-30 | 2016-03-10 | 2016-04-10 | April- Rapid Feedback Report was created with outcomes from strategies. March 2016- Since we just turned in the surveys, they are in the process of developing the results. February 2016- Its also been a challenge collecting the surveys, especially during the difficult weather and with the many obligations with the other strategies. We hope to turn in the intercept surveys in the month of March. January 2016- Its been a challenge collecting the surveys, especially during the difficult weather and with the many obligations with the other strategies. We hope to turn in the intercept surveys in the month of February.December 2015- The intecept surveys havent been sent. November 2015- We are in the process of collecting intercept surveys and have not yet submitted them to the evaluators. November 2015- We are in the process of collecting intercept surveys.
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2014-12-01 | 2015-12-20 | 2016-04-15 | 2016-04-15 | April- Will present results during next CPAW meeting March 2016- Since we just turned in the surveys, they are in the process of developing the results. February 2016- We hope to send the surveys in the month of March. Its been challenging to collect the surveys due to other obligations for the other strategies.
| Set goals and plan the first phase of the marketing campaign. | Hispanic parents and adults in general | Discuss with CPAW members places where we can continue exposing the message to the target population. | CETPA Prevention | APP Staff, CPAW, Social Marketing coach. | 2015-11-21 | 2015-12-19 | 2016-04-15 | 2016-04-15 | April- Will present results during next CPAW meeting March 2016- Since we just turned in the surveys, they are in the process of developing the results. February 2016- We hope to send the surveys in the month of March. Its been challenging to collect the surveys due to other obligations for the other strategies.
Re-evaluate the strategy | Revise the evaluation of 2015 and re-evaluate if is necessary to make any changes | Hispanic parents and adults in general | Revise intercept survey results of 2015 strategy and analyze the possible changes that are necessary in order to have better results. | CETPA Prevention | APP Staff | 2016-01-04 | 2016-01-15 | 2016-04-18 | 2016-04-18 | April 2016- Upon Community's Feedback and TA with RPS and Evaluation team, we will move to next phase of the strategy. March 2016- Since we just turned in the surveys, they are in the process of developing the results.
Managing/ implement the Campaign | Running the marketing campaign on a regular basis. It includes placing print and broadcast media messages, leading activities and managing interaction with the community. | Hispanic parents and adults in general | Review the list of marketing materials from previous year and comparing appropriateness for this year. Choose additional materials accordingly with the target population. (Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff, CPAW, | 2016-01-04 | 2016-01-15 | 2016-03-01 | 2016-03-01 | March 2016- We still have plenty of material.
|  |  | Purchase additional marketing material (Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff | 2016-01-04 | 2016-01-15 | 2016-03-01 | 2016-03-01 | March 2016- We still have plenty of material, there is no need to purchase at this moment.
|  |  | Distribute supporting marketing material | Places in the community chosen to expose the logo/message. | APP staff, CPAW, Community partners | 2016-01-18 | 2016-04-11 | 2016-01-18 | Ongoing | March 2016- I attend community fairs, schools gatherings and events to promote the message and has parents sign pledges. PC visits clinics and organization and collects pledges and intercept surveys.
Planning the ongoing evaluation process | Prepare and conduct a follow up process with the community in order to evaluate the effectiveness of the campaign. | Hispanic parents and adults in general | Identify areas where the logo has been exposed in order to conduct intercept surveys. | Places in the community chosen to expose the logo. | APP Staff, CPAW, evaluator. | 2016-01-18 | 2016-01-23 | N/A |  | May 2016- In April we had a TA session with the RPS Nykia Greene-Young, Director Jeniffer Manon, and our evaluator Shenee Bryan. Upon finding out of some resistance the community was displaying for political reasons, in relation to the wall image in the campaign, it was decided to move on to the second phase of implementation where we are showing a new message to the community. The message reads (from Spanish); You have taught them how to walk, now teach them to walk away from alcohol. (English Version: They may have grown, but they have not outgrown you). This tested to be more appealing amongts the community we are reaching to, given that there are many families in our zip codes, and they are culturally family oriented. We are making the appropriate arrangements to display the message locally and through media venues, such as Mundo Hispanico, and La Vision. The new poster has been placed in many clinics and stores throughout all three communities, in english and spanish. March- It was decided to only conduct one set of intercept surveys and then the post tests. Because for evaluation purposes, they didn't see it as necessary.
|  |  | Conduct and collect the third set of intercept surveys (second of the year). | Places in the community chosen to expose the logo. | APP Staff | 2016-01-26 | 2016-02-26 | N/A
| Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Intercept Surveys sent to Evaluators | Evaluators office | APP Staff | 2016-02-28 | 2016-03-06 | N/A
Evaluating the Survey results |  |  | Evaluator develops survey results | Evaluators office | Evaluator | 2016-03-27 | 2016-04-01 | N/A
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2016-04-01 | 2016-04-15 | N/A
|  |  | Analyze intercept surveys and make ajustments to the marketing campaing if is necessary. | Evaluators office | Evaluator | 2016-04-15 | 2016-04-24 | N/A
|  |  | Purchase additional marketing material (As needed-Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff | 2016-04-27 | 2016-05-01 | 2016-03-01 | 2016-03-16 | June 2016- PC contacted Univision and Telemundo for the to air a 15-20 second PSA commercial in their TV stations. PC has contacted Radio Kerigma and Radio Informacion also. PC will be contacting previous radio stations that we've worked with in the past. We are in the process of putting together the voice over for the poster and we are working with team of young men, known as The Escaped Artist. As soon as its finalized we will be sending it for approval and to the media outlets. March 2016- We still have plenty of material, there is no need to purchase at this moment.
Continue distributing marketing material | Continue running the marketing campaign on a regular basis. Placing print and broadcasting media messages, leading activities and managing interaction with the community. | Hispanic parents and adults in general | Placing print, promoting logo and broadcasting media messages, leading activities and managing interaction with the community. | Places in the community chosen to expose the logo. | APP staff, CPAW, Community partners | 2016-05-11 | 2016-09-30 | 2006-05-11 | Ongoing | June 2016- PC contacted Univision and Telemundo for the to air a 15-20 second PSA commercial in their TV stations. PC has contacted Radio Kerigma and Radio Informacion also. PC will be contacting previous radio stations that we've worked with in the past. We are in the process of putting together the voice over for the poster and we are working with team of young men, known as The Escaped Artist. As soon as its finalized we will be sending it to the media outlets. May 2016- PC has been attending several fairs and events throughout the month. Sequoyah Middle school is the first school that approved for us to place a large banner at the entrance of the school, thanks to the Lead School Counselor, Jean Damrich and she also welcomed for us to place more items if need be. For the campaign, PC attends community fairs, schools gatherings and events to promote the message, and has parents sign pledges. On May 5th, she attended Radio Kerigma, since it was Cinco de Mayo it was appropriate to talk about the dangers of alcohol abuse. On May 9th, PC hosted a town hall meeting in Catholic Center in Sandy Springs and BTW information was given and the APP staff spoke about underage drinking and the importance of having a good relationship with child. On May 10, PC attended a Parent Teacher Connference in Sequoyah Middle School and collected pledges and conducted a mini workshop on underage drinking. On May 14, PC attended a CIMA Healthfair and promoted the BTW campaign and gave a mini workshop on how to communicate with their children about drinking. Later that day PC paricipated on Radio Kerigma and spoke about alcoholism. During the SFP Graduation, parents were also presented with the BTW message, as the youth took their Post tests. Nine adults signed the pledge agreeing to "be a protective wall" between themselves and the youth. PC has been placing the new poster in different locations such as clinics, attorneys offices, stores and schools. March 2016- I attend community fairs, schools gatherings and events to promote the message and has parents sign pledges. PC visits clinics and organizations.
Planning the ongoing evaluation process | Prepare and conduct a follow up process with the community in order to evaluate the effectiveness of the campaign. | Hispanic parents and adults in general | Identify areas where the logo has been exposed in order to conduct intercept surveys. (POST TESTS) | Places in the community chosen to expose the logo. | APP Staff, CPAW, evaluator. | 2016-05-18 | 2016-05-15 | 2016-05-11 | Ongoing | March 2016- PC constantly visits clinics and schools promoting the logo and message. PC has participated in school events, parent teach conferences and radio stations.
|  |  | Conduct and collect the fourth set of intercept surveys | Places in the community chosen to expose the logo. | APP Staff | 2016-05-15 | 2016-06-15 | N/A |  | June 2016- The post surveys are being developed. May 2016- In April we had a TA session with the RPS Nykia Greene-Young, Director Jeniffer Manon, PRoject Coordinator Veronica Melara, and our evaluator Shenee Bryan. Upon finding out of some resistance the community was displaying for political reasons, in relation to the wall image in the campaign, it was decided to move on to the second phase of implementation where we are showing a new message to the community. The message reads (from Spanish); You have taught them how to walk, now teach them to walk away from alcohol. (English Version: They may have grown, but they have not outgrown you). This tested to be more appealing amongts the community we are reaching to, given that there are many families in our zip codes, and they are culturally family oriented. We are making the appropriate arrangements to display the message locally and through media venues, such as Mundo Hispanico, and La Vision. The new poster has been placed in many clinics and stores throughout all three communities, in english and spanish. March- It was decided to only conduct one set of intercept surveys and then the post tests. Because for evaluation purposes, they didn't see it as necessary. It was decided to only conduct one set of intercept surveys and then the post tests. Because for evaluation purposes, they didn't see it as necessary.
| Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Intercept Surveys sent to Evaluators | Evaluators office | APP Staff | 2016-06-16 | 2016-06-19 | N/A
Evaluating the Survey results |  |  | Evaluator develops survey results and waiting for results. | Evaluators office | Evaluator | 2016-07-06 | 2016-07-11 | N/A
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2016-07-11 | 2016-07-30 | N/A
|  |  | Collect Post surveys | CETPA Prevention | APP Staff | 2016-07-01 | 2016-08-15
|  |  | Submitting Post surveys | CETPA Prevention | APP Staff | 2016-08-15 | 2016-08-15
|  |  | Evaluate the results throughout the campaign | CETPA Prevention | APP Staff | 2016-08-22 | 2016-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY 14-15 Milestones at-a-glance
Strengthening Families Program
Sticker Shock Campaign
Be The Wall
Project Activities (Milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Continue with the collection of data | bar: Oct to Feb
Implementating Phase 1 | bar: Oct to Nov
Re-evaluate the strategy | bar: Nov to Jan
Recruitment of Families (Phase 2) | bar: Dec to Jan
Planning the marketing campaign | bar: Jan to Apr
Managing/ implement the Campaign | bar: Feb to Sep
Implementating Phase 2 | bar: Feb to Mar
Printing the Material | bar: Feb
Partnerships with Retail Stores | bar: Feb to Mar
Recruiting volunteers/ CPAW members | bar: Mar
Contact and Invite Local Media . | bar: Mar
Training Volunteers | bar: Mar
Conduct Phase 1 of Implementation | bar: Mar to Apr
Distribute marketing material | bar: Apr to Sep
Planning the ongoing evaluation process | bar: Apr to Sep
Prepare and conduct a follow up process with the community | bar: Apr to Sep
Recruitment of Families (Phase 3) | bar: Apr to May
Conduct Phase 2 of Implementation | bar: May to Jul
Implementating Phase 3 | bar: Jun to Jul
Publish a newspaper article with the results of the strategy | bar: Jun
Evaluation | bar: Jul
Note on A6: T A: Enter the Milestone Activities chronlogically. Color-code the timeline by assigning a color for each strategy. Include a LEGENDon the side for readers to comprehend at a glance. Refer to Column A from each Strategy DAP. For each activity in this column, Providers are to fill in the cell where they anticipate the activity starting through its anticipated end date. Since the chart is set up according to months and not weeks, filling in one cell suggests that the activity will be complete within that month.