## Provider & CPAW Info
Provider Information
Provider Name | CETPA, Inc.
Project Coordinator | Oralia Luevano
State Priority | Goal 2: Reduce access to alcohol and binge drinking among 9-20 year olds
Approved IV/CF | Social Availability: provision to Minors; Social Availability: available laces to drink, lack of parental monitoring of supply of alcohol; Pereption of Risk: perception of harm of drinking, perception of risk
Assigned Communities & Community Readiness Score (CRS) | Dalton, GA zip codes: 30720, 30721
Community 1/CRS | Dalton, GA 30720 - 3- Vague Awareness
Community 2/CRS | Dalton, GA 30721 - 4- Preplanning
Community 3/CRS
Community 4/CRS
Community 5/CRS
Community 6/CRS
Community 7/CRS
Memorandum of Agreement Information
Partner/Consultant Information | Role | Pending | Confirmed
America Gruner | CPAW member |  | X
Jesus Luevano | CPAW member |  | X
Samantha Trejo | CPAW member |  | X
Maria Sanchez | Community member | x
CLILA | Provide space, volunteers |  | X
Veronica Sanchez | Community member | x
Lorena Ibarra | Community member | x
Ismael Band | CPAW member |  | X
Juan Botello | Community member | x

## PMP for BTW
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Be The Wall
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Social Availability - CF: Available places to drink; lack of parental monitoring of supply of alcohol
Strategy Intent: | Increase knowledge about underage drinking and promote responsabibilities in adults to monitor youth activities and restrict access.
Target Audience: | Hispanic parents and adults in general
IOM Category | Universal and Selective
Estimated Reach: | 30% of the Latinos in Dalton (9,239)
What is the dosage for this strategy? | This information will be determined during the planning step with the advice of the CPAW and the developers of the strategy. Since we moved to this strategy on June 2014 we need further discussion with coach.
How frequent will the strategy be implemented? | This information will be determined during the planning step with the advice of the CPAW and the developers of the strategy
Necessary Resources for Successful Implementation | Staff, Trainings, Materials and Supplies, Evaluator
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: |  | Oralia Luevano
Number of staff to be hired/contracted: | One local evaluator | Jeniffer Manon, APP Director | Ongoing | Contracts, job expectations | Signed contract
Staff/Consultant Recruitment Strategy | Eval Group has worked with CETPA in the past successfully and we will keep her | Jeniffer Manon, APP Director | Ongoing | Contracts, job expectations | Signed contract
Staff/Consultant Training | PC, all APP staff, and evaluator received training about the strategy | Jeniffer Manon, APP Director | 2014-07-14 | The strategy just requires an online training. We also participated in a webinar facilitated by the developers and hosted by the state coaches. | The online training is on your own and the second webinar showed the names of who participated.
Staff Retention Strategy | Contracts and payment | CETPA's Admin Staff | Ongoing | Contracts, job expectations | Signed contract
Additional Training | If needed | PC | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | Since the community readiness is very low we have to use low intensity activities that will make it unfeasible to reach the entire Latino parents & adults | PC and APP staff | Ongoing | Job description | Not sure yet
Retention Strategies | TBD | PC and APP staff | Ongoing | TBD | TBD
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Make one on one visits with the community stakeholders and members | Create and/or reinforce partnerships with different groups in the community who serve Latino/Hispanic population (including CPAW members) to encourage them to involve the underage drinking problem and prevention efforts to their agendas. Provide them information and materials. | APP Staff | Ongoing | Recording meetings with parents, youth, and stakeholders by signing in. To use evaluation forms to acquire information about their perception of the issue. | Participants considered that the underage drinking is a problem.
Begin to initiate our own events and participate on ongoing events that are attended by Latinos in Dalton | Use workshops, presentations, and awareness materials such as brochures and the "Alcohol: the Unknown Drug" documentary in Spanish. | PC and PC Assistant | Ongoing | Sign in sheets, pictures, videos, pledges | Community readiness assessment done at the end of the grant year
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | NA | NA | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2015-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP for PYPM
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Protecting You/Protecting Me
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Perception of Risk > Perception of harm of drinking, perception of risk
Strategy Intent: | Increase the perception of harm of drinking alcohol on students of fourth and fifth grade
Target Audience: | Latino fourth and fifth graders
IOM Category | Selected
Estimated Reach: | 40 to 50 students
What is the dosage for this strategy? | 6 sessions for youth and 1 workshop for parents each time we implement
How frequent will the strategy be implemented? | Twice per grant year
Necessary Resources for Successful Implementation | PYPM trained facilitators, PYPM curriculum, supplies and materials, two classrooms, evaluator
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy:
Number of staff to be hired/contracted: | Two bilingual PYPM facilitators. These facilitators have experience teaching PYPM | PC, CPAW member | 2015-10-01 | MOU and or contract | By observation, qualified facilitator
Staff/Consultant Recruitment Strategy | Use the services of the facilitators that facilitated last time | PC | 2015-10-01 | MOU and or contract | Hire qualified bilingual facilitators experienced with PYPM and working with youth
Staff/Consultant Training | PC, America Gruner, Sharon Diaz | PC | 2015-10-01 | Facilitators completed six hours of training. | During the sessions, the APP Director will be present in some of the sessions
Staff Retention Strategy | Payment, PYPM training, clear goals and expectations, support by CETPA APP staff. Inkind donations for snacks and free facilities. Remind parents by phone to bring their children and confirm attendance. | APP Director | Ongoing | Sign in sheets | 100% staff retention.
Additional Training | If needed | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | Recruitment is coordinated by PC and America Gruner, CLILA President. Raquel Cardona from Whitfield County Public Shools will also assist in the recruitment among the families they already serve by promoting the PYPM program verbally and through flyers and filling out registration forms. No screener is necessary. The children will be Hispanic fourth and fifth graders. | PC | 10/3/2015 First Cycle 2/27/2016 Second Cycle | Student registration form and parent consent | To have students registered before the initiation of each cycle.
Retention Strategies | Self motivation and initiative, inkind donation of snacks and incentives. Building relationships with them, sharing information, giving them positive feedback on their efforts, participating in other stakeholders events and meetings. | PC and PC Assistant | Ongoing | Sign in sheets, MOUs, emails | 80% participants retention.
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Denial/resistance 30720, 30721 | Increase awarenesss by participation in CLILA events with educational material and workshops | PC | Ongoing | Number of material handled | PYPM registration forms
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | Facilitators' completion of PYPM training. We will use the PYPM curriculum and materials | PC | Already trained. Curriculum already purchased | N/A | N/A
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2016-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP Sticker Shock
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Sticker Shock Campaign
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Social Availability > Provision to minors
Strategy Intent: | Reduce the number of minors who access alcohol from adults
Target Audience: | Hispanic adults in Dalton
IOM Category | Universal
Estimated Reach: | 5 to 10 retailers
What is the dosage for this strategy? | 3,000 total stickers in English and Spanish distributed among five stores, 1,000 per cycle. Paper bags will also be used to accommodate retailers' needs.
How frequent will the strategy be implemented? | 3 cycles
Necessary Resources for Successful Implementation | CPAW members, volunteers, design and reproduction of stickers and fridge clings.
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: |  | PC
Number of staff to be hired/contracted: | None, we will use CPAW members and/or volunteers | PC | December 2015, March 2016, June 2016 | Picture during the implementation in each retail store. Form to keep record of the number of stickers distributed. | Confirm 5 Latino stores, 5 signed pledges, number of stickers, and clings.
Staff/Consultant Recruitment Strategy | We already have a group set for this strategy | PC
Staff/Consultant Training | Re-Training to volunteers and training to new ones, MADD model | PC | 2015-12-01 | Sign in sheet | NA
Staff Retention Strategy | T-shirt, training, engagement in person and by phone, share information | PC | Ongoing | NA | NA
Additional Training | N/A | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | Contact merchants in person, coordinate dates/times, reproduce stickers and clings. Volunteers will participate in the sticker, clings, and posters placement. | PC and assistant | December 2015, March 2016, June 2016 | A record with the number of times we contact the store managers | In person visits, phone calls
Retention Strategies | Self motivation and initiative. After the end of the first visit, each owner or manager will receive a certificate of appreciation for their support. We also are going to publish a newspaper article with the names of the retail stores that will participate in the strategy. | PC | December 2015, March 2016, June 2016 | Number of merchants committed | Certificates of appreciation, pictures, newspaper article
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Vague awareness 30720. Continue one on one visits and encourage those you have spoken to asist. | The cartons will have stickers placed and the person who purchases will take it with them, the clings stay permanently in the fridge and the store. | PC | Ongoing | Recording number of visits with the retail stores. | 90% of the participants will sign the pledge
Preplanning 30721. Post flyers and posters related with the sticker shock message | The clings,and stickers will have the legal consequences of serving alcohol to minors. For both zip codes we will publish an article in the local newspaper presenting the legal and health consequences of UAD and the SSC efforts in the community. | PC | December 2015, March 2016, June 2016 | Keep record on the number of posters distributed and also pictures of the posters in the stores. | 90% of the stores wil allow us to distribute the glass clings in the stores.
To point out media articles to describe the underage drinking and the provision to minors issues. | We are going to publish a newspaper article discussing the facts about the provision to minors within the Latino/Hispanic community and the consequences of the problem. | PC | 2016-08-01 | Copy of the actual article | For the articles to be published in the newspaper
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | The steps will be according to SSC steps. | PC | NA | SSC surveys | SSC surveys completed
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Eval Group | 2015-09-01
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## FY15-16 DAP for BTW
Approved Strategy Name: |  | Be The Wall
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Continue with Marketing Campaign |  |  | Continue to disseminate message. Detemine activities, time frames, and marketing mediums to continue to reach the target population. | CETPA Prevention | APP Staff, CPAW, Marketing Coach. | 2015-10-01 | 2016-04-11 | 2015-10-01 | on going
Continue with the collection of data | Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Collect Intercept surveys | Community Partner Facilities | APP Staff | 2015-10-01 | 2015-11-01 | 2015-10-01 | 12/05/015
|  |  | Submit 2nd set of Intercept surveys to evaluators | CETPA Prevention | APP Staff | 2015-11-03 | 2015-11-07 | 2015-11-02 | 2015-12-05
|  |  | Evaluator develops Intercept survey results | Evaluators office | Evaluator | 2015-11-07 | 2015-11-30 | 2015-11-02 | 2015-12-05
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2014-12-01 | 2015-12-20 | 2015-12-05 | 2016-01-14
| Set goals and plan the first phase of the marketing campaign. | Hispanic parents and adults in general | Discuss with CPAW members places where we can continue exposing the message to the target population. | CETPA Prevention | APP Staff, CPAW, Social Marketing coach. | 2014-11-21 | 2014-12-19 | 2015-12-05 | 2015-12-19
Re-evaluate the strategy | Revise the evaluation of 2015 and re-evaluate if is necessary to make any changes | Hispanic parents and adults in general | Revise intercept survey results of 2015 strategy and analyze the possible changes that are necessary in order to have better results. | CETPA Prevention | APP Staff | 2015-01-04 | 2016-01-15 | 2016-01-14 | 2016-01-14
Managing/ implement the Campaign | Running the marketing campaign on a regular basis. It includes placing print and broadcast media messages, leading activities and managing interaction with the community. | Hispanic parents and adults in general | Review the list of marketing materials from previous year and comparing appropriateness for this year. Choose additional materials accordingly with the target population. (Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff, CPAW, | 2016-01-04 | 2016-01-15 | 2016-01-14 | 2016-01-14
|  |  | Purchase additional marketing material (Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff | 2016-01-04 | 2016-01-15 | 2016-01-14 | 2016-01-14
|  |  | Distribute supporting marketing material | Places in the community chosen to expose the logo/message. | APP staff, CPAW, Community partners | 2016-01-18 | 2016-04-11 | 2016-01-15 | on going
Planning the ongoing evaluation process | Prepare and conduct a follow up process with the community in order to evaluate the effectiveness of the campaign. | Hispanic parents and adults in general | Identify areas where the logo has been exposed in order to conduct intercept surveys. | Places in the community chosen to expose the logo. | APP Staff, CPAW, evaluator. | 2016-01-18 | 2016-01-23 | 2016-01-14 | 2016-01-14
|  |  | Conduct and collect the third set of intercept surveys (second of the year). | Places in the community chosen to expose the logo. | APP Staff | 2016-01-26 | 2016-02-26 | 2016-01-14 | 2016-02-27
| Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Intercept Surveys sent to Evaluators | Evaluators office | APP Staff | 2016-02-28 | 2016-03-06 | 2016-02-04 | 2016-02-29
Evaluating the Survey results |  |  | Evaluator develops survey results | Evaluators office | Evaluator | 2016-03-27 | 2016-04-01 | 2016-03-14 | 2016-04-28
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2016-04-01 | 2016-04-15 | 2016-04-22 | 2016-04-29 | The Stakeholder and the CPAW were glad to hear the positive outcome of BTW with 56% recalled seeing the logo amd 60% have seen the image more then once.
|  |  | Analyze intercept surveys and make ajustments to the marketing campaing if is necessary. | Evaluators office | Evaluator | 2016-04-15 | 2016-04-24 | 2016-04-22 | 4/28/216 | April 16- Based upon evaluation's recommendations. We will continue with our efforts as the population is receiving and understanding the message.
|  |  | Purchase additional marketing material (As needed-Depending upon results of the intercept surveys). | CETPA Prevention | APP Staff | 2016-04-27 | 2016-05-01 | 2016-04-16 | 2016-04-28 | April 16- May not be necessary as we continue our efforts with already purchased materials
Continue distributing marketing material | Continue running the marketing campaign on a regular basis. Placing print and broadcasting media messages, leading activities and managing interaction with the community. | Hispanic parents and adults in general | Placing print, promoting logo and broadcasting media messages, leading activities and managing interaction with the community. | Places in the community chosen to expose the logo. | APP staff, CPAW, Community partners | 2016-05-11 | 2016-09-30 | 2016-05-23 | 2016-06-03 | Rotated the banners that are in the same location just in different area, it was a recommendation for our TTA.
Planning the ongoing evaluation process | Prepare and conduct a follow up process with the community in order to evaluate the effectiveness of the campaign. | Hispanic parents and adults in general | Identify areas where the logo has been exposed in order to conduct intercept surveys. | Places in the community chosen to expose the logo. | APP Staff, CPAW, evaluator. | 2016-05-18 | 2016-05-15 | 2016-05-23 | 2016-05-23
|  |  | Conduct and collect the fourth set of intercept surveys | Places in the community chosen to expose the logo. | APP Staff | 2016-05-15 | 2016-06-15 | 2016-05-23 | 2016-06-10
| Identifying perceptions in the community about the consumption/provision of alcohol to minors | Hispanic parents and adults in general | Intercept Surveys sent to Evaluators | Evaluators office | APP Staff | 2016-06-16 | 2016-06-19 | 2016-06-10 | 2016-06-10
Evaluating the Survey results |  |  | Evaluator develops survey results and waiting for results. | Evaluators office | Evaluator | 2016-07-06 | 2016-07-11
|  |  | Present results to stakeholders and CPAW | CETPA Prevention | Evaluator, APP Staff | 2016-07-11 | 2016-07-30
|  |  | Collect Post surveys | CETPA Prevention | APP Staff | 2015-07-15 | 2015-08-28
|  |  | Evaluate the results throughout the campaign | CETPA Prevention | APP Staff | 2016-08-22 | 2016-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY15-16 DAP for PYPM
Approved Strategy Name: |  | PROTECTING YOU / PROTECTING ME
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Planning and Recruitment for Cycle 1 | Coordinate details for the program | 4th and 5th graders | 1. Meet with America Gruner, to review our experience to do our planning for next PYPM sessions. Review evaluators recommendations and findings from previous PYPM to take into consideration. Coordinate details like time and dates. | CLILA | PC and America Gruner | 2015-10-01 | 2015-10-15 | 2015-10-22 | 2015-10-22
|  |  | 2. Make a list of supplies and materials needed and purchase them | CLILA | PC and America Gruner | 2015-10-08 | 2015-10-30 | 2015-10-22 | 2015-10-22
|  |  | 3. Plan recruitment for Cycle 1 | Dalton | PC, CPAW members | 2015-10-08 | 2015-10-14 | 2015-10-10 | 2015-10-22
|  |  | 4. Recruit children and get parents' consent | Dalton | PC, America Gruner | 2015-10-14 | 2015-11-14 | 2015-10-10 | 2016-01-22 | Nov 15- We will continue recruiting for this cycle 1 since is going to start on February 2015
Conduct PYPM sessions to parents & youth | Implement PYPM sessions | Students of 4th and 5th grade and their parents. | 1. Deliver PYPM Cycle 1 | CLILA | PC, America Gruner, 2 assistants, child care person | 2015-11-14 | 2015-12-12 | 2015-11-09 | 2016-02-05 | Nov 15- Cycle 1 was postponed and it will start on February 2016 because facilitator America Gruner reported that co-facilitator Shanon Diaz wasn't able to help her for this Cycle, until February 2016. We cannot start, since they are the only people that have all the training requirements, and training is no longer available for new facilitators. We are having conversations with the developers of the program, to look for alternative options in case this problem prolongs. We have taking all the training necessary that is need for this workshop. We have 2 new Facilitators Iliana Martinez and Nancy Reynolds.
|  |  | 2. Administer pre and post-survey to the students at the beginning and end of PYPM | Dalton | PC, facilitators | 2015-11-14 | 2015-12-12 | 2015-11-09 | 2016-04-01 | We has finsh our first cycle in April 1, 2016 and adminster the post-test to each children.
Coordinate and facilitate parents workshop for Cycle 1 | Parent workshop | Parents of students who participated on PYPM | 3. Get all the materials and presentation ready for the parent workshop and coordinate and facilitate parent workshop after Cycle 1. | CLILA | PC | 2015-12-01 | 2015-12-12 | 2015-12-01 | 2016-04-01
Planning and Recruitment for Cycle 2 | Coordinate details for the program | 4th and 5th graders | 1. Meet with America Gruner to review our experience to do our planning for next PYPM sessions. Review evaluators recommendations and findings from previous PYPM to take into consideration. Coordinate details like time and dates. | CLILA | PC and America Gruner | 2015-12-15 | 2015-12-19 | 2015-12-15 | 2016-06-03 | After several attempts trying to communicate through email and phone calls, America Gruner doesn’t respond. Hazelden Betty Ford Foundation has given us the contact that is needed to rescheldule the date of the training. We will no longer be meeting with America Gruner since she can't no longer give the classes. The facilitators Iliana Martinez ans Nancy Reynolds will be meeting with them in March 24,2016, to review.
|  |  | 2. Make a list of supplies and materials needed and purchase them | CLILA | PC and America Gruner | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2016-04-22
|  |  | 3. Plan recruitment for Cycle 2 | Dalton | PC, CPAW members | 2016-01-15 | 2016-01-27 | 2015-01-22 | 2016-04-22 | we are going to start the 1st cycle in February 4, 2016 - March 11, 2016 and just right after the 1st cycle is done, we will be move on the the 2nd cycle.
|  |  | 4. Recruit children and get parents' consent | Dalton | PC, America Gruner | 2016-01-27 | 2016-02-27 | 2016-02-29 | 2016-04-28
Conduct PYPM sessions to parents & youth | Implement PYPM sessions | Students of 4th and 5th grade and their parents. | 1. Deliver PYPM Cycle 2 | CLILA | PC, America Gruner, 2 assistants, child care person | 2016-02-27 | 2016-04-02 | 2016-06-06 | on going | We will be moving the class from April 29 to June 03,2016 at the Community Center's Summer Camp. CLILA will no longer be participating in this program.
|  |  | 2. Administer pre and post-survey to the students at the beginning and end of PYPM | Dalton | PC, facilitators | 2016-02-27 | 2016-04-02 | 2016-06-06 | on going | We administer the pre-test on 6/6/2016 and the post-test will be done on 7/25/2016
Coordinate and facilitate parents workshop for Cycle 2 | Parent workshop | Parents of students who participated on PYPM | 3. Get all the materials and presentation ready for the parent workshop and coordinate and facilitate parent workshop after Cycle 2. | CLILA | PC | 2016-04-02 | 2016-04-02 | 2016-04-29 | 2016-06-03
Evaluation |  |  | 1. Be in constant contact with local evaluator | Dalton | PC, APP Director | 2015-10-01 | 2016-09-30 | 2015-12-01 | on going
|  |  | 2. Develop a report of the findings of all surveys submitted | Dalton | Eval Group | 2016-05-30 | 2016-06-30 | 2016-06-06 | on going
|  |  | 3. Provide findings to the CPAW members and stakeholders | Dalton | PC | 2015-07-01 | 2015-08-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on C4: CETPA: Since we alreay confirmed places, we only need to follow one step
Note on C11: CETPA: Since we alreay confirmed places, we only need to follow one step

## FY15-16 DAP for STICKER SHOCK
Approved Strategy Name: |  | Sticker Shock Campaign
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Re-evaluate the strategy | Revise the evaluation of 2013-2015 and re-evaluate if is necessary to do any change to the steps and/or the design. | Hispanic parents and adult in general | Revise Merchant Evaluations for 2013-2015 strategy and analyze the possible changes that are necessary in order to have better results. | Dalton | PC, CPAW | 2015-10-01 | 2015-10-10 | 2015-10-01 | 2015-10-10
|  |  | Make any necessary changes according to the feedback received (Ie. Colors, sizes, language) | Graphic design office | PC, CPAW | 2015-10-01 | 2015-10-10 | 2015-10-01 | 2015-10-10
|  |  | Contact/Confirm with stakeholders such as (Police Department, Chamber of Commerce, Local Churches, CLILA, amongst other local institutions/organizations) if they would be interested in being part of the collaboration for the campaign. | Dalton | PC, CPAW | 2015-10-01 | 2015-10-25 | 2015-10-01 | 2015-10-14
|  |  | Prepare invitation letter in English and Spanish for stores we'll visit, including logos from the collaborative. | Dalton | PC | 2015-10-01 | 2015-10-25 | 2015-10-01 | 2015-10-23
Partnerships with retail stores | Owners of the retail establishments to agree on the distribution of the stickers and posters | Retail Stores Owners/managers | Contact retail stores managers/owners that participated in 2013-2015 strategy. Invite them to support the strategy again. | Shopping centers and stores in each community | PC, CPAW | 2015-10-04 | 2015-10-25 | 2015-10-01 | 2015-10-23
|  |  | Contact new stores or stores that denied us in the past. | Shopping centers, pharmacies and stores in each community | PC, CPAW | 2015-10-04 | 2015-10-25 | 2015-10-01 | 2015-10-23
|  |  | Visiting the new retail stores to personally meet owners/managers and provide them the invitation. Explaining the goalof the campaign. | Stores in the community | PC. CPAW | 2015-10-25 | 2015-11-25 | 2015-10-23 | 2015-11-22
|  |  | Contact and confirm with the new retail stores owners/managers the agreement to participate in the strategy. | Dalton | PC | 2015-10-25 | 2015-11-25 | 2015-10-23 | 2015-11-22
|  |  | Coordinate with all retail stores owners/ managers the schedule for distribution of the stickers and other material. | Stores in the community | PC | 2015-10-25 | 2015-11-25 | 2015-10-23 | 2015-11-22
Printing the material | To have all the materials ready for the implementation of the strategy in the stores. | Hispanic parents and adult in general | Print the material in English and Spanish | Graphic design office | PC | 2015-10-27 | 2015-11-08 | 2015-10-23 | 2015-11-30
Recruiting volunteers/ CPAW members | To have enough volunteers and staff to complete the strategy | Volunteers | Having a meeting with the youth volunteers and CPAW members to explain to them the strategy and confirm their participation. | Dalton | PC | 2015-11-03 | 2015-11-20 | 2015-11-19 | 2015-11-19
Training volunteers | To explain to them the process of the implementation | Volunteers | Having a meeting with volunteers and explaining to them step by step how to conduct the strategy. | Dalton | PC | 2015-11-13 | 2015-11-23 | 2015-11-19 | 2015-11-19
Conduct the first phase of the strategy | Distribuite 1,000 stickers in 10 retail stores. | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | PC | 2015-12-01 | 2015-12-30 | 2015-12-09 | 2015-12-09
|  |  | 2. Prepare an appreciation certificate for the stores that will participate in the strategy. | Dalton | PC | 2015-12-01 | 2015-12-30 | 2015-12-09 | 2016-01-07
|  |  | 3. Contacting volunteers to confirm dates of the implementation | Dalton | PC | 2015-11-30 | 2015-12-04 | 2015-12-07 | 2015-12-07
|  |  | 4. Distribuite the stickers and posters in the two communities. Present the certificate to the store owners/managers. | Dalton | PC, CPAW | 2015-12-05 | 2016-01-30 | 2015-12-09 | 2015-12-09
Conduct the second phase of the strategy | Distribuite 1000 stickers in 10 retail stores | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Dalton | PC. CPAW | 2016-03-16 | 2016-04-10 | 2016-02-20 | 2016-03-31
|  |  | 2. Contacting volunteers to confirm dates of the implementation | Dalton | PC | 2016-03-30 | 2016-04-03 | 2016-03-31 | 2016-04-19
|  |  | 3. Distribute the stickers and posters. | Stores in the community | PC, CPAW | 2016-04-06 | 2016-04-30 | 2016-02-20 | 2016-04-19
Conduct the third phase of the strategy | Distribuite 1,000 stickers in 10 retail stores. | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | PC | 2016-06-01 | 2016-06-12 | 2016-06-16 | 2016-06-16
|  |  | 2. Prepare an appreciation certificate for the stores that will participate in the strategy. | Dalton | PC | 2016-06-15 | 2016-06-26 | 2016-06-18 | 2016-06-18
|  |  | 3. Contacting volunteers to confirm dates of the implementation | Dalton | PC, CPAW | 2016-07-01 | 2016-07-31
|  |  | 4. Distribuite the stickers and posters. | Dalton | PC, CPAW | 2016-07-01 | 2016-07-31
Publish a newspaper article with the results of the strategy | Inform the community the results of the implementation and give a public appreciation to the retail stores that support the strategy. | Hispanic parents and adult in general | 1. Prepare an article with pictures of the implementation of the strategy and names of retail stores. Publish sticker shock article with pictures in newspaper. | Dalton | PC | 2016-07-20 | 2016-07-22
|  |  | 2. Publish the article in one newspaper. | Newspaper | PC | 2016-08-03 | 2016-08-07
Evaluation | Evaluate the results of the strategy and the feedback from the store owners/managers | Store owners/managers | 1. Distribute and collect the Merchant Evaluation form to the store owners/managers. | Dalton | PC | 2016-07-27 | 2016-08-01
|  |  | 2. Revise the feedback. | Dalton | PC | 2016-08-03 | 2016-08-07
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY15-16 Milestones at-a glance
Project Activities (Milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Planning and Recruitment of children and get parents' consent for Cycle 1 | bar: Oct
Evaluation Pre Surveys Cycle 1 | [12 empty] | PYPM | bar: Oct to Nov
Continue collecting surveys | [12 empty] | Sticker Shock | bar: Oct
Re-evaluate the strategy | [12 empty] | BTW | bar: Oct
Contact retail stores managers/owners that participated in 2013-2014 strategy. | bar: Oct
Coordinate with all retail stores owners/ managers about implementation | bar: Oct
Printing the material | bar: Oct to Nov
Recruiting and training volunteers/ CPAW members | bar: Nov
Implement PYPM sessions to parents & youth Cycle 1 | bar: Nov to Dec
Evaluation Pre and Post Surveys Cycle 1 | bar: Nov to Dec
Conduct the first phase of the strategy | bar: Dec to Jan
Parent workshop Cycle 1 | bar: Dec
Planning and Recruitment for Cycle 2 | bar: Jan to Feb
Plan marketing campaign | bar: Jan to Feb
Discuss with CPAW members places of exposure | bar: Jan to Feb
Review the list of marketing materials and keeping track | bar: Jan to Feb
Implement strategy | bar: Feb
Purchase marketing material with the BTW logo | bar: Feb
Planning and Recruit children and get parents' consent Cycle 2 | bar: Jan to Feb
Distribute marketing material according to plan | bar: Mar to Sep
Conduct the second phase of the strategy | bar: Mar to Apr
Evaluation Pre Surveys Cycle 2 | bar: Feb to Apr
Implement PYPM sessions to parents & youth Cycle 2 | bar: Feb to Apr
Parent workshop Cycle 2 | bar: Apr
Conduct the third phase of the strategy | bar: Jun
Evaluation Pre and Post Surveys Cycle 2 | bar: Jun
Evaluation | bar: Sep
Publish a newspaper article | bar: Jul
Identify areas where the logo has been exposed in order to conduct intercept surveys. | bar: Jul
Conduct intercept surveys | bar: Aug
Distribute/collect the Merchant Evaluation and Revise Feedback | bar: Aug
Analyze intercept surveys and make adjustments to the marketing campaign | bar: Sep
Note on A1: T A: Enter the Milestone Activities chronlogically. Color-code the timeline by assigning a color for each strategy. Include a the side for readers to comprehend at a glance. Refer to Column A from each Strategy DAP. For each activity in this column, Providers are to fill in the cell where they anticipate the activity starting through its anticipated end date. Since the chart is set up according to months and not weeks, filling in one cell suggests that the activity will be complete within that month.

## Modified EXAMPLE DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Run 1st of 4 PSAs in newspaper by January 2014 | Spread the word about the dangers of underage drinking. | Parent | 1. Draft a 'catchy' announcement |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-14 | 2013-12-01 | 2013-12-20 | Activity started after the PC and CPAW attended a social marketing training offered at the local university on 11/23/13.Despite the delay, we implemented the activity as planned.
|  |  | 2. Identify 10 parents to participate in 2 focus groups to elicit input on PSA |  | Lisa Smith and John Williams - Partners | 2013-11-20 | 2013-11-30 | 2013-12-15 | 2013-12-30
|  |  | 3. Contract with newspaper outlets to run first PSA |  | Anita Conley | 2013-12-01 | 2013-12-10 | 2013-12-01 | 2013-12-07
Host 1st of 4 Lunch & Learn programs by March 2014 | To raise awareness about underage drinking and social host liability among community stakeholders. | Stakeholders | 1. Put together a powerpoint that explains the purposed of SPF, the implications of youth possession in the community, and the need for community involvement. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-07 | 2013-11-01 | 2013-11-07
|  |  | 2. Identify a donor and/or inkind support to provide the food for the L & L. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 3. Secure a venue in collaboration with a community partner to host the L & L in a location convenient to stakeholders. |  | Anita Conley - Administrative Asst. | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 4. Host first L & L |  | Kimberly Jones - Project Coordinator | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01
Poll community to gather data concerning communities view of underage drinking/social hosting | Gather data to determine the communities responsiveness to a social host ordinance | Parents of youth 9 to 20 and community members | Develop 4 to 5 questions concering underage drinking and social hosting to gather data | Provider Office | Evaluator | 2014-03-01 | 2014-04-30 | 2014-03-10 | 2014-04-15 | Our projected dates were delayed to include student involvment and input throughout this activity. We started after spring break and continued after the students returned to campus.
|  | Law Enforcement, Workgroup and community members | Attend community events and visit various community locations where polls can be distributed and collected | [Local Community] | CPAW Workgroup, Kimberly Jones - Project Coordinator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-15
|  | Law Enforcement, Workgroup and community members | Analyze poll data as received to determine communities receptiveness towards social host ordinance | Provider Office | Evaluator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-30
Present report of community poll to City Council during 2014 calendar year | To educate and inform the City Council about the community's views about social host ordinance. | City Council | Contact the appropriate office to get on the 2014 4th quarter City Council calendar. | [Local Community] | Kimberly Jones - Project Coordinator | 2014-08-01 | 2014-09-30 | 2014-09-20 | 2014-12-22 | We were advised by the CPAW to wait until the data was compiled and report drafted before pursuing a date. Unfortunately, due to the political climate in our community, 1) Social Host Liability is not a priority at this time; 2) we were informed that the 2015 City Council calendar has already been set as well.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY14-15 DAP for PYPM
Approved Strategy Name: |  | PROTECTING YOU / PROTECTING ME
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Planning and Recruitment for Cycle 1 | Coordinate details for the program | 4th and 5th graders | 1. Meet with America Gruner to review our experience to do our planning for next PYPM sessions. Review evaluators recommendations and findings from previous PYPM to take into consideration. Coordinate details like time and dates. | CLILA | Belen Reyes and America Gruner | 2014-09-01 | 2014-09-01 | 2014-10-01 | 2014-10-21
|  |  | 2. Make a list of supplies and materials needed and purchase them | CLILA | Belen Reyes and America Gruner | 2014-09-01 | 2014-09-05 | 2014-10-21 | 2014-10-21
|  |  | 3. Plan recruitment for Cycle 1 | Dalton | PC, CPAW members | 2014-09-05 | 2014-09-10 | 2014-10-12 | 2014-10-21
|  |  | 4. Recruit children and get parents' consent | Dalton | PC, America Gruner | 2014-09-16 | 2014-10-01 | 2014-09-20 | 2014-10-21
Conduct PYPM sessions to parents & youth | Implement PYPM sessions | Students of 4th and 5th grade and their parents. | 1. Deliver PYPM Cycle 1 | CLILA | PC, America Gruner, 2 assistants, child care person | 2015-10-03 | 2014-12-10 | 2014-11-15 | 2014-12-06 | Our last session will be on December 06/2014
Coordinate and facilitate parents workshop for Cycle 1 | Parent workshop | Parents of students who participated on PYPM | 2. Get all the materials and presentation ready for the parent workshop and coordinate and facilitate parent workshop after Cycle 1. | CLILA | PC | 2014-12-10 | 2014-12-10 | 2014-12-20 | 2014-12-20
Planning and Recruitment for Cycle 2 | Coordinate details for the program | 4th and 5th graders | 1. Meet with America Gruner to review our experience to do our planning for next PYPM sessions. Review evaluators recommendations and findings from previous PYPM to take into consideration. Coordinate details like time and dates. | CLILA | Belen Reyes and America Gruner | 2014-12-15 | 2014-12-19 | 2014-12-20 | 2014-12-20
|  |  | 2. Make a list of supplies and materials needed and purchase them | CLILA | Belen Reyes and America Gruner | 2014-12-15 | 2014-12-15 | 2015-01-16 | 2015-01-16
|  |  | 3. Plan recruitment for Cycle 2 | Dalton | PC, CPAW members | 2015-02-02 | 2015-02-13 | 2015-01-16 | 2015-01-16
|  |  | 4. Recruit children and get parents' consent | Dalton | PC, America Gruner | 2015-02-09 | 2015-03-01 | 2015-02-03 | 2015-05-23 | May 1st, during the CLILA's anniversary, the last attempt of recruitment will take place.
Conduct PYPM sessions to parents & youth | Implement PYPM sessions | Students of 4th and 5th grade and their parents. | 1. Deliver PYPM Cycle 2 | CLILA | PC, America Gruner, 2 assistants, child care person | 2015-05-01 | 2015-06-11 | 2015-05-23 | 2015-05-23
Coordinate and facilitate parents workshop for Cycle 2 | Parent workshop | Parents of students who participated on PYPM | 2. Get all the materials and presentation ready for the parent workshop and coordinate and facilitate parent workshop after Cycle 2. | CLILA | PC | 2015-06-15 | 2015-06-25 | 2015-05-23 | 2015-05-23
Evaluation | Evaluate effectiveness | Students of 4th and 5th grade | 1. Administer pre-survey to the students at the beginning of PYPM on both cycles | Dalton | PC, facilitators | 10/1/2014, 05/01/2015 | 10/1/2014, 05/01/2015 | 2015-05-23 | 2015-05-23
|  |  | 2. Administer post-survey to the same students at the end of PYPM | Dalton | PC, facilitators | 11/11/2014, 6/12/2015 | 11/11/2014, 6/12/2015 | 2015-06-20 | 2015-06-20
|  |  | 3. Be in constant contact with local evaluator | Dalton | PC, APP Director | 2014-10-01 | 2015-09-30 | 2015-07-03 | 2015-07-13
|  |  | 4. Develop a report of the findings of all surveys submitted | Dalton | Eval Group | 2015-05-30 | 2015-06-30 | 2015-06-20 | 2015-07-23
|  |  | 5. Provide findings to the CPAW members and stakeholders | Dalton | PC | 2015-07-01 | 2015-07-30 | 2015-07-16 | 2015-08-20
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on C3: CETPA: Since we alreay confirmed places, we only need to follow one step
Note on C9: CETPA: Since we alreay confirmed places, we only need to follow one step

## FY14-15 DAP for BTW
Approved Strategy Name: |  | Be The Wall
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment
Continue collecting surveys | Identifying perceptions in the community about the consumption/provision of alcohol to minors | Latino parents & adults in assigned communities | 1. Continue with the survey collection | Dalton | PC, PC Assistant | 2014-08-01 | 2014-10-31 | 2014-08-15 | 2014-10-15
|  |  | 2. Evaluator develops survey results | Dalton | Evaluator | 2014-11-01 | 2014-11-30 | 2015-07-13 | 2015-08-24
|  |  | 3. Present results to stakeholders and CPAW | Dalton | PC | 2014-12-01 | 2014-12-15 | 2015-06-16 | 2015-06-18
Plan marketing campaign | Plan first phase | Latino parents & adults in Dalton | 1. Discuss with CPAW members places of exposure of the wall logo within our community | Dalton | PC, CPAW members | 2014-12-15 | 2015-01-31 | 2015-06-22 | 2015-06-22 | Feb 15- We will discuss this on our February CPAW meeting
|  |  | 2. Decide activities, time frames, and marketing outlets to reach target | Dalton | PC, CPAW members | 2015-01-31 | 2015-02-15 | 2015-02-03 | 2015-05-02 | March 2015 We are contemplating bombarding the community with Be The Wall materilas during the month of April. Feb 15- We are currently getting quotes from local newspapers, radio station and billboard companies to start working on where we are going to distribute the message.
|  |  | 3. Plan dates of exposure | Dalton | PC, CPAW members | 2015-01-31 | 2015-02-15 | 2015-02-03 | 2015-05-02 | March 2015 We are starting to bombard the community with Be The Wall during the month of April. Feb 15- We are getting feedback from members of our community and our CPAW to see how we can deliver the message and what will work good in our community
|  |  | 4. Review the list of marketing materials available and choose the material accordingly with the target population. | Dalton | PC | 2015-01-31 | 2015-02-15 | 2015-02-01 | 2015-03-05 | Feb 2015- We will be reviewing the list on our next CPAW meeting on March 5.
|  |  | 5. Keep track of the material distributed | Dalton | PC, PC Assistant | 2015-02-15 | Until the end of the first phase | 2015-05-01 | 2015-05-02
Implement strategy | Running the marketing campaign on a continous basis, including placing message and managing interaction with the community. | Hispanic parents and adults in Dalton | 1. Purchase marketing material with the BTW logo | Dalton | APP Staff, CPAW, Evaluator. | 2015-02-15 | 2015-02-27 | 2015-03-01 | 2015-03-01
|  |  | 2. Distribute marketing material according to plan | Places in Dalton chosen for exposure | PC, CPAW members, volunteers | 2015-03-01 | 2015-09-10 | 2015-04-28 | 2015-05-02 | March 2015- Materials will be distributed during April, as a way to reinforce Alcohol Awareness Month
Ongoing evaluation process | Prepare and conduct a follow up process with the community in order to evaluate the effectiveness of the campaign. | Hispanic parents and adults in Dalton | 1. Identify areas where the logo has been exposed in order to conduct intercept surveys. | Dalton | PC, Evaluation team | 2015-07-01 | 2015-07-15 | 2015-06-23 | 2015-07-17
|  |  | 2. Create a schedule to conduct intercept surveys | Places in Dalton chosen for exposure | PC, CPAW members | 2015-07-16 | 2015-07-30 | 2015-06-23 | 2015-07-22
|  |  | 3. Conduct intercept surveys | Places in Dalton chosen for exposure | PC, CPAW members, volunteers | 2015-08-15 | 2015-08-30 | 2015-07-17 | 2015-07-22
|  |  | 4. Analyze intercept surveys and make adjustments to the marketing campaign if necessary. | Evaluators office | Evaluator | 2015-09-01 | 2015-09-15 | 2015-07-24 | 2015-08-17
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.

## FY14-15 DAP for Sticker Shock
Approved Strategy Name: |  | Sticker Shock Campaign
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Re-evaluate the strategy | Revise the evaluation of 2013-2014 and re-evaluate if is necessary to do any change to the steps and/or the design. | Hispanic parents and adult in general | 1. Revise Merchant Evaluations for 2013-2014 strategy and analyze the possible changes that are necessary in order to have better results. | Dalton | APP Staff, CPAW | 2014-10-01 | 2014-10-10 | 2014-09-24 | 2014-10-21
|  |  | 2. Make any necessary changes acording to the feedback received (sticker shock stickers & posters; volunteers ID, door stickers) | Graphic design office | APP Staff, CPAW | 2014-10-01 | 2014-10-10 | 2014-09-24 | 2014-10-21
Printing the material | To have all the materials ready for the implementation of the strategy in the stores. | Hispanic parents and adult in general | 4. Print the material | Graphic design office | APP Staff | 2014-10-27 | 2014-11-08 | 2014-11-20 | 2015-01-20
Partnerships with retail stores | Owners of the retail establishments to agree on the distribution of the stickers and posters | Retail Stores Owners/managers | 1. Contact retail stores managers/owners that participated in 2013-2014 strategy. Invite them to support the strategy again. | Shopping centers and stores in each community | APP Staff, CPAW | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
|  |  | 2. If is necessary, contact new stores or stores that denied us in the past. | Shopping centers and stores in each community | APP Staff, CPAW | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
|  |  | 3. If is necessary prepare an invitation letter for new stores. | Dalton | APP Staff | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
|  |  | 4. Visiting the new retail stores to personally meet owners/managers and provide them the invitation. Explaining the goalof the campaign. | Stores in the community | APP Staff, CPAW | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
|  |  | 5. Contact and confirm with the new retail stores owners/managers the agreement to participate in the strategy. | Dalton | APP Staff | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
|  |  | 6. Coordinate with all retail stores owners/ managers the schedule for distribution of the stickers and other material. | Stores in the community | APP Staff | 2014-10-04 | 2014-10-22 | 2014-11-11 | 2014-11-15
Recruiting volunteers/ CPAW members | To have enough volunteers and staff to complete the strategy | Volunteers | Having a meeting with the volunteers and CPAW members to explaining to them the strategy and confirm their participation. | Dalton | APP Staff | 2014-11-03 | 2014-11-21 | 2014-11-18 | 2014-11-18
Training volunteers | To explain to them the process of the implementation | Volunteers | Having a meeting with volunteers and explaining to them step by step how to conduct the strategy. | Dalton | APP Staff | 2014-11-17 | 2014-11-28 | 2014-11-18 | 2014-11-18
Conduct the first phase of the strategy | Distribuite 1,000 stickers in 10 retail stores. | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | APP Staff | 2014-12-01 | 2014-12-30 | 2014-12-15 | 2014-12-15
|  |  | 2. Prepare an appreciation certificate for the stores that will participate in the strategy. | Dalton | APP Staff | 2014-12-01 | 2014-12-30 | 2015-12-20 | 2015-12-20
|  |  | 3. Contacting volunteers to confirm dates of the implementation | Dalton | APP Staff | 2014-12-01 | 2014-12-05 | 2015-12-20 | 2015-01-16
|  |  | 4. Distribuite the stickers and posters in the two communities. Present the certificate to the store owners/managers. | Dalton | APP Staff | 2014-12-01 | 2015-01-30 | Ongoing | Ongoing | Feb 2015- The SSC was at first reschedule from Jan 24 to Feb 24 due to conflicts with two of the retailers that had previously agreed to participate and now they are saying that they need permission from their corporate office and that is going to take 3 weeks, plus there was a delay with the delivery of the stickers .This activity was rescheduled from 02/24 to 03/09 due to inclement weather in the area. -
Conduct the second phase of the strategy | Distribuite 1000 stickers in 10 retail stores | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Dalton | APP Staff | 2015-03-16 | 2015-04-10 | 2015-05-18 | 2015-05-22 | April 2015- New PC started working with us as of April 28th, 2015, so will be working on this strategy during the month of May. March 2015-New stores are identified where to place new stickers for the second phase. The stores will be contacted during month of April, with the integration of New PC.
|  |  | 2. Contacting volunteers to confirm dates of the implementation | Dalton | APP Staff | 2015-03-30 | 2015-04-03 | 2015-05-15 | 2015-05-22 | April 2015- New PC has a group of youth from Dalton College that will be supporting her with the implementation. March 2015- As soon as new PC is on board; arranging schedule with volunteers will take place
|  |  | 3. Distribute the stickers and posters. | Stores in the community | APP Staff | 2015-04-06 | 2015-04-30 | 2015-05-22 | 2015-05-22 | April 2015- Will occur during May, after new PC meets with former PC to give her the stickers at the beginning of the month. We were behind becousre of the transfer from PC.
Conduct the third phase of the strategy | Distribuite 1,000 stickers in 10 retail stores. | Hispanic parents and adult in general | 1. Contacting owners or managers of each store to confirm dates of the implementation | Stores in the community | APP Staff | 2015-06-01 | 2015-06-12 | 2015-06-23 | 2015-09-02 | becouse we are justing finshing the second phase we got to wait a couple of weeks to start the third phase, APP for Cepta came and help with in my Region.
|  |  | 2. Prepare an appreciation certificate for the stores that will participate in the strategy. | Dalton | APP Staff | 2015-06-15 | 2015-06-26 | 2015-07-23 | 2015-09-04
|  |  | 3. Contacting volunteers to confirm dates of the implementation | Dalton | APP Staff | 2015-07-01 | 2015-07-31 | 2015-07-16 | 2015-09-04
|  |  | 4. Distribuite the stickers and posters. | Dalton | APP Staff | 2015-07-01 | 2015-07-31 | 2015-09-04 | 2015-09-04
Publish a newspaper article with the results of the strategy | Inform the community the results of the implementation and give a public appreciation to the retail stores that support the strategy. | Hispanic parents and adult in general | 1. Prepare an article with pictures of the implementation of the strategy and names of retail stores. Publish sticker shock article with pictures in newspaper. | Dalton | APP Staff | 2015-07-20 | 2015-07-22 | 2015-09-04 | 2015-09-16
|  |  | 2. Publish the article in one newspaper. | Newspaper | APP Staff | 2015-08-03 | 2015-08-07 | 2015-09-04 | 2015-09-16
Evaluation | Evaluate the results of the strategy and the feedback from the store owners/managers | Store owners/managers | 1. Distribute and collect the Merchant Evaluation form to the store owners/managers. | Dalton | APP Staff | 2015-07-27 | 2015-08-01 | 2015-09-04 | 2015-09-16
|  |  | 2. Revise the feedback and analyze the changes that will be necessary to implement in the future. | Dalton | APP Staff/CPAW | 2015-08-03 | 2015-08-07 | 2015-09-16 | 2015-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.