## Provider Info New
Provider Information
Provider Name | Coalition to Prevent the Misuse of Alcohol
Project Coordinator | Scott Sherwin
State Priority | Reduce Youth Access to Alcohol & Binge Drinking
Approved IV/CF | Lack of Parental Monitoring, Compliance with Minimum Drinking/Purchasing Age Laws & Regulations, Low Perceived Risk of Drinking, Provision to Minors; and Availability of Unsupervised Places to Drink / Perception of Risk, Retail Availability; and Social Availability
Assigned Communities & Community Readiness Score (CRS)
Cartersville/CRS | 3
Rockmart/CRS | 3
Memorandum of Agreement Information
Partner/Consultant Information | Role | Pending | Confirmed
CPAW - Bartow | Oversee |  | X
CPAW - Polk | Oversee |  | X
Woodland High School, Principal Dr. Melissa Williams | Partner | X
Rockmart Middle School | Partner | X
Law Enforcement - Chief of Campus Police, Dan Knowles | Partner | X
Bartow Collaborative, Family Connective; Exec Director Tina Grubbs | Partner | X
Political
Cartersville Mayor - Matt Santini
Bartow County Commissioner - Steve Taylor
Rockmart Police Chief - Keith Sorrells
Rockmart Judge Mark Murphy
Rockmart Assistant Supt - Greg Teems
Bartow Schools - Dir Secondary Curriculum - Jim Gottwald
Cartersville Police Chief - Tommy Culpepper

## PMP AlcoholEDU 2016
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | AlcoholEDU
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Perception of Risk / Perceived Harm of Drinking
Strategy Intent: | To increase alcohol-related knowledge, discourage acceptance of underage drinking, and prevent or decrease alcohol use and its related negative consequences.
Target Audience: | Polk - approximately 300 8th grade students at Rockmart Middle
IOM Category | Universal
Estimated Reach: | 300 students total
What is the dosage for this strategy? | 2 sessions each week - and a 30 day follow up.
How frequent will the strategy be implemented? | Each person will be exposed 3 x over the course of the strategy
Necessary Resources for Successful Implementation | Credit carryover from last year - no cost this year
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 3 |  | Mike Carpenter
Number of staff to be hired/contracted: 0 | NA | NA | NA | NA | NA
Staff/Consultant Recruitment Strategy | No additional staff is required; however, we will be working very closely with each school's administration with whom we have established working relationships with over the past two years. | NA | NA | na | NA
Staff/Consultant Training | AlcoholEDU training - as provided by the vendor. | Mike Carpentar | 2015-09-04 | MPR | NA
Staff Retention Strategy | Staff is committed to this effort | NA | NA | NA | NA
Additional Training | NA | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | It will take a well coordinated effort, with each school, to schedule the delivery of this curriculum. We have already had initial conversations with both Cartersville High and Rockmart High. | Mike Carpenter | 2015-11-15 | MPR | NA
Retention Strategies | NA
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Provide school staff information on the program | We will conduct informational webinars or other discussions on the details of the program | Mike Carpenter | 2015-06-30 | MPR | MDS
Provide parents information on the program | We will provide an explanatory letter home to each student participant | Mike Carpenter | 2015-11-15 | MPR | MDS
Deliver the AlcoholEDU program | The 3 science teacher(s) will provide the students with instructions on how to complete the program. We will provide ongoing training and monitoring through our rep with AlcoholEDU. | Mike Carpenter | 2015-11-15 | MPR | MDS
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | We are not planning to modify the current system/structure of this strategy. | NA | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Valerie Gilreath | 2016-06-01
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.(job description, MOU, etc)
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.How many people were hired, for example.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged. (appropriate incentives, be creative - small groups, etc. talk to RPS for ideas)
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on D28: Ongoing is acceptable
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark. (sign-n sheets, post-test, survey)
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on B36: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E36: T A: Discuss the mechanism that will be used to track each indicator.
Note on F36: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP Compliance 2016
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Promotion of Compliance Checks
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | IV: Retail Availability CF: Compliance with Minimum Age Drinking/Purchase Laws
Strategy Intent: | Gain support of public officials, and community so that will they can champion an increase of complaince checks at the rate of 2x/year for all retailers. 4-6x/year for "problem" retailers.
Target Audience: | Government (local) Officials and Law/Court Personnel (prosecutors, judges, administrative/zoning departments) Retailers/Restaurants (117 alcohol retailers within the Cartersville Community licensed). Law Enforcement Agencies. Media (newspaper, tv, etc). General Public
IOM Category | Universal
Estimated Reach: | Government (local) Officials and Law/Court Personnel (prosecutors, judges, administrative/zoning departments) Retailers/Restaurants (117 alcohol retailers within the Cartersville Community licensed). Law Enforcement Agencies. Media (newspaper, tv, etc). General Public
What is the dosage for this strategy? | Meetings as needed with public officials/key stakeholders,
How frequent will the strategy be implemented? | As needed from the stakeholder analysis tool
Necessary Resources for Successful Implementation | Posters, Focus Groups, Meeting Space
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 4 |  | Scott - Bartow; Mike - Polk
Number of staff to be hired/contracted: 0 | We have already contracted with an Evaluator. She will attend future trainings and CPAW meetings. | Scott - Bartow; Mike - Polk | Ongoing | Evaluation Measures | TBD at Eval. Training
Staff/Consultant Recruitment Strategy | Will address if necessary. At this time we do not anticipate the need for additional staff. | NA | NA | NA | NA
Staff/Consultant Training | We will partner with GASPS and other providers to identify training | Scott - Bartow; Mike - Polk | NA | NA | NA
Staff Retention Strategy | Frequent communications, staff development | Scott - Bartow | NA | Measure against our timeline | NA
Additional Training | TBD | Scott - Bartow | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | In both communities we have already begun engaging key leaders in order to gain their support before moving forward with our strategy. We have met with each city's Mayor and have received their support and willingness to assist us as we move forward. We are drafting letters, to be signed by each Mayor, that will be presented to local retailers, through the assistance of law enforcement, and will ask for voluntary participation. We will explain the importance of their compliance with our strategy. | Scott - Bartow; Mike - Polk | NA | NA | NA
Retention Strategies | To keep our communities involved, we will implement a "Youthful 21" approach to finding out whether local retailers are in compliance with the current laws surrounding the sale of alcohol to adults under 21 years of age. Once we have attained the data we need, we will share the results with key stakeholders. | Scott - Bartow; Mike - Polk | NA | NA | NA
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Presenting our findings to civic groups, school personnel, students and parents to support increase enforcement of alcohol related laws. | We will coordinate our activities through local government officials, law enforcement, and school administration with whom we have succesfully established relationships. Some of the officials are involved on our CPAW and others serve as advisors. We will schedule a variety of engagements throughout the year. | Scott - Bartow; Mike - Polk | Ongoing | MPR | Agenda and/or Sign-in Sheet
Partner with local business owners/retailers to create establishment 'best practices & policies' that in turn will decrease the chance that servers and sellers illegally sell alcohol to underage persons. | We have the support of local officials and will use their influence (letters, speaking) to increase awareness and show a unified effort. | Scott - Bartow; Mike - Polk | Ongoing | MPR | Submissions into MDS and/or MOUs
To raise awareness, we plan to partner with law enforcement to increase the number of compliance checks across each community. | We plan to ask local law enforcement to sign an MOU showing their support of our effort. | Scott - Bartow; Mike - Polk | Ongoing | MPR | MOUs
We will offer online server training to a selected group of licensees. | Once the target group has been identified (criteria= x number of violations within a given year) we will meet with the owner/operators to explain/offer the server training curriculum. The organization we chose to implement is Professional Server Certification Corporation (PSCC) which is a nationally recognized leader in the field. They offer state-of-the art training which may help our local businesses reduce their liability and/or fines in the event of a citation. | Scott - Bartow; Mike - Polk | 2016-07-31 | Online Certificates | Number of Completions per Establishment
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | Alcohol licensees are informed that compliance checks will be conducted at various times and penalties for non-compliance do apply. Our adaptation to the current process will include our staff providing the retailers with a folder of information along with posters which details the compliance statutes. | Scott - Bartow; Mike - Polk | Ongoing | MPR and/or MDS | Number of Folders provided to retail establishments
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Scott - Bartow; Mike - Polk | 2016-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on B16: bcnelson1: Fantastic!
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on E19: bcnelson1: How are you going to ensure what needs to get done does? At the appropriate time? Consistently? thanks
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on B24: bcnelson1: Recruitment is insufficient and a high risk for a successul implementation. Only voluntary so depends on mayor support + law enforcement. Depends on if you can get the mayor to write the letter and also how much influence will a mayor provide onto retailers? Look into insurance incentives w/ TIPPS.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A34: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A36: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A40: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP PSN HAINES 2016
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Positive Social Norms Approach: Haines Model
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Perception of Risk / Perceived Harm of Drinking
Strategy Intent: | Our intent is to discourage youth's current acceptance of underage drinking, and prevent or decrease alcohol use and its related negative consequences.
Target Audience: | Bartow: All students at Woodland High School and all students at Cartersville High School; Polk: All students at Rockmart High School.
IOM Category | Universal
Estimated Reach: | Woodland High School: 1600; Cartersville High School:1100; Rockmart High School:
What is the dosage for this strategy? | 3 schools-No control group due to the lack of a homogenous population between the schools.
How frequent will the strategy be implemented? | The messages will change up to every 6 weeks.
Necessary Resources for Successful Implementation | 5000
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 3 |  | Christa - Bartow; Mike - Polk
Number of staff to be hired/contracted: 0 | NA | NA | NA | NA | NA
Staff Retention Strategy | Staff is committed to this effort. | Christa - Bartow; Mike - Polk | Ongoing | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | It will take a well coordinated effort, with each school to schedule the pre-surveys to establish our baseline data. We have already established good relationships with Cartersville, Woodland, and Rockmart High administration. | Christa - Bartow; Mike - Polk | NA | MPR | Agendas and Rosters
Retention Strategies | Our staff is committed to this effort, and will be meeting with administration at each of the high schools to coordinate dates for conducting the pre-surveys to collect our baseline data. | Christa - Bartow; Mike - Polk | TBD | MPR | Agendas and Rosters
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Provide alcohol awareness messages. | Through an ongoing text back campaign. | Christa - Bartow; Mike - Polk | Ongoing | MPR | MDS
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | We do not plan to modify the plan. Meet as a group and develop a local implementation plan. | Christa- Bartow; Mike - Polk | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Valerie Gilreath, Evaluator | 2016-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on B3: bcnelson1: What model are you using? Also, I will be holding comments on Positive Social Norms until after the training in Macon next week & you've had a chance to edit as well.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A19: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A20: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B20: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E20: T A: Discuss the mechanism that will be used to track each indicator.
Note on F20: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A21: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A22: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A24: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A25: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B25: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E25: T A: Discuss the mechanism that will be used to track each indicator.
Note on F25: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A29: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A31: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A35: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## POLK Alcohol Edu DAP 2016
Approved Strategy Name: |  | Alcohol Edu (Polk ONLY)
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Deliver the AlcoholEDU program, Rockmart MS | Alcohol EDU administration | Rockmart Middle School Staff | Provide RMS staff information on the Alcohol EDU course and plans to implement the course during the 2015-16 school year. | Rockmart Middle School | Mike, RMS administration, Kelley McLendon | 2015-08-01 | 2015-08-31 | 2015-08-01 | 2015-08-31
Deliver the AlcoholEDU program, Rockmart MS | Alcohol EDU administration | Rockmart School Community | Conduct informational sessions and facilitate on-going discussions on the details of the Alcohol EDU course to the school community. | Rockmart Middle School | Mike, administration, Kelley McLendon | 2015-08-01 | 2015-12-31 | 2015-09-01 | 2015-09-30
Review logistics | Feedback | RMS parents and students | Provide 8th grade parents and students information on the Alcohol EDU course through social media, the RMS website, RethinktheDrink.org, etc. | Rockmart Middle School | Mike, administration, Kelley McLendon | 2015-10-01 | 2015-12-18 | 2015-10-01 | 2015-10-15
Determine viability of continuing Alcohol Edu | Alcohol EDU funding for 2015-16 | RMS 8th grade students | Schedule the AlcoholEDU course to be administered during first semester in 8th grade science classes with a planned effort to offer the Alcohol EDU course to all 225 8th graders on Ipads (if working properly) and/or desktop computers. | Rockmart Middle School | Mike, administration, Kelley McLendon, Everfi Staff | 2015-10-01 | 2015-11-20 | 2015-10-01 | 2015-10-20
Examine the Everfi contract for 2015-16 | Feedback | RMS 8th grade students | Offer the first session of Alcohol EDU to 8th graders during the month of October and follow-up one month later in November with the last session (before Thanksgiving break). | Rockmart Middle School | Mike, administration, Kelley McLendon, Laura Mayfield- Everfi | 2015-10-01 | 2015-11-20 | 2015-10-19 | 2015-11-10
| Feedback | RMS 8th grade students and staff | Offer ongoing technical assistance to staff and 8th grade students being administered the online Alcohol EDU course using Ipads and/or desktop computers. | Rockmart Middle School | Mike, Kelley McLendon, Laura Mayfield- Everfi | 2015-09-01 | 2015-11-20 | 2015-10-19 | 2015-11-10 | Ipads work in the Puffin browser more efficiently than Safari.
| Feedback | RMS 8th grade students and staff | Offer last session of alcohol EDU more than 30 days after initial lessons | Rockmart Middle School | Mike, administration, Kelley McLendon, Laura Mayfield- Everfi | 2015-12-01 | 2015-12-18 | 2015-12-15 | 2015-12-15
|  | RMS 8th grade students and staff | Compile a preliminary completion report to address the glows and grows that were mentioned during the course offering in addition to feedback from the science staff. The completion goal is a have a minimum of 80% of 8th graders to finish the course. | Rockmart Middle School | Mike, Kelley McLendon, Laura Mayfield- Everfi | 2016-12-01 | 2016-02-01 | 2016-01-01 | 2016-03-16
|  | RHS 8th grade students | Compile a final completion report comprising the number of students completing the course. Share information from Everfi and RHS about completion numbers including glows and grows in administering the Alcohol EDU course to 8th graders at RMS. | Rockmart Middle School | Mike, Valeri | 2016-06-01 | 2016-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## BARTOW Compliance DAP 2016
Approved Strategy Name: |  | Compliance Checks
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Develop a "Youthful 21" Campaign as a Compliance Check | Create a plan to re-visit retailers | Target Group of 13 Retail Locations surveyed in Round 1
|  |  | Coordinate a calendar/schedule to visit | Community | Scott | 2015-10-01 | 2015-10-14 | 2015-10-10 | 2015-10-10
Create our Reward & Reminder Cards
|  |  | Get approval from DBHDD | DBHDD | Scott/Brian Le | 2015-10-01 | 2015-10-01 | 2015-09-01 | 2015-09-16
|  |  | Have printed | Community | Scott | 2015-10-05 | 2015-10-10 | 2015-10-05 | 2015-10-11
| Recruit Volunteers | Young Adults
|  |  | Identify and Train two "youthful" appearing adult (21 years or older) willing to participate. One male & one female. | CPMA | Team | 2015-11-01 | 2015-11-14 | 2015-11-01 | 2015-11-11
|  |  | Ask volunteers to assist us with strategy | CPMA | Scott | 2015-11-14 | 2015-11-25 | 2015-11-01 | 2015-11-11
|  |  | Review responsibilities and discuss availability and timelines for both communities. | CPMA | Scott | 2015-11-14 | 2015-11-25 | 2015-11-01 | 2015-11-11
| Meet with Police Chief | Chief Culpepper & Asst Chief McCann
|  |  | Hold a meeting with the Chief and his assistant to explain Round 2 | Police Station | Scott & Christa | 2015-11-23 | 2015-11-23 | 2015-11-23 | 2015-11-23
|  |  | Ask for a new letter of endorsement |  |  | 2015-11-23 | 2015-11-23 | 2015-11-23 | 2015-11-23
| Create a Plan of Action | Team
|  |  | Develop an action plan/calendar to visit retailers. | Community | Scott | 2015-11-14 | 2015-11-30 | 2015-11-01 | 2015-11-01 | Visited alcohol retailers one week and then the following week
|  |  | Selected Adult will visit retailers to purchase alcohol; and, a) If the Adult is asked for an ID - they should state they "left it at home" and see if the sale is allowed to move forward; or b) if the Adult is NOT asked for an ID, they are to purchase the alcohol and leave. | Community | Scott, Recruits | 2015-11-14 | 2015-12-01 | 2015-11-23 | 2015-12-30 | Cartersville City Police Chief asked that we delay our Compliance Check until later in December or beginning of January, due to a recent sting operation that occurred from the state last week.
| Visit Retailers | City Retailers
|  |  | Attempt to purchase alcohol, Round 2 - male | Community | Scott, Recruits | 2015-11-23 | 2015-12-01 | 2015-11-23 | 2015-12-14 | Round 1 of Phase 2
|  |  | If clerk is willing to sell without ID, our volunteer will leave them a "Reminder" Card as to the law. If the clerk refuses to sell without first seeing an ID, our volunteer will leave them a "Reward" Card congratulating them on their efforts. | Stores | Scott, Recruits | 2015-11-23 | 2015-12-01 | 2015-11-23 | 2015-12-14 | We handed out 10 Reward Cards on 12/14 and 3 Reminder Cards.
|  |  | Attempt to purchase alcohol, Round 2 - female | Community | Scott, Recruits | 2015-11-23 | 2015-12-01 | 2015-11-23 | 2015-12-30 | Round 1 of Phase 2
|  |  | If clerk is willing to sell without ID, our volunteer will leave them a "Reminder" Card as to the law. If the clerk refuses to sell without first seeing an ID, our volunteer will leave them a "Reward" Card congratulating them on their efforts. | Stores | Scott, Recruits | 2015-11-23 | 2015-12-01 | 2015-11-23 | 2015-12-30 | We handed out 12 Reward Cards and 1 Reminder Card
|  |  | Report Results to new Police Chief | CPMA | CPMA | 2015-01-02 | 2016-01-30 | 2016-01-08 | 2016-01-08 | Meeting with Police Chief
|  |  | Gather and update media contact lists | Community | Scott | 2016-01-05 | 2016-01-11
|  |  | Coordinate promotional effort with law enforcement agencies in the arena of compliance checks | Community | Scott | 2015-11-23 | 2015-11-23 | 2016-01-08 | 2016-01-08 | Plan to meet with Asst Chief McCann in the near future to get him up to speed on this initiative
|  |  | Write a media advisory and news release about compliance checks | Community | Scott | 2016-01-20 | 2016-01-28
|  |  | Encourage the local paper to run an article about the effect of illegal purchase of alcohol in Cartersville | Community | Scott | 2016-01-20 | 2016-01-28
|  |  | Mail a media advisory to key media contacts | Community | Scott | 2016-01-20 | 2016-01-28
|  |  | Propose / present your best practices to town/council meetings and use data to help drive the promotional effort of compliance checks. Present best practies to leadership at agencies that are conducting compliance checks. Attempt to get agencies to adopt best practies. Helping to institionalize the proposed changes can be a good way to help them become sustained. Helping agencies that are tasked with this conducting compliance checks by provinding them with usful information, models and public support. | Community | Scott | 2016-02-01 | 2016-02-28
| Educate Retailers | Round 1 Locations
|  |  | Provide a letter to the Store Owner/Operator letting them know about this initiative and the results of our visit to their location. | Community | Scott | 2016-02-01 | 2016-02-28 | 2016-02-28 | 2016-03-03 | Provide the specifics of our visit and the details of their clerks actions.
| Create a Plan for Rounds 3 & 4 |  | Choose random retail winner from those who passed all four compliance checks. Visit store with office for media picture. |  |  | 2016-03-01 | 2016-03-20 | 2016-03-03
|  |  | Plan for the following quarter | Office | Scott | 2016-03-01 | 2016-03-15
|  |  | Draft a realistic plan to maintain visibility within our community and to ensure the viability of ongoing compliance checks. | Office | Scott | 2016-04-01 | Ongoing |  |  | We will mirror this plan for subsequent quarters in 2016 in order to have solid data as to which retailers either improve and/or fail in their attempt to check ID of those potentially underage buyers.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## POLK Compliance DAP 2016
Approved Strategy Name: |  | Compliance Checks
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Develop a "Youthful 21" Campaign as a Compliance Check | Create a plan to re-visit retailers | Target Group of 11 Retail Locations surveyed in Round 1
|  |  | Coordinate a calendar/schedule to visit | Community | Mike | 2015-10-01 | 2015-10-14 | 2015-10-15 | 2015-10-15
| Recruit Volunteers | Young Adults
|  |  | Identify and Train two "youthful" appearing adult (21 years or older) willing to participate. One male & one female. | CPMA | Team | 2015-10-01 | 2015-11-14 | 2015-10-15 | 2015-10-15
|  |  | Ask volunteers to assist us with strategy | CPMA | Mike | 2015-10-14 | 2015-11-25 | 2015-10-15 | 2015-10-15
|  |  | Review responsibilities and discuss availability and timelines for both communities. | CPMA | Mike | 2015-11-14 | 2015-11-25 | 2015-10-15 | 2015-10-15
| Meet with Polk Co Sheriffs Dept | Jonathan Blackmon
|  |  | Hold a meeting with law enforcement to explain Round 2 | Polk County Sheriff's Dept | Mike | 2015-11-26 | 2015-11-30 | 2015-10-15 | 2015-10-15
|  |  | Ask for a letter of endorsement |  |  | 2015-11-26 | 2015-11-30 | 2015-11-10 | 2015-11-10
| Create a Plan of Action | Team
|  |  | Develop an action plan/calendar to visit retailers. | Community | Mike | 2015-10-01 | 2015-10-30 | 2015-11-06 | 2015-11-11 | Visited alcohol retailers one week and then the following week
|  |  | Selected Adult will visit retailers to purchase alcohol; and, (a) If the Adult is asked for an ID - they should state they "left it at home" and see if the sale is allowed to move forward; or (b) if the Adult is NOT asked for an ID, they are to notify the merchant of the State Law regarding ID-ing. | Community | Mike, Recruits | 2015-11-14 | 2015-11-30 | 2015-11-06 | 2015-11-11 | In Rockmart the two youthful 21 individuals visited the retailers in the afternoon on FRI Nov 6 and WED Nov 11
| Visit Retailers | City Retailers
|  |  | Attempt to purchase alcohol | Community | Mike, Recruits | 2015-11-01 | 2015-11-15 | 2015-11-06 | 2015-11-11 | Rockmart
|  |  | If clerk is willing to sell without ID, our volunteer will leave them a "Reminder" Card as to the law. If the clerk refuses to sell without first seeing an ID, our volunteer will leave them a "Reward" Card congratulating them on their efforts. | Stores that sell alcohol | Mike, Recruits | 2015-12-01 | 2015-12-14 | 2015-11-06 | 2015-11-11 | Each volunteer visiting businesses found only one store that agreed to sell alcohol to them without having an ID. This business, Raceway, was given a reminder card.
|  |  | Report Results | CPMA | CPMA | 2015-12-15 | 2015-12-20 | 2015-11-06 | 2015-11-11 | Meeting with Law Enforcement
|  |  | Gather and update media contact lists | Community | Mike | 2016-01-05 | 2016-01-11 | 2016-01-20 | 2016-01-25
|  |  | Coordinate promotional effort with law enforcement agencies in the arena of compliance checks | Community | Mike | 2016-01-05 | 2016-01-11 | 2016-01-10 | 2016-01-22 | Plan to meet with law enforcement in the near future to get him up to speed on this initiative
|  |  | Write a media advisory and news release about compliance checks | Community | Mike | 2016-01-20 | 2016-01-28 | 2016-01-05 | 2016-01-22
|  |  | Encourage the local paper to run an article about the effect of illegal purchase of alcohol in Rockmart | Community | Mike | 2016-01-20 | 2016-01-28 | 2016-01-22 | 2016-01-29 | Sent to online (Facebook, etc.) newspaper Jan 21. Projected to be online before end of Jan.
|  |  | Share media advisory to key media contacts | Community | Mike | 2016-01-20 | 2016-01-28 | 2016-01-22 | 2016-01-29 | Limited in small community
|  |  | Propose / present your best practices to town/council meetings and use data to help drive the promotional effort of compliance checks. Present best practies to leadership at agencies that are conducting compliance checks. Attempt to get agencies to adopt best practies. Helping to institionalize the proposed changes can be a good way to help them become sustained. Helping agencies that are tasked with this conducting compliance checks by provinding them with useful information, models and public support. | Community | Mike | 2016-02-01 | 2016-02-28 | 2016-01-22 | 2016-03-01 | Shared results in the local online newspaper i(Rockmart Fish Wrap) n addition in a letter shared with each business.
| Educate Retailers | Round 1 Locations
|  |  | Provide a letter to the Store Owner/Operator letting them know about this initiative and the results of our visit to their location. | Community | Mike | 2016-02-01 | 2016-02-28 | 2016-01-20 | 2016-03-01 | Provide the specifics of our visit and the details of their clerks actions.
Create a Plan for Rounds 3 & 4
|  |  | Plan for the following quarter | Office | Mike | 2016-03-01 | 2016-04-01 | 2016-04-01 |  | Planning compliance checks dates andsSelecting youthful looking checkers
|  |  | Draft a realistic plan to maintain visibility within our community and to ensure the viability of ongoing compliance checks. | Office | Mike | 2016-04-01 | Ongoing |  |  | We will mirror this plan for subsequent quarters in 2016 in order to have solid data as to which retailers either improve and/or fail in their attempt to check ID of those potentially underage buyers.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## BARTOW PSN DAP 2016
Approved Strategy Name: |  | Positive Social Norms Approach: Michael Haines Model
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Target audience for messaging | Identify schools who will participate | High Schools | Contact last year's participating schools (Woodland HS, Cartersville HS) | schools/email | STAFF | 2015-07-27 | 2015-08-04 | 2015-07-29 | 2015-08-05
|  |  | Contact Control Group from last year (Adairsville HS), add into the group receiving messaging | schools/email | STAFF | 2015-07-27 | 2015-08-04 | 2015-07-29 | 2015-08-05
|  |  | Contact Cass HS about being this year's Control Group | schools | STAFF | 2015-07-27 | 2015-08-04 | 2015-07-29 | 2015-10-15
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Develop Pre-Survey utilizing Survey Monkey | tbd | STAFF | 2015-07-01 | 2015-07-26 | 2015-07-01 | 2015-07-31
|  |  | Analyze data from schools (Woodland HS, Cartersville HS, Adairsville HS) | tbd | Survey Monkey, STAFF & Evaluator | 2015-09-01 | 2015-09-18 | 2015-09-07 | 2015-09-14
|  |  | Report on results to CPAW & RPS | tbd | STAFF & Evaluator | 2015-09-21 | 2015-09-25 | 2015-09-22 | 2015-09-22
|  |  | Present findings to school administration (WHS, CHS, AHS, Cass HS) and school teachers. Make sure everyone is on board and understanding the data and purpose of the PSN campaign to avoid lack of support from school employees. | Via email, presentations at schools, data packets | STAFF | 2015-09-21 | 9/2152015 | 2015-10-26 | 2015-11-02
|  |  | Create parent newsletter to go home, to further create support for campaign | schools | STAFF & School staff | 2015-09-21 | 2015-09-25 | 2015-11-02 | 2015-11-06
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade students(Cartersville, Woodland, Adairsville) | Create messages based upon baseline data collected (Fall Pre-Survey 2015) | tbd | STAFF & Evaluator | 2015-09-18 | 2015-09-25 | 2015-09-16 | 2015-09-30
Test messages and media | Determine relevance of messages designed to target population. | 9th-12th grade students at Cartersville HS, WHS, AHS, Cass HS | Identify focus group participants | schools | STAFF & Bartow Youth Action Team | 2015-08-04 | 2015-09-18 | 2015-08-04 | 2015-09-14 | Using Bartow Youth Action Team Students, so the focus groups are happening during their regularly scheduled monthly meetings.
|  |  | Focus group 1: Test sample PSN messages | Teen Center | STAFF & Bartow Youth Action Team | 2015-09-21 | 2015-09-25 | 2015-09-15 | 2015-09-15
|  |  | Focus group 2: Test draft of PSN msgs based on our data | Teen Center | STAFF & Bartow Youth Action Team | 2015-09-28 | 2015-10-02 | 2015-10-06 | 2015-10-06
|  |  | Focus group 3: Present edited PSN mgs based on our data | Teen Center | STAFF & Bartow Youth Action Team | 2015-10-05 | 2015-10-09 | 2016-01-26 | 2016-01-26
Create final media | Create messages that reflectstudent's positive attitudes toward prevention of underage drinking | 9th-12th grade students (Cartersville, Woodland, & Adairsville HS) | Incorporate edits based upon feedback from all 3 focus groups | tbd | STAFF & Evaluator | 2015-10-12 | 2015-10-16 | 2015-10-06 | 2015-10-12
|  |  | Determine effective media channels. | tbd | STAFF | 2015-10-12 | 2015-10-16 | 2015-10-06 | 2015-10-12
|  |  | Create media-specific messages according to media format | tbd | STAFF | 2015-10-12 | 2015-10-16 | 2015-10-06 | 2015-10-12
|  |  | Present final messages to School Administrators | Via email | STAFF | 2015-10-19 | 2015-10-23 | 2015-10-26 | 2015-10-30
|  |  | Order posters for campaigns | tbd | STAFF | 2015-10-23 | 2015-10-30 | 2015-10-16 | 2015-10-23
Dissimenation of media | Deliver consistent alcohol prevention messages through proper channels | 9th-11th grade students(Cartersville, Woodland, Adairsville) | Dissimenate first messaging campaign (1 of 3, TBD) | tbd | STAFF & Bartow Youth Action Team | 2015-11-02 | 2015-12-04 | 2015-11-02 | 2015-12-09
|  |  | Dissimentate second messaging campaign (2 of 3)-TBD, based on data | tbd | STAFF & Bartow Youth Action Team | 2016-01-05 | 2016-01-29 | 2015-01-05 | 2016-01-29
|  |  | Dissemenate third messaging campaign (3 of 3)-TBD, based on data | tbd | STAFF & Bartow Youth Action Team | 2016-02-08 | 2016-03-04 | 2016-02-22 | 2016-03-18
Evaluation of messaging | Determine effectiveness of messaging | 9th-12th grade students (Cartersville, Woodland, & Adairsville HS) | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. First intercept survey (1 of 3). | schools | STAFF & Bartow Youth Action Team | 2015-12-07 | 2015-12-18 | 2015-12-14 | 2015-12-18
|  |  | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (2 of 3). | schools | STAFF & Bartow Youth Action Team | 2016-02-01 | 2016-02-05 | 2016-02-01 | 2016-02-05
|  |  | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (3 of 3). | schools | STAFF & Bartow Youth Action Team | 2016-03-07 | 2016-03-11 | 2016-03-23 | 2016-03-25
Control Group (Cass High) | Determine the effectiveness of the campaign versus without the PSN campaign | 9th-12th grade students (Cass High) | Conduct Pre survey | school via survey monkey | STAFF | 2015-08-20 | 2015-08-31 |  |  | The Principal did not feel comfortable participating this school year due to scheduling conflicts. We will hold mtg with him in the Spring to discuss how to incorporate them into the strategy next school year.
Evaluation of Campaign | Determine effectiveness of the campaign | 9th-12 grade students (Adairsville, Cartersville, and Woodland High | Conduct Post survey | school via survey monkey | STAFF | 2016-03-14 | 2016-04-01 | 2016-03-28
|  |  | Analyze data from schools | online | STAFF & Evaluator | 2016-04-04 | 2016-04-29
|  |  | Report on results to CPAW & RPS | TBD | Staff | 2016-05-02 | 2016-05-20
|  |  | Present findings to school administration and school teachers. | via email | Staff | 2016-05-02 | 2016-05-20
|  |  | Create parent newsletter to go home, to further create support for campaign | Via flier sent home through schools; school website; Parent Portal | STAFF & School staff | 2016-05-02 | 2016-05-20
Text Back Campaign-"Rethink the Drink" | Deliver consistent alcohol prevention messages to our targeted population. | 9-12th grade students at Cartersville HS, Woodland HS, Adairsville HS, & Cass HS | Create Campaign to reach students at Woodland, Cartersville, Adairsville, and Cass HS | NA | STAFF | Ongoing | Ongoing
|  |  | Develop varying messages-Ideas at rethinkthedrink.org | Na | STAFF | Ongoing | Ongoing
|  |  | Increase capacity by presenting text back campaign at school assemblies (text to pledge to" remain alcohol free until 21 and to not get into a car where the driver has been drinking") | High schools | STAFF | 2015-08-04 | 2016-05-20
|  |  | Text prevention messages 2x per month to participants. | NA | STAFF | ongoing | Ongoing
Target audience for messaging | Identify schools who will participate | High Schools | Contact last year's participating schools (Woodland HS, Cartersville HS, Adairsville HS, Cass HS) | schools/email | STAFF | 2016-07-27 | 2016-08-04
|  |  | Contact Control Group from last year (Cass HS), add into the group receiving messaging | schools/email | STAFF | 2016-07-25 | 8/12016
|  |  | NO CONTROL GROUP | na | na | na | na
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Develop Pre-Survey utilizing Survey Monkey | tbd | STAFF | 2016-07-01 | 2016-07-29
|  |  | Collect Pre-Survey Baseline Data from Schools (Woodland HS, Cartersville HS, Adairsville HS, Cass HS) | schools | STAFF, school staff | 2016-08-01 | 2016-08-31
|  |  | Analyze data from schools (Woodland HS, Cartersville HS, Adairsville HS, Cass HS) | tbd | Survey Monkey, STAFF & Evaluator | 2016-09-01 | 2016-09-16
|  |  | Report on results to CPAW & RPS | tbd | STAFF & Evaluator | 2016-09-19 | 2016-09-23
|  |  | Present findings to school administration (WHS, CHS, AHS, Cass HS) and school teachers. Make sure everyone is on board and understanding the data and purpose of the PSN campaign to avoid lack of support from school employees. | Via email, presentations at schools, data packets | STAFF | 2016-09-19 | 2016-09-23
|  |  | Create parent newsletter to go home, to further create support for campaign | schools | STAFF & School staff | 2016-09-26 | 2016-09-30
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade students(Cartersville, Woodland, Adairsville, Cass HS) | Create messages based upon baseline data collected (Fall Pre-Survey 2016) | tbd | STAFF & Evaluator | 2016-09-19 | 2016-09-23
Test messages and media | Determine relevance of messages designed to target population. | 9th-12th grade students at Cartersville HS, WHS, AHS, Cass HS | Identify focus group participants | schools | STAFF & Bartow Youth Action Team | 2016-08-01 | 2016-09-19
|  |  | Focus group 1: Test sample PSN messages | Teen Center | STAFF & Bartow Youth Action Team | 2016-09-26 | 2016-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on A7: bcnelson1: Too big of a gap between activities? Since you have already been trained by Haines, they can collect baseline data in January. Haines has tools for data collection. What is the difference between collecting baseline evaluation data and collect positive behavior and attitude data?

## POLK PSN DAP 2016
Approved Strategy Name: |  | Positive Social Norms Approach: Michael Haines Model
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Target audience for messaging | Identify schools who will participate | High Schools | Contact last year's participating school (Rockmart HS) to acknowledge their support to continue PSN messaging | schools/email | STAFF | 2015-07-01 | 2015-08-04 | 2015-08-01 | 2015-09-01
|  |  | Ask Cedartown HS, who was the Control Group last school year, if they will implement the PSN strategy. | schools/email | STAFF | 2015-07-01 | 2015-08-04 | 2015-08-01 | 2015-09-01
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Develop Pre-Survey utilizing Survey Monkey | tbd | STAFF | 2015-07-01 | 2015-08-04 | 2015-08-01 | 2015-09-01
|  |  | Collect Pre-Survey Baseline Data from Schools (Rockmart & Cedartown High Schools) | schools | STAFF, school staff | 2015-08-10 | 2015-08-31 | 2015-09-01 | 2015-09-18
|  |  | Analyze data from schools (Rockmart & Cedartown HS) | tbd | Survey Monkey, STAFF & Evaluator | 2015-09-01 | 2015-09-18 | 2015-09-15 | 2015-10-01
|  |  | Report on results to CPAW & RPS | tbd | STAFF & Evaluator | 2015-09-21 | 2015-09-25 | 2015-10-01 | 2015-11-07
|  |  | Present findings to school administration ((Rockmart & Cedartown HS) and school teachers. Make sure everyone is on board and understanding the data and purpose of the PSN campaign to avoid lack of support from school employees. | Via email, presentations at schools, data packets | STAFF | 2015-09-21 | 9/2152015 | 2015-10-01 | 2015-10-01
|  |  | Create parent newsletter to go home, to create support for campaign | schools | STAFF & School staff | 2015-09-21 | 2015-09-25 | 2015-11-01 | 2015-11-01
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade (Rockmart & Cedartown HS) | Create messages based upon baseline data collected (Fall Pre-Survey 2015) | tbd | STAFF & Evaluator | 2015-09-18 | 2015-09-25 | 2015-10-01 | 2015-10-26
Test messages and media | Determine relevance of messages designed to target population. | 9th-12th grade students at (Rockmart & Cedartown HS) | Identify focus group participants (Student Council & SADD Club) | schools | STAFF & RHS/CHS Youth Action Teams | 2015-08-04 | 2015-09-18 | 2015-10-01 | 2015-10-01
|  |  | Focus group 1: Test sample PSN messages | schools | STAFF & RHS/CHS Youth Action Teams | 2015-09-21 | 2015-09-25 | 2015-09-25 | 2015-09-25
|  |  | Focus group 2: Test draft of PSN msgs based on our data | schools | STAFF & Youth Action Team | 2015-09-28 | 2015-10-02 | 2015-10-01 | 2015-10-01
|  |  | Focus group 3: Present edited PSN mgs based on our data | schools | STAFF & Youth Action Team | 2015-10-05 | 2015-10-09 | 2015-10-09 | 2015-10-09
Create final media | Create messages that reflectstudent's positive attitudes toward prevention of underage drinking | 9th-12th grade students (RHS/CHS) | Incorporate edits based upon feedback from focus groups | tbd | STAFF & Evaluator | 2015-10-12 | 2015-10-16 | 2015-10-10 | 2015-10-10
|  |  | Determine effective media channels. | tbd | STAFF | 2015-10-12 | 2015-10-16 | 2015-10-01 | 2015-10-12
|  |  | Create media-specific messages according to media format | tbd | STAFF | 2015-10-12 | 2015-10-16 | 2015-10-01 | 2015-10-12
|  |  | Present final messages to School Administrators | Via email | STAFF | 2015-10-19 | 2015-10-23 | 2015-10-01 | 2015-10-12
|  |  | Order posters for campaigns | tbd | STAFF | 2015-10-23 | 2015-10-30 | 2015-10-15 | 2015-10-20
Dissimenation of media | Deliver consistent alcohol prevention messages through the proper channels | 9th-11th grade students (RHS/CHS) | Dissimenate first messaging campaign (1 of 3, TBD) | tbd | STAFF & Youth Action Team | 2015-11-02 | 2015-12-04 | 2015-11-06 | 2015-12-18 | Posters were to be taken down during the week of Dec 7-11 at both CHC and RHS. Intervept surveys were to be finished and mailed by Dec 18
|  |  | Dissimentate second messaging campaign (2 of 3)-TBD, based on data | tbd | STAFF & Youth Action Team | 2016-01-05 | 2016-01-29 | 2016-01-29 | 2016-02-04 | Rockmart HS has tweaked locations and placed the second messaging poster up on Feb 4 TH. CHS has not placed second poster up yet because I have never received the intercept surveys.
|  |  | Dissemenate third messaging campaign (3 of 3)-TBD, based on data Column K- RHS Column L- CHS | tbd | STAFF & Youth Action Team | 2016-02-08 | 2016-03-04 |  |  | RHS placed 3rd poster up on May 17. Received intercept surveys from CHS but they have never responded after many emails/texts.
Evaluation of messaging | Determine effectiveness of messaging | 9th-12th grade students (RHS/CHS) | Utilize Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. First intercept survey (1 of 3). | schools | STAFF & Youth Action Team | 2015-12-07 | 2015-12-18
|  |  | Utilize Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (2 of 3). | schools | STAFF & Youth Action Team | 2016-02-01 | 2016-02-05 |  |  | CHS has nor returned the first intercept survey even though it has been promised for more than two months.
|  |  | Utilize Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (3 of 3). | schools | STAFF & Youth Action Team | 2016-03-07 | 2016-03-11
|  |  | Conduct Post survey | school via survey monkey | STAFF | 2016-03-14 | 2016-04-01
Evaluation of Campaign | Determine effectiveness of campaign | 9-12th grade students at RHS/CHS | Conduct post survey | Schools utilizing Survey Monkey | STAFF & Evaluator | 2016-03-14 | 2016-04-01
|  |  | Analyze data from schools (RHS/CHS) | online | STAFF & Evaluator | 2016-04-04 | 2016-04-29
|  |  | Report on results to CPAW & RPS | TBD | Staff | 2016-05-02 | 2016-05-20
|  |  | Present findings to school administration (RHS/CHS) and school teachers. | via email | Staff | 2016-05-02 | 2016-05-20
|  |  | Create newsletter to go home, to further create support for campaign | Via flier sent home through schools; school website; Parent Portal | STAFF & School staff | 2016-05-02 | 2016-05-20
Text Back Campaign-"Rethink the Drink" | Deliver consistent alcohol prevention messages to our targeted population. | 9-12th grade students at RHS/CHS | Create Campaign to reach students at RHS/CHS | NA | STAFF | Ongoing | Ongoing
|  |  | Develop varying messages-Ideas at rethinkthedrink.org | Na | STAFF | Ongoing | Ongoing
|  |  | Increase capacity by presenting text back campaign at school assemblies (text to pledge to" remain alcohol free until 21 and to not get into a car where the driver has been drinking") | High schools | STAFF | 2015-08-04 | 2016-05-20
|  |  | Text prevention messages 2x per month to participants. | NA | STAFF | ongoing | Ongoing
Target audience for messaging | Identify schools who will participate | High Schools | Contact last year's participating schools (Rockmart HS and Cedartown HS) | schools/email | STAFF | 2015-07-27 | 2015-08-04
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Develop Pre-Survey utilizing Survey Monkey | tbd | STAFF | 2016-07-01 | 2016-07-29
|  |  | Collect Pre-Survey Baseline Data from Schools (Rockmart HS and Cedartown HS) | schools | STAFF, school staff | 2016-08-01 | 2016-08-31
|  |  | Analyze data from schools (Rockmart HS and Cedartown HS) | tbd | Survey Monkey, STAFF & Evaluator | 2016-09-01 | 2016-09-16
|  |  | Report on results to CPAW & RPS | tbd | STAFF & Evaluator | 2016-09-19 | 2016-09-23
|  |  | Present findings to school administration (Rockmart HS and Cedartown HS) and school teachers. Make sure everyone is on board and understanding the data and purpose of the PSN campaign to avoid lack of support from school employees. | Via email, presentations at schools, data packets | STAFF | 2016-09-19 | 2016-09-23
|  |  | Create parent newsletter to go home, to create support for campaign | schools | STAFF & School staff | 2016-09-26 | 2016-09-30
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade students(Rockmart HS and Cedartown HS) | Create messages based upon baseline data collected (Fall Pre-Survey 2016) | tbd | STAFF & Evaluator | 2016-09-19 | 2016-09-23
Test messages and media | Determine relevance of messages designed to target population. | 9th-12th grade students at Rockmart HS and Cedartown HS | Identify focus group participants | schools | STAFF & POLK Youth Action Teams | 2016-08-01 | 2016-09-19
|  |  | Focus group 1: Test sample PSN messages | Teen Center | STAFF & POLK Youth Action Teams | 2016-09-26 | 2016-09-30
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on A7: bcnelson1: Too big of a gap between activities? Since you have already been trained by Haines, they can collect baseline data in January. Haines has tools for data collection. What is the difference between collecting baseline evaluation data and collect positive behavior and attitude data?

## FY15-16 Milestone Timeline
Projected Activities (milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Create a Plan to Visit Retailers | bar: Oct to Nov; Apr to May
Recruit Volunteers | bar: Oct to Nov; Apr to May
Meet with Police Chief | bar: Oct to Nov; Apr to May
Create a Plan of Action | bar: Oct to Nov; Apr to May
Visit Retailers | bar: Dec to Jan; Jun to Jul
Educate Retailers after the Visit | bar: Feb to Mar; Jul to Aug
Create a Plan for Rounds 3 & 4 | bar: Sep
Create messages supported by data | bar: Oct
Test messages and media | bar: Oct
Create final media | [12 empty] | AlcoholEDU | bar: Oct
Dissimenation of media | [12 empty] | Cartersville PSN | bar: Nov to Feb
Evaluation of Campaign | [12 empty] | Polk PSN | bar: Mar to May
Text Back Campaign-"Rethink the Drink" | [12 empty] | Cartersville Youthful 21
Educate RMS Community/Staff/Students on AlcoEDU | [12 empty] | Polk Youthful 21 | bar: Oct to Dec
Administer AlcoEDU to 8th grade students | bar: Oct to Dec
Develop a preliminary report on AlcoEDU findings | bar: Jan to Feb
Develop a final report on AlcoEDU findings | bar: Jun to Sep
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.

## Provider Info
Provider Information
Provider Name | Coalition to Prevent the Misuse of Alcohol
Project Coordinator | Scott Sherwin
State Priority | Reduce Youth Access to Alcohol & Binge Drinking
Approved IV/CF | Lack of Parental Monitoring, Compliance with Minimum Drinking/Purchasing Age Laws & Regulations, Low Perceived Risk of Drinking, Provision to Minors; and Availability of Unsupervised Places to Drink / Perception of Risk, Retail Availability; and Social Availability
Assigned Communities & Community Readiness Score (CRS)
Cartersville/CRS | 3
Rockmart/CRS | 3
Memorandum of Agreement Information
Partner/Consultant Information | Role | Pending | Confirmed
CPAW - Bartow | Oversee |  | X
CPAW - Polk | Oversee |  | X
Woodland High School, Principal Dr. Melissa Williams | Partner | X
Rockmart Middle School | Partner | X
Law Enforcement - Chief of Campus Police, Dan Knowles | Partner | X
Bartow Collaborative, Family Connective; Exec Director Tina Grubbs | Partner | X
Political
Cartersville Mayor - Matt Santini
Bartow County Commissioner - Steve Taylor
Rockmart Police Chief - Keith Sorrells
Rockmart Judge Mark Murphy
Rockmart Assistant Supt - Greg Teems
Bartow Schools - Dir Secondary Curriculum - Jim Gottwald
Cartersville Police Chief - Tommy Culpepper

## PMP AlcoholEDU
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | AlcoholEDU
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Perception of Risk / Perceived Harm of Drinking
Strategy Intent: | To increase alcohol-related knowledge, discourage acceptance of underage drinking, and prevent or decrease alcohol use and its related negative consequences.
Target Audience: | Polk - approximately 300 8th grade students at Rockmart Middle
IOM Category | Universal
Estimated Reach: | 300 students total
What is the dosage for this strategy? | 2 sessions each week - and a 30 day follow up.
How frequent will the strategy be implemented? | Each person will be exposed 3 x over the course of the strategy
Necessary Resources for Successful Implementation | Credit carryover from last year - no cost this year
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 3 |  | Mike Carpenter
Number of staff to be hired/contracted: 0 | NA | NA | NA | NA | NA
Staff/Consultant Recruitment Strategy | No additional staff is required; however, we will be working very closely with each school's administration with whom we have established working relationships with over the past two years. | NA | NA | na | NA
Staff/Consultant Training | AlcoholEDU training - as provided by the vendor. | Mike Carpentar | 2015-09-04 | MPR | NA
Staff Retention Strategy | Staff is committed to this effort | NA | NA | NA | NA
Additional Training | NA | NA | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | It will take a well coordinated effort, with each school, to schedule the delivery of this curriculum. We have already had initial conversations with both Cartersville High and Rockmart High. | Mike Carpenter | 2015-11-15 | MPR | NA
Retention Strategies | NA
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Provide school staff information on the program | We will conduct informational webinars or other discussions on the details of the program | Mike Carpenter | 2015-06-30 | MPR | MDS
Provide parents information on the program | We will provide an explanatory letter home to each student participant | Mike Carpenter | 2015-11-15 | MPR | MDS
Deliver the AlcoholEDU program | The 3 science teacher(s) will provide the students with instructions on how to complete the program. We will provide ongoing training and monitoring through our rep with AlcoholEDU. | Mike Carpenter | 2015-11-15 | MPR | MDS
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | We are not planning to modify the current system/structure of this strategy. | NA | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Valerie Gilreath | 2016-06-01
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.(job description, MOU, etc)
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.How many people were hired, for example.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged. (appropriate incentives, be creative - small groups, etc. talk to RPS for ideas)
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on D28: Ongoing is acceptable
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark. (sign-n sheets, post-test, survey)
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on B36: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E36: T A: Discuss the mechanism that will be used to track each indicator.
Note on F36: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP Compliance
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Promotion of Compliance Checks
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | IV: Retail Availability CF: Compliance with Minimum Age Drinking/Purchase Laws
Strategy Intent: | Gain support of public officials, and community so that will they can champion an increase of complaince checks at the rate of 2x/year for all retailers. 4-6x/year for "problem" retailers.
Target Audience: | Government (local) Officials and Law/Court Personnel (prosecutors, judges, administrative/zoning departments) Retailers/Restaurants (117 alcohol retailers within the Cartersville Community licensed). Law Enforcement Agencies. Media (newspaper, tv, etc). General Public
IOM Category | Universal
Estimated Reach: | Government (local) Officials and Law/Court Personnel (prosecutors, judges, administrative/zoning departments) Retailers/Restaurants (117 alcohol retailers within the Cartersville Community licensed). Law Enforcement Agencies. Media (newspaper, tv, etc). General Public
What is the dosage for this strategy? | Meetings as needed with public officials/key stakeholders,
How frequent will the strategy be implemented? | As needed from the stakeholder analysis tool
Necessary Resources for Successful Implementation | Posters, Focus Groups, Meeting Space
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 4 |  | Scott - Bartow; Mike - Polk
Number of staff to be hired/contracted: 0 | We have already contracted with an Evaluator. She will attend future trainings and CPAW meetings. | Scott - Bartow; Mike - Polk | Ongoing | Evaluation Measures | TBD at Eval. Training
Staff/Consultant Recruitment Strategy | Will address if necessary. At this time we do not anticipate the need for additional staff. | NA | NA | NA | NA
Staff/Consultant Training | We will partner with GASPS and other providers to identify training | Scott - Bartow; Mike - Polk | NA | NA | NA
Staff Retention Strategy | Frequent communications, staff development | Scott - Bartow | NA | Measure against our timeline | NA
Additional Training | TBD | Scott - Bartow | NA | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | In both communities we have already begun engaging key leaders in order to gain their support before moving forward with our strategy. We have met with each city's Mayor and have received their support and willingness to assist us as we move forward. We are drafting letters, to be signed by each Mayor, that will be presented to local retailers, through the assistance of law enforcement, and will ask for voluntary participation. We will explain the importance of their compliance with our strategy. | Scott - Bartow; Mike - Polk | NA | NA | NA
Retention Strategies | To keep our communities involved, we will implement a "Youthful 21" approach to finding out whether local retailers are in compliance with the current laws surrounding the sale of alcohol to adults under 21 years of age. Once we have attained the data we need, we will share the results with key stakeholders. | Scott - Bartow; Mike - Polk | NA | NA | NA
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Presenting our findings to civic groups, school personnel, students and parents to support increase enforcement of alcohol related laws. | We will coordinate our activities through local government officials, law enforcement, and school administration with whom we have succesfully established relationships. Some of the officials are involved on our CPAW and others serve as advisors. We will schedule a variety of engagements throughout the year. | Scott - Bartow; Mike - Polk | Ongoing | MPR | Agenda and/or Sign-in Sheet
Partner with local business owners/retailers to create establishment 'best practices & policies' that in turn will decrease the chance that servers and sellers illegally sell alcohol to underage persons. | We have the support of local officials and will use their influence (letters, speaking) to increase awareness and show a unified effort. | Scott - Bartow; Mike - Polk | Ongoing | MPR | Submissions into MDS and/or MOUs
To raise awareness, we plan to partner with law enforcement to increase the number of compliance checks across each community. | We plan to ask local law enforcement to sign an MOU showing their support of our effort. | Scott - Bartow; Mike - Polk | Ongoing | MPR | MOUs
We will offer online server training to a selected group of licensees. | Once the target group has been identified (criteria= x number of violations within a given year) we will meet with the owner/operators to explain/offer the server training curriculum. The organization we chose to implement is Professional Server Certification Corporation (PSCC) which is a nationally recognized leader in the field. They offer state-of-the art training which may help our local businesses reduce their liability and/or fines in the event of a citation. | Scott - Bartow; Mike - Polk | 2016-07-31 | Online Certificates | Number of Completions per Establishment
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | Alcohol licensees are informed that compliance checks will be conducted at various times and penalties for non-compliance do apply. Our adaptation to the current process will include our staff providing the retailers with a folder of information along with posters which details the compliance statutes. | Scott - Bartow; Mike - Polk | Ongoing | MPR and/or MDS | Number of Folders provided to retail establishments
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Scott - Bartow; Mike - Polk | 2016-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on B16: bcnelson1: Fantastic!
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on E19: bcnelson1: How are you going to ensure what needs to get done does? At the appropriate time? Consistently? thanks
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on B24: bcnelson1: Recruitment is insufficient and a high risk for a successul implementation. Only voluntary so depends on mayor support + law enforcement. Depends on if you can get the mayor to write the letter and also how much influence will a mayor provide onto retailers? Look into insurance incentives w/ TIPPS.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A34: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A36: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A40: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP PSN HAINES
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name: | Positive Social Norms Approach: Haines Model
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy: | Perception of Risk / Perceived Harm of Drinking
Strategy Intent: | Our intent is to discourage youth's current acceptance of underage drinking, and prevent or decrease alcohol use and its related negative consequences.
Target Audience: | Bartow: All students at Woodland High School and all students at Cartersville High School; Polk: All students at Rockmart High School.
IOM Category | Universal
Estimated Reach: | Woodland High School: 1600; Cartersville High School:1100; Rockmart High School:
What is the dosage for this strategy? | 3 schools-No control group due to the lack of a homogenous population between the schools.
How frequent will the strategy be implemented? | The messages will change up to every 6 weeks.
Necessary Resources for Successful Implementation | 5000
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 3 |  | Christa - Bartow; Mike - Polk
Number of staff to be hired/contracted: 0 | NA | NA | NA | NA | NA
Staff Retention Strategy | Staff is committed to this effort. | Christa - Bartow; Mike - Polk | Ongoing | NA | NA
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies | It will take a well coordinated effort, with each school to schedule the pre-surveys to establish our baseline data. We have already established good relationships with Cartersville, Woodland, and Rockmart High administration. | Christa - Bartow; Mike - Polk | NA | MPR | Agendas and Rosters
Retention Strategies | Our staff is committed to this effort, and will be meeting with administration at each of the high schools to coordinate dates for conducting the pre-surveys to collect our baseline data. | Christa - Bartow; Mike - Polk | TBD | MPR | Agendas and Rosters
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Provide alcohol awareness messages. | Through an ongoing text back campaign. | Christa - Bartow; Mike - Polk | Ongoing | MPR | MDS
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | We do not plan to modify the plan. Meet as a group and develop a local implementation plan. | Christa- Bartow; Mike - Polk | NA | NA | NA
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation? |  | Valerie Gilreath, Evaluator | 2016-09-30
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on B3: bcnelson1: What model are you using? Also, I will be holding comments on Positive Social Norms until after the training in Macon next week & you've had a chance to edit as well.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on A19: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A20: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B20: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E20: T A: Discuss the mechanism that will be used to track each indicator.
Note on F20: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A21: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A22: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on A24: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A25: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B25: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E25: T A: Discuss the mechanism that will be used to track each indicator.
Note on F25: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A29: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A31: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A35: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## POLK Alcohol Edu DAP
Approved Strategy Name: |  | Alcohol Edu (Polk ONLY)
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Deliver the AlcoholEDU program, Rockmart MS | Alcohol EDU administration | One class of 8th graders | Assess a class of 8th grade students in the fall of the year during science class to see if there will be any complications with using Ipads with the Alcohol EDU program | Rockmart Middle School | CPMA Team, RMS adm | 2015-09-01 | 2015-09-30
Deliver the AlcoholEDU program, Rockmart MS | Alcohol EDU administration | Four classes of 8th graders | Assess the reminder of the 8th grade students in the fall of the year during science class using Ipads with the Alcohol EDU program | Rockmart Middle School | CPMA Team, RMS adm | 2015-09-01 | 2015-09-30
Review logistics | Feedback | Everfi/RMS | Follow up one month later. And complete pre/post state and program evals. | Rockmart Middle School | CPMA Team, RMS adm, Everfi Staff | 2015-11-01 | 2015-11-15
Determine viability of continuing Alcohol Edu | Alcohol EDU funding for 2015-16 | RMS and Cedartown HS | Meet with Everfy and our CPMA team to discuss our options for 2016-17. | Rockmart Middle School | CPMA Team and Everfi Staff | 2016-01-01 | 2016-03-01
Examine the Everfi contract for 2015-16 | Feedback | Rockmart High School | Make a decision if RMS will support administering alcohol EDU to 8th graders online for the fourth year and ask Cedartown if it would offer the course for 9th graders during health classes at Cedartown HS. Everfi has agreed to offer Alcohol EDU for the first semester in 2015 at no cost; however, both schools would be charged for the program second semester in 2016. At this time Cedartown High School's administration appears to not be supportive. In addition, Everfi prefers for schools to use computers over Ipads with their online Alcohol EDU program where Polk County has invested Ipads for every student. | Rockmart Middle School Cedartown High School | CPMA Team, administration at RMS and CHS | 2016-05-01 | 2016-07-01
| Feedback | RMS and Cedartown HS | If admistrators give their consent, all 8th RMS students and 9th CHS students will be administered Alcohol EDU during the fall of 2016-17 school year. | Rockmart Middle School Cedartown High School | CPMA Team, RMS adm, Everfi Team | 2016-09-01 | 2017-01-01
| Feedback | RMS and Cedartown HS | If Alcohol EDU went smoothly fall semester at either or both RMS and Cedartown HS and if funding is available, 8th graders at RMS students and/or 9th graders at CHS students will be administered Alcohol EDU during the spring semester of 2016-17 school year. | Rockmart Middle School Cedartown High School | CPMA Team, RMS adm, Everfi Team | 2016-01-01 | 2016-06-01
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## BARTOW Compliance DAP 2015
Approved Strategy Name: |  | Compliance Checks
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Develop a "Youthful 21" Campaign as a Compliance Check | Create a plan to visit retailers | Retailers who sell, but do not serve, alcohol.
Identify the Retail Establishments, within our target areas, who sell alcohol. Gain an accurate count of the locations.
|  |  | Research the existing licensed retailers | Community | Scott | 2015-12-01 | 2014-12-31 | 2014-12-01 | 2014-12-15 | 13 Retailers in Bartow
|  |  | Create a list of retailers located within the Cartersville City Limits | Community | Scott | 2015-12-01 | 2014-12-31 | 2014-12-01 | 2014-12-15
|  |  | Discuss list with CPMA team and create a schedule for visiting the locations. | CPMA | Team | 2015-01-20 | 2015-02-27 | 2015-02-01 | 2015-02-27
| Recruit Volunteers | Young Adults
|  |  | Identify and Train two "youthful" appearing adult (21 years or older) willing to participate. One male & one female. | CPMA | Team | 2015-02-01 | 2015-02-27 | 2015-04-29 | 2015-05-11 | Meeting with Josh Haire & Courtny Davis to discuss the campaign
|  |  | Ask volunteers to assist us with strategy | CPMA | Scott | 2015-02-01 | 2015-02-27 | 2015-05-11 | 2015-05-22
|  |  | Review responsibilities and discuss availability and timelines for both communities. | CPMA | Scott | 2015-03-01 | 2015-03-31 | 2015-05-11 | 2016-05-11 | Chose two youthful 21 individuals (Josh & Courtney) to visit both communities
| Meet with Police Chief | Chief Culpepper | Hold a meeting with the Chief to explain the program and to gain his support. | Police Station | Scott & Christa | 2015-04-11 | 2015-04-11 | 2015-04-11 | 2015-04-11 | Met with Chief
|  |  | Ask for a letter of endorsement |  |  | 2015-04-11 | 2015-04-11 | 2015-04-11 | 2015-04-11 | Received Letter via email
| Create a Plan of Action | Team
|  |  | Develop an action plan/calendar to visit retailers. | Community | Scott | 2015-04-01 | 2015-04-15 | 2015-05-11 | 2015-05-11 | Visited alcohol retailers one week and then the following week
|  |  | Selected Adult will visit retailers to purchase alcohol; and, a) If the Adult is asked for an ID - they should state they "left it at home" and see if the sale is allowed to move forward; or b) if the Adult is NOT asked for an ID, they are to purchase the alcohol and leave. | Community | Scott, Recruits |  |  |  |  | In Cartersville the two youthful 21 individuals visited the retailers in the late afternoon/evening on the same day each of the two weeks .
| Visit Retailers | City Retailers
|  |  | Visit 13 Retailers | Community | Scott, Recruits | 2015-04-15 | 2015-05-15 | 2015-05-11 | 5/272015 | Cartersville
|  |  | Report Results | CPMA | CPMA | 2015-05-15 | 2015-06-15 | 2015-06-30 | 2015-06-30 | Meeting with Police Chief
|  |  | Gather and update media contact lists | Community | Scott | 2015-05-15 | 2015-06-15 | 2015-07-01 | 2015-07-01
|  |  | Coordinate promotional effort with law enforcement agencies in the arena of compliance checks | Community | Scott | 2015-05-15 | 2015-06-15 | 2015-06-30 | 2015-07-15 | Plan to meet with Asst Chief McCann in the near future to get him up to speed on this initiative
|  |  | Write a media advisory and news release about compliance checks | Community | Scott | 2015-06-15 | 2015-07-01
|  |  | Encourage the local paper to run an article about the effect of illegal purchase of alcohol in Cartersville | Community | Scott | 2015-07-01 | 2015-12-01 |  |  | We are going to wait until Round 2 is completed before doing this.
|  |  | Mail a media advisory to key media contacts | Community | Scott | 2015-07-01 | 2015-12-01
|  |  | Propose / present your best practices to town/council meetings and use data to help drive the promotional effort of compliance checks. Present best practies to leadership at agencies that are conducting compliance checks. Attempt to get agencies to adopt best practies. Helping to institionalize the proposed changes can be a good way to help them become sustained. Helping agencies that are tasked with this conducting compliance checks by provinding them with usful information, models and public support. | Community | Scott | 2015-07-01 | Ongoing
| Educate Retailers | Round 1 Locations
|  |  | Provide a letter to the Store Owner/Operator letting them know about this initiative and the results of our visit to their location. | Community | Scott | 2015-08-01 | Ongoing |  |  | Provide the specifics of our visit and the details of their clerks actions.
|  |  | Develop Reward & Reminder Cards |  | Scott | 2015-09-01 | 2015-09-05 | 2015-09-01 | 2015-09-25 | City Police gave permission to add their emblem at our last CPAW mtg.
|  |  | Get approval from DBHDD on Cards |  | Scott | 2015-09-06 | 2015-09-06 | 2015-09-01 | 2015-09-30
|  |  | Print Cards for distribution |  | Scott | 2015-10-01 | 2015-10-15 | 2015-09-30
Create a Plan for Round 2
|  |  | Plan for the following year, based on this years experiences. Sustainability of our efforts | Office | Scott | 2015-07-01 | Ongoing
|  |  | Draft a realistic plan to maintain visibility within our community and to ensure the viability of ongoing compliance checks. | Office | Scott | 2015-07-02 | Ongoing
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## POLK FY Compliance DAP
Approved Strategy Name: |  | Compliance Checks
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Develop a "Youthful 21" Campaign | Find out which, if any, retailers are selling alcohol to minors. | Retailers who sell, but do not serve, alcohol. | Identify the Retail Establishments, within our target areas, who sell alcohol. Gain an accurate count of the locations.
|  |  | Research the existing licensed retailers | Community | Scott, Mike | 2015-12-01 | 2014-12-31 | 2014-12-01 | 2014-12-15 | 10 businesses in Polk
|  |  | Create a list of retailers located within the Rockmart City Limits | Community | Mike | 2015-12-01 | 2014-12-31 | 2014-12-01 | 2014-12-15 | List created
|  |  | Discuss list with CPMA team and create a schedule for visiting the locations. | CPMA | Team | 2015-01-20 | 2015-02-27 | 2015-02-01 | 2015-02-27 | Plan for visiting businesses has been determined in Polk/Rockmart
|  |  | Identify and Train a "youthful" appearing adult (over 21) willing to participate. | CPMA | Team | 2015-02-01 | 2015-02-27 | 2015-04-29 | 2015-05-11 | Meeting with Josh Haire to discuss the campaign
|  |  | Ask candidate to assist us with strategy | CPMA | Mike | 2015-02-01 | 2015-02-27 | 2015-05-11 | 2015-05-22 | In Polk Mike coordinated his efforts with the Sheriff's Department; however, for consistency we decided to use the same youth 21 individuals.
|  |  | Review responsibilities and discuss availability and timelines for both communities. | CPMA | Mike | 2015-03-01 | 2015-03-31 | 2015-05-11 | 2016-05-11 | Chose two youthful 21 individuals (Josh & Courtney) to visit both communities
|  |  | Create a plan (milestones) to visit retailers. | Community | Mike | 2015-04-01 | 2015-04-15 | 2015-05-11 | 2015-05-11 | Visited alcohol retailers one week and then the following week
|  |  | Selected Adult will visit retailers to purchase alcohol; and, a) If the Adult is asked for an ID - they should state they "left it at home" and see if the sale is allowed to move forward; or b) if the Adult is NOT asked for an ID, they are to purchase the alcohol and leave. | Community | Mike, Josh H. |  |  |  |  | In Cartersville the two youthful 21 individuals visited the retailers in the late afternoon/evening on the same day each of the two weeks while ln Rockmart they visited the retailers in the early afternoon.
|  |  | Visit Retailers | Community | CPMA | 2015-04-15 | 2015-05-15 | 2015-05-11 | 5/272015 | Rockmart
|  |  | Report Results | CPMA | CPMA | 2015-05-15 | 2015-06-15 | 2015-06-20
|  |  | Gather and update media contact lists | Community | Mike | 2015-05-15 | 2015-06-15 | 2015-06-20
|  |  | Coordinate promotional effort with law enforcement agencies in the arena of compliance checks | Community | Mike | 2015-05-15 | 2015-06-15 | 2015-06-30
|  |  | Write a media advisory and news release about compliance checks | Community | Mike | 2015-06-15 | 2015-11-01
|  |  | Encourage the local paper to run an article about the effect of illegal purchase of alcohol in Cartersville | Community | Mike | 2015-07-01 | 2015-11-01
|  |  | Mail a media advisory to key media contacts | Community | Mike | 2015-07-01 | 2015-07-31
|  |  | Propose / present your best practices to town/council meetings and use data to help drive the promotional effort of compliance checks. Present best practies to leadership at agencies that are conducting compliance checks. Attempt to get agencies to adopt best practies. Helping to institionalize the proposed changes can be a good way to help them become sustained. Helping agencies that are tasked with this conducting compliance checks by provinding them with usful information, models and public support. | Community | Mike | 2015-07-01 | Ongoing
|  |  | Plan for the following year, based on this years experiences. Sustainability of our efforts | Office | Mike | 2015-07-01 | Ongoing
|  |  | Draft a realistic plan to maintain visibility within our community and to ensure the viability of ongoing compliance checks. | Office | Mike | 2015-07-02 | Ongoing
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## BARTOW PSN DAP
Approved Strategy Name: |  | Positive Social Norms Approach: Michael Haines Model
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Collect Data from Schools (Woodland HS, Cartersville HS) |  |  | 2014-09-17 | 2014-10-05 | 2014-09-08 | 2014-11-01 | We were able to begin surveying earlier than expected; however, it took a longer period of time to obtain the total number of needed surveys from each of the 3 schools.
|  |  | Analyze data from schools (Woodland HS, Cartersville HS) |  | Survey Monkey & Val Gilreath | 2014-10-06 | 2014-10-22 | 2014-11-01 | 2014-11-03 | We did not require as long to evaluate the data as we previously thought. Since we were able to use Survey Monkey, it anazlyzed the data for us.
|  |  | Report on results |  | STAFF & Evaluator | 2014-11-01 | 2014-11-15 | 2014-11-03 | 2014-11-03 | Our evaluator created a one page summary report on the analyzed data for us to present.
|  |  | Present findings to school administration (WHS, CHS) and CPAW, and RPS (Brad Nelson) | Via email | Christa & Mike | 2014-10-23 | 2014-10-31 | 2014-11-14 | 2014-11-14
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade students(Cartersville, Woodland) | Create messages based upon baseline data collected. |  | STAFF | 2014-11-01 | 2014-11-30 | 2014-12-10 | 2014-12-12 | With help from our RPS, the team was able to look at the data and craft two solid messages to be used over the Spring semester at school.
Test messages and media | Determine relevance of messages designed to target population. | 9th-11th grade students(Cartersville, Woodland) | Hold focus groups to test all messages with 9th-12th grade students from the selected high schools. | tbd | STAFF & Evaluator | 2014-12-01 | 2014-12-31 | 2014-12-09 | 2015-01-07 | A focus group in Bartow was put together and met twice. The first focus group was to get the youth's opinions on some PSN messages in order to incorporate the components that they liked, into our messages. The second focus group was where the youth actually looked at and gave feedback on our messages and their graphics. The same was done in Polk County.
Create final media | Create messages that reflectstudent's positive attitudes toward prevention of underage drinking | 9th-12th grade students (Cartersville, Woodland, & Rockmart High) | Incorporate edits based upon feedback from test messaging. | tbd | STAFF & Evaluator | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | We created our final finished posters after having to delay the last focus group in Polk to Jan. Printing took a little while longer due to the format of one of the posters. We had to recreate that poster in a different program so that it was at a high enough resolution for the printer.
|  |  | Determine effective media channels. | tbd | STAFF | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | The students at our focus group in Bartow and the students at the focus in group in Polk, were able to give us specific locations throughout the school that they thought would be the most effective locations for our posters to be hung.
|  |  | Create media-specific messages according to media format | tbd | STAFF | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | All of our messages are in poster format.
Dissimenation of media | Deliver consistent alcohol prevention messages through the proper channels | 9th-11th grade students(Cartersville, Woodland) | Dissimenate first messaging campaign (1 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-01-01 | 2015-02-13 | 2015-01-26 | 3/2/2015 (Bartow) and 2/27/15 (Polk) | All schools began their first round of messaging the week of Jan. 26th. Due to inclement weather, Bartow was unable to take down 1st msg until 3/2/15
|  |  | Dissimentate second messaging campaign (2 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-02-01 | 2015-03-15 | 3/12/2015 (Bartow) | 4/13/15 (Bartow) | Because of inclement weather, Bartow's schedule was altered. 2nd message did not go up until 3/12.
|  |  | Dissemenate third messaging campaign (3 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-03-15 | 2015-05-01 | 4/20/2015 (Bartow | 5/8/15 (Bartow) | Third message has been put up (Bartow)
Evaluation of messaging | Determine effectiveness of messaging | 9th-12th grade students (Cartersville, Woodland, & Rockmart High) | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. First intercept survey (1 of 2). |  | STAFF & Bartow Youth Action Team | 2015-02-09 | 2015-02-13 | 3/9 (Bartow) & 3/2/15 (Polk) | 3/11/15 (Bartow); 3/6/15 (Polk) | As noted above, due to inclement weather dates had to be altered for Bartow.
|  |  | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (2 of 2). |  | STAFF & Bartow Youth Action Team | 2015-03-23 | 2015-04-03 | 2015-04-13 | 2015-04-17 | Completed.
Control Group (Adairsville High and Cedartown High) | Determine the effectiveness of the campaign versus without the PSN campaign | 9th-12th grade students (Adairsville & Cedartown High School) | Conduct Pre survey |  | STAFF | 2015-01-05 | 2015-02-01 | 2/4/2015 (Bartow & Polk) | 2/18/15 (Bartow); Polk still in progress | Control group schools are so far being cooperative.
|  |  | Conduct Post survey |  | STAFF | 2015-05-01 | 2015-05-30 | 2015-05-11 | 2015-05-22 | Did not get the amount of survey responses that we needed. Learned that it is very difficult to accomplish anything in the schools during the month of May. Will finish PSN campaign by April next school year.
Evaluation of Campaign | Determine effectiveness of campaign | 9th-11th grade students(Cartersville, Woodland) | Conduct post survey | tbd | STAFF & Evaluator | 2015-09-01 | 2015-10-01 | 2015-05-11 | 2015-05-22 | Did not get the amount of survey responses that we needed. Learned that it is very difficult to accomplish anything in the schools during the month of May. Will finish PSN campaign by April next school year.
Text Back Campaign-"Rethink the Drink" | Deliver consistent alcohol prevention messages to our targeted population. | 9th-11th grade students(Cartersville, Woodland) | Create Campaign to reach students at Woodland, Cartersville, and Rockmart High Schools as a community readiness strategy. | NA | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | 2015-05-22 | Text back pledge campaign grew each month!
|  |  | Develop varying messages-Ideas at rethinkthedrink.org | Na | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
|  |  | Increase capacity by presenting text back campaign at school assemblies (text to pledge to" remain alcohol free until 21 and to not get into a car where the driver has been drinking") | High schools | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | 2015-05-22 | Were able present the text back pledge to about 1300 students at Bartow Teen Maze in May 2015.
|  |  | Text prevention messages 2x per month to participants. | NA | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on A4: bcnelson1: Too big of a gap between activities? Since you have already been trained by Haines, they can collect baseline data in January. Haines has tools for data collection. What is the difference between collecting baseline evaluation data and collect positive behavior and attitude data?

## POLK PSN DAP
Approved Strategy Name: |  | Positive Social Norms Approach: Michael Haines Model
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Collect baseline evaluation data | Identify actual and perceived norms | Staff | Collect Data from Rockmart HS |  |  | 2014-09-17 | 2014-10-05 | 2014-09-08 | 2014-11-01 | We were able to begin surveying earlier than expected; however, it took a longer period of time to obtain the total number of needed surveys from each of the 3 schools.
|  |  | Analyze data from Rockmart HS |  | Survey Monkey & Val Gilreath | 2014-10-06 | 2014-10-22 | 2014-11-01 | 2014-11-03 | We did not require as long to evaluate the data as we previously thought. Since we were able to use Survey Monkey, it anazlyzed the data for us.
|  |  | Report on results |  | STAFF & Evaluator | 2014-11-01 | 2014-11-15 | 2014-11-03 | 2014-11-03 | Our evaluator created a one page summary report on the analyzed data for us to present.
|  |  | Present findings to school administration (WHS, CHS, RHS) and CPAW, and RPS (Brad Nelson) | Via email | Christa & Mike | 2014-10-23 | 2014-10-31 | 2014-11-14 | 2014-11-14
Create messages supported by data | Create messages that reflect student's positive attitudes toward prevention of underage drinking | 9th-11th grade students(Rockmart High) | Create messages based upon baseline data collected. |  | STAFF | 2014-11-01 | 2014-11-30 | 2014-12-10 | 2014-12-12 | With help from our RPS, the team was able to look at the data and craft two solid messages to be used over the Spring semester at school.
Test messages and media | Determine relevance of messages designed to target population. | 9th-12th grade students (Rockmart High) | Hold focus groups to test all messages with 9th-12th grade students from the selected high schools. | tbd | STAFF & Evaluator | 2014-12-01 | 2014-12-31 | 2014-12-09 | 2015-01-07 | A focus group in Bartow was put together and met twice. The first focus group was to get the youth's opinions on some PSN messages in order to incorporate the components that they liked, into our messages. The second focus group was where the youth actually looked at and gave feedback on our messages and their graphics. The same was done in Polk County.
Create final media | Create messages that reflectstudent's positive attitudes toward prevention of underage drinking | 9th-12th grade students (Rockmart High) | Incorporate edits based upon feedback from test messaging. | tbd | STAFF & Evaluator | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | We created our final finished posters after having to delay the last focus group in Polk to Jan. Printing took a little while longer due to the format of one of the posters. We had to recreate that poster in a different program so that it was at a high enough resolution for the printer.
|  |  | Determine effective media channels. | tbd | STAFF | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | The students at our focus group in Bartow and the students at the focus in group in Polk, were able to give us specific locations throughout the school that they thought would be the most effective locations for our posters to be hung.
|  |  | Create media-specific messages according to media format | tbd | STAFF | 2014-12-01 | 2014-12-31 | 2014-12-17 | 2015-01-07 | All of our messages are in poster format.
Dissimenation of media | Deliver consistent alcohol prevention messages through the proper channels | 9th-12th grade students (Cartersville, Woodland, & Rockmart High) | Dissimenate first messaging campaign (1 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-01-01 | 2015-02-13 | 2015-01-26 | 2/27/15 (Polk) | All schools began their first round of messaging the week of Jan. 26th.
|  |  | Dissimentate second messaging campaign (2 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-02-01 | 2015-03-15
|  |  | Dissemenate third messaging campaign (3 of 3) | tbd | STAFF & Bartow Youth Action Team | 2015-03-15 | 2015-05-01
Evaluation of messaging | Determine effectiveness of messaging | 9th-12th grade students (Rockmart High) | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. First intercept survey (1 of 2). |  | STAFF & Bartow Youth Action Team | 2015-02-09 | 2015-02-13 | 3/2/15 (Polk) | 3/6/15 (Polk)
|  |  | Utilize Bartow Youth Action Team to perform intercept survey between each message rotation to determine message effectiveness. Second intercept survey (2 of 2). |  | STAFF & Bartow Youth Action Team | 2015-03-23 | 2015-04-03 | 2015-04-13 | 2015-04-17 | Completed.
Control Group (Adairsville High and Cedartown High) | Determine the effectiveness of the campaign versus without the PSN campaign | 9th-12th grade students (Cedartown High School) | Conduct Pre survey |  | STAFF | 2015-01-05 | 2015-02-01 | 2015-02-04 | Polk still in progress | Control group schools are so far being cooperative.
|  |  | Conduct Post survey |  | STAFF | 2015-05-01 | 2015-05-30
Evaluation of Campaign | Determine effectiveness of campaign | 9th-12th grade students (Rockmart High) | Conduct post survey | tbd | STAFF & Evaluator | 2015-09-01 | 2015-10-01
Text Back Campaign-"Rethink the Drink" | Deliver consistent alcohol prevention messages to our targeted population. | High school students at Rockmart | Create Campaign to reach students at Rockmart High Schools as a community readiness strategy. | NA | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
|  |  | Develop varying messages-Ideas at rethinkthedrink.org | Na | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
|  |  | Increase capacity by presenting text back campaign at school assemblies (text to pledge to" remain alcohol free until 21 and to not get into a car where the driver has been drinking") | High schools | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
|  |  | Text prevention messages 2x per month to participants. | NA | STAFF | 2013-12-01 | Ongoing | 2013-12-01 | Ongoing
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.
Note on A4: bcnelson1: Too big of a gap between activities? Since you have already been trained by Haines, they can collect baseline data in January. Haines has tools for data collection. What is the difference between collecting baseline evaluation data and collect positive behavior and attitude data?

## POLK RASS DAP
Approved Strategy Name: |  | RASS & Compliance Checks (Polk ONLY)
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Continue to educate the Rockmart Community on compliance checks and RASS training and how these strategies work to reduce underage alcohol use. | Meet with community leaders in Rockmart City on the importance of reducing underage drinking and increasing the number of compliance checks and RASS training. | Family Connection, Judge Murphy's Stakeholders | Meet with Family Connection, Judge Murphy's Stakeholders and service clubs to educate the community about how compliance checks and RASS training working together will reduce underage drinking. | Rockmart City | CPMA Team | 2014-09-01 | 2014-12-30 | 2014-09-01 | 2014-11-01 | Businesses in Rockmart that sell and serve alcohol were offered RASS training online. They were notified of the services by personal phone calls and certified letters. Four businesses asked for online codes. One administered training.
Continue to collaborate with law enforcement to emphasize the importance of increasing the number of compliance checks each year. | Meet with law enforcement agencies in Polk County, etc. and specifically Rockmart City to increase the number of compliance checks. | Law enforcement agencies in Rockmart City, Sheriff's Department & Polk Drug Rask Force. | Conferred with the Polk County Sheriff's Department (Jonathan Blackmon) and Polk County Drug Task Force, Rockmart City Police (Chief Keith Sorrells), and the State Division of Alcohol and Tobacco Division (ATD) to focus on increasing the number of compliance check. | Rockmart City and Polk County | CPMA Team and RPS | 2014-12-01 | 2015-01-01 | 2015-01-01 | 2015-02-01 | Because there was little support from the Rockmart City Gvmt for employees to have RASS training that sell and serve alcohol, it was decided to focus on Compliance Checks. If businesses did not comply to check IDs they would be again offered RASS training. See the tab on Compliance Checks.
Continue to collaborate with Rockmart City Council and Govt to offer RASS training to employees that sell or serve alcohol. | Meet with Rockmart City leaders to promote developing a proactive stance on RASS training being required for a business license for those that sell or serve alcohol. | Rockmart City Council, Govt, and businesses that sell or serve alcohol. | Present to the Rockmart City Council a plan to offer a RASS training component for all businesses that serve or sell alcohol and/or businesses that have been found guilty of selling/serving alcohol to underage youth.
Publicize in print on billboards, sinage, text back campaign and/or on radio, etc. businesses that support offering RASS training to their employees. | Publicity educate the community in Rockmart City about RASS training and share the names of the businesses that support our underage alcohol initiative. | Fish Wrap, Rockmart Newspaper, others | During Red Ribbon Week, before Christmas break, St Patrick's Day, and Cinco de Mayo, for example, publicize the problem with underage alcohol use among youth and to counteract this with Compliance Checks and RASS training.
Invite businesses that sell or serve alcohol to show their support by requiring employees to complete RASS training. | Communicate with businesses that sell or serve alcohol to be proactive by offering certification training on the Georgia State Law to employees. | Businesses that sell or serve alcohol | Contact businesses every four months (Oct 2014, Feb 2015 and June 2015) to encourage their participation in RASS training.
After meeting with our RPS our CPMA team agreed to modify our POLK strategy and move it into our new Compliance Check DAP for both Bartow and Polk. Our plan, however, is to continue to offer RASS training to any businesses that attempt to sell alcohol to our Youthful 21 individuals that do not have an ID.
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY14-15 Milestone Timeline
AlcoholEDU
Projected Activities (milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Polk RASS
Deliver the AlcoholEDU program, Rockmart MS | [12 empty] | Positive Social Norms | bar: Oct to Nov
Review logistics | [12 empty] | Cartersville Compliance | bar: Nov
Deliver the AlcoholEDU program, Rockmart MS | bar: Nov to Jan
Review logistics | bar: Jan
Deliver the AlcoholEDU program, Rockmart MS | bar: Jan to Mar
Review logistics | bar: Mar
Deliver the AlcoholEDU program, Rockmart MS | bar: Mar to May
Review logistics | bar: May to Jun
Determine viability of continuing Alcohol Edu | bar: May to Aug
Continue to educate the Rockmart Community on compliance checks and RASS training and how these strategies work to reduce underage alcohol use.
Continue to collaborate with law enforcement to emphasize the importance of increasing the number of compliance checks each year.
Continue to collaborate with Rockmart City Council and Govt to offer RASS training to employees that sell or serve alcohol.
Publicize in print on billboards, sinage, text back campaign and/or on radio, etc. businesses that support offering RASS training to their employees.
Invite businesses that sell or serve alcohol to show their support by requiring employees to complete RASS training.
Collect baseline evaluation data | bar: Oct to Nov
Create messages supported by data | bar: Nov
Test messages and media | bar: Dec
Create final media | bar: Dec
Dissimenation of media | bar: Jan to May
Evaluation of Campaign | bar: Sep
Text Back Campaign-"Rethink the Drink" | bar: Dec to Sep
If we decide to move forward, our next step is to work with the individual law enforcement agency to help promote their compliance check policy. | bar: Oct to Feb
Media Awareness Campaign | bar: Mar to Sep
Propose / present your best practices to town/council meetings and use data to help drive the promotional effort of compliance checks | bar: Apr to Sep
Plan for the following year, based on this years experiences | bar: May to Sep
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.