## Implementation Plan Guidance
IMPLEMENTATION PLAN
INSTRUCTIONS FOR COMPLETING THE IMPLEMENTATION PLAN NOTE: Prepared in 8.5 x 14
1. Save the IMPLEMENTATION PLAN Excel as: Your Provider Name-State Priority [EX: Alpha/Omega Center-Priority 1]
2. There are THREE Parts to the IMPLEMENTATION PLAN:
Part 1 - Project Management Plan (PMP)
Part 2 - Detailed Action Plan (DAP)
Part 3 - At-A-Glance Milestone Timeline
3. The IMPLEMENTATION PLAN is informed by your APPROVED Strategic Plan. Each plan should have at least 3 strategies , otherwise known as your Prevention Portfolio. To start, replace each PMP Strategy Tab and each Strategy DAP name with the name of your specific APPROVED strategies - one strategy per tab.
Part 1 - Project Management Plan (PMP) (one per strategy)
There are two primary sections that you will be required to complete:
I. SCOPE Considerations
II. Community Readiness
1.1 Although the questions are the same under each PMP Strategy tab, your responses are specific to the strategy.
1.2 Please provide as much detail as possible for all questions. For Excel 2007 users, adjust your cell to accommodate your narrative responses by doing the following: Home/Cells/Format/AutoFit Row Height.
1.3 To ensure that questions were not omitted, please note NA (not applicable) or zero (0) when appropriate.
The PMP will also introduce two areas for you to review and begin thinking about in preparation for the Evaluation Training. NOTE: There are only a few cells to complete in these sections. Do not attempt to address the blackened sections at this time.
III. Fidelity
IV. Evaluation & Data Collection
Part 2 - Detailed Action Plan (DAP) (one per strategy)
The Detailed Action Plan is designed to outline all of the core activities and action steps necessary to successfully implement your APPROVED strategy. Also use this tab to outline any capacity efforts associated with the Approved Strategy (See EXAMPLE Tab).
Part 3 - At-a-Glance Milestone Timeline (one per prevention portfolio)
This Gannt-style timeline is designed to outline the approximate start and completion of major activities, otherwise referred to as the milestones, assocated with each strategy. Please note this timeline is not intended to capture all of the multiple action steps detailed in column D of the Detailed Action Plan tabs. Instead, Providers should refer to column A in their Detailed Action Plan tabs to guide them in this process.
When printing out your Implementation Plan or sections of the plan:
1) Highlight the section(s) to be printed.
2) Go to the Page Layout Tab and select Print Area
3) Under Print Area, select Set Print Area.
4) Print
The IMPLEMENTATION PLAN to include all three parts will be due two weeks from the date of your Regional Training.
If you have any questions or need additional assistance completing the Implementation Plan, please submit your questions via ECCO..

## Provider Info
Provider Information
Provider Name
Project Coordinator
State Priority
Approved IV/CF
Assigned Communities & Community Readiness Score (CRS)
Memorandum of Agreement Information
Partner/Consultant Information | Role | Pending | Confirmed

## PMP 1- Strategy Name
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name:
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy:
Strategy Intent:
Target Audience:
IOM Category
Estimated Reach:
What is the dosage for this strategy?
How frequent will the strategy be implemented?
Necessary Resources for Successful Implementation
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 100% PC; 25% Executive Director; 75% Program Assistant; 33% webmaster and graphic designer
Number of staff to be hired/contracted: None
Staff/Consultant Recruitment Strategy
Staff/Consultant Training
Staff Retention Strategy
Additional Training
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies
Retention Strategies
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | N/A | N/A | N/A | N/A | N/A
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation?
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on F19: Retaining your employees for the duration of the initiative is an achievement measure.
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on B25: What retention strategies are in place to retain the relationships with the retailers? This applies to E25 and F25
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP 2- Strategy Name
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name:
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy:
Strategy Intent:
Target Audience:
IOM Category
Estimated Reach:
What is the dosage for this strategy?
How frequent will the strategy be implemented?
Necessary Resources for Successful Implementation
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 100% PC; 25% Executive Director; 75% Program Assistant; 33% webmaster and graphic designer
Number of staff to be hired/contracted: None
Staff/Consultant Recruitment Strategy
Staff/Consultant Training
Staff Retention Strategy
Additional Training
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies
Retention Strategies
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | N/A | N/A | N/A | N/A | N/A
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation?
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on F19: Retaining your employees for the duration of the initiative is an achievement measure.
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on B25: What retention strategies are in place to retain the relationships with the retailers? This applies to E25 and F25
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## PMP 3- Strategy Name
I. SCOPE DETAILS
A. Strategy Intent
Evidenced-based Strategy Name:
Intervening Variable(s) and Contributing Factor(s) addressed by the Strategy:
Strategy Intent:
Target Audience:
IOM Category
Estimated Reach:
What is the dosage for this strategy?
How frequent will the strategy be implemented?
Necessary Resources for Successful Implementation
B. Staffing Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Number of staff currently in place to facilitate the implementation of the strategy: 100% PC; 25% Executive Director; 75% Program Assistant; 33% webmaster and graphic designer
Number of staff to be hired/contracted: None
Staff/Consultant Recruitment Strategy
Staff/Consultant Training
Staff Retention Strategy
Additional Training
C. Recruitment & Retention Considerations
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Recruitment/Engagement Strategies
Retention Strategies
II. COMMUNITY READINESS
Community Readiness Strategies | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
III. FIDELITY
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Proposed adaptations and rationale for proposed adaptations | N/A | N/A | N/A | N/A | N/A
Plans for monitoring fidelity
Plans for addressing lack of fidelity
IV. EVALUATION & DATA COLLECTION
Strategy Implementation Indicators | How will this be implemented? | Lead Staff | Deadline for Completion | Monitoring Tool(s) | Achievement Measures
Who is conducting the evaluation?
Key questions that should be asked.
What data will be collected?
How will the data be collected?
Note on A1: T A: There are three sections that address the scope of the strategy: Strategy Intent, Staffing Considerations and Recruitment & Retention.
Note on A3: T A: This will come directly from your approved Strategic Plan.
Note on A4: T A: This will come directly from your approved Strategic Plan.
Note on A5: T A: Briefly state the overall intent of this strategy and its expected impact in relation to your approved IV/CF.
Note on A6: T A: Who is the target audience(s).
Note on A7: T A: Is this strategy targeting UNIVERSAL, SELECTED or INDICATED populations?
Note on A8: T A: For Individual Level strategies, Providers should indicate the number of people they plan to reach with this strategy by September 30, 2013. For Environmental Strategies, Providers should also give strong consideration to reach as well. For example, how many vendors will you target for a Sticker Shock, Shoulder Tap Operation or Responsible Beverage Server Training? What is the expected reach with a media campaign, etc?
Note on A9: T A: Dosage: The administration of an intervention/strategy in prescribed amounts and at prescribed interval What is required to complete one cycle of this strategy. This may be answered in terms of the # of sessions or the # of hours. Please refer to the literature regarding this strategy to appropriately respond. EXAMPLE: AlcoholEdu for High School - 1 session weekly for 3 weeks plus one 30-day FU = 1 cycle Sticker Shock - 10 retail establishments in 30 days =1 cycle (this is just an example)
Note on A10: T A: Indicate the number of times an average person/home is exposed to the strategy within a given time period. This applies to individual level strategies and environmental strategies such as, but not limited to: Media, Sticker Shock, Compliance Checks, Shoulder Tap, Responsible Beverage Service Training, Sobriety Checkpoints, Saturation Patrols, Reward & Reminder, etc.
Note on A11: T A: This refers to the resources that were budgeted for in the strategic plan budget. For example, staff time, materials, facility, equipment, etc.
Note on A13: TA In this section, Providers are asked to discuss their human resource capacity to implement the strategy
Note on A14: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B14: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on C14: T A: Who will be leading the efforts discussed in Column B. This follows throughout the rest of the document.
Note on E14: T A: Discuss the mechanism that will be used to track each indicator.
Note on F14: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A15: T A: Enter this information here.
Note on A16: T A: Discuss the human resources needed to implement this strategy.
Note on A17: T A: Discuss the plans to recruit the necessary human resources.
Note on A18: T A: Discuss the trainng that is required to implement this strategy. What mechanisms are in place to ensure that staff/consultants are properly trained? For staff who have been previously trained on this strategy, discuss the plan to ensure that the staff can implement with a high degree of fidelity?
Note on A19: T A: Good staff is often hard to come by and there is quite an investment to train staff. Discuss the plan to retain the human resources needed to successfully implement,
Note on F19: Retaining your employees for the duration of the initiative is an achievement measure.
Note on A20: T A: Discuss plans for others trainings that may be beneficial while implementing this strategy.
Note on A22: T A: This section relates back to the Strategy Intent section. NOTE: This is not limited to Individual Level strategies. For example, discuss your plans to engage merchants or other key stakeholders needed to successfully implement the strategy. IF THE STRATEGY FOR RECRUITMENT and/or RETENTION CHANGES PER COMMUNITY, CLEARLY DISCUSS THIS AS WELL.
Note on A23: T A: This represents benchmarks that need to be carefully considered prior to implementation.
Note on B23: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E23: T A: Discuss the mechanism that will be used to track each indicator.
Note on F23: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A24: T A: For ENVIRONMENTAL: Providers will discuss in detail their plan to reach all of the individuals in their target population? Consider your readiness score when addressing this section. For INDIVIDUAL - Providers should discuss in detail the recruitment process that will be used to reach the target population. Will there be a screener? What is the referral process? If the strategy calls for ENGAGING stakeholders (i.e. Law Enforcement, Legislators, School Board, etc), Providers will discuss their approach in detail. If the strategy differs by community, be sure to discuss the distinctions.
Note on A25: T A: Discuss in detail the plan to keep participants, stakeholders and communities involved/engaged.
Note on B25: What retention strategies are in place to retain the relationships with the retailers? This applies to E25 and F25
Note on A27: T A: Providers are asked to think through their plans to build community readiness, specifically as it relates to this particular strategy.
Note on A28: T A: Beginning with the following row, list the Community Readiness activities planned specifically around the APPROVED Strategy. The goal is to improve the readiness of each community to effectively address the State Priority. You may add additional rows as need.
Note on B28: T A: Providers are asked to discuss in the details their plan to achieve the indicator/benchmark in Column A.
Note on E28: T A: Discuss the mechanism that will be used to track each indicator.
Note on F28: T A: Discuss what measure will be used to demonstrate achievement of the indicator/benchmark.
Note on A35: T A: All of the of APPROVED strategies should be evidenced-based. Therefore, please refer to the curriculum, framework, model, or empirical literature used to select the strategy as a guide to address fidelity.
Note on A37: T A: Often times this is relevant for Individual Level Strategies. However, some providers are implementing Environmental Strategies that may be from other existing policies or practices (i.e. an ordinance)
Note on A41: T A: For INDIVIDUAL Level strategies, Providers are encouraged to refer to the program related information to guide them in the completion of this section. Other tools specific to INDIVIDUAL Level strategies will be advised by the APP Evaluation Team. For ENVIRONMENTAL Level strategies, Providers are encouraged to minimally include their considerations regarding Process Evaluation. Additonal guidance will be offered from the APP Evaluation Team.

## Modified EXAMPLE DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Run 1st of 4 PSAs in newspaper by January 2014 | Spread the word about the dangers of underage drinking. | Parent | 1. Draft a 'catchy' announcement |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-14 | 2013-12-01 | 2013-12-20 | Activity started after the PC and CPAW attended a social marketing training offered at the local university on 11/23/13.Despite the delay, we implemented the activity as planned.
|  |  | 2. Identify 10 parents to participate in 2 focus groups to elicit input on PSA |  | Lisa Smith and John Williams - Partners | 2013-11-20 | 2013-11-30 | 2013-12-15 | 2013-12-30
|  |  | 3. Contract with newspaper outlets to run first PSA |  | Anita Conley | 2013-12-01 | 2013-12-10 | 2013-12-01 | 2013-12-07
Host 1st of 4 Lunch & Learn programs by March 2014 | To raise awareness about underage drinking and social host liability among community stakeholders. | Stakeholders | 1. Put together a powerpoint that explains the purposed of SPF, the implications of youth possession in the community, and the need for community involvement. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-07 | 2013-11-01 | 2013-11-07
|  |  | 2. Identify a donor and/or inkind support to provide the food for the L & L. |  | Kimberly Jones - Project Coordinator | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 3. Secure a venue in collaboration with a community partner to host the L & L in a location convenient to stakeholders. |  | Anita Conley - Administrative Asst. | 2013-11-01 | 2013-11-15 | 2013-11-01 | 2013-11-15
|  |  | 4. Host first L & L |  | Kimberly Jones - Project Coordinator | 2013-12-01 | 2013-12-01 | 2013-12-01 | 2013-12-01
Poll community to gather data concerning communities view of underage drinking/social hosting | Gather data to determine the communities responsiveness to a social host ordinance | Parents of youth 9 to 20 and community members | Develop 4 to 5 questions concering underage drinking and social hosting to gather data | Provider Office | Evaluator | 2014-03-01 | 2014-04-30 | 2014-03-10 | 2014-04-15 | Our projected dates were delayed to include student involvment and input throughout this activity. We started after spring break and continued after the students returned to campus.
|  | Law Enforcement, Workgroup and community members | Attend community events and visit various community locations where polls can be distributed and collected | [Local Community] | CPAW Workgroup, Kimberly Jones - Project Coordinator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-15
|  | Law Enforcement, Workgroup and community members | Analyze poll data as received to determine communities receptiveness towards social host ordinance | Provider Office | Evaluator | 2014-05-01 | 2014-08-30 | 2014-05-01 | 2014-09-30
Present report of community poll to City Council during 2014 calendar year | To educate and inform the City Council about the community's views about social host ordinance. | City Council | Contact the appropriate office to get on the 2014 4th quarter City Council calendar. | [Local Community] | Kimberly Jones - Project Coordinator | 2014-08-01 | 2014-09-30 | 2014-09-20 | 2014-12-22 | We were advised by the CPAW to wait until the data was compiled and report drafted before pursuing a date. Unfortunately, due to the political climate in our community, 1) Social Host Liability is not a priority at this time; 2) we were informed that the 2015 City Council calendar has already been set as well.
SHADED FOR EXAMPLE ONLY3
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY15-16 Strategy 1 DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Activity |  |  | Action Step 1
Action Step 2
Activity 2 |  |  | Action Step 1
Action Step 2
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY15-16 Strategy 2 DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Activity |  |  | Action Step 1
Action Step 2
Activity 2 |  |  | Action Step 1
Action Step 2
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## FY15-16 Strategy 3 DAP
Approved Strategy Name:
List activity associated with the APPROVED strategy | Activity Goal | Target Audience | Action Steps: Steps/Tasks required to complete each activity Use multiple rows to indicate the various steps, as needed. | Setting / Location | Responsible Party Who will do it? | Projected Start Date | Projected End Date | Actual Start Date | Actual End Date | Comment | Status Code
Activity |  |  | Action Step 1
Action Step 2
Activity 2 |  |  | Action Step 1
Action Step 2
Note on C1: T A: Type in the name of your Approvied Strategy.
Note on A2: If there are multiple major activities associated with the Approved strategy, please list each major activity on a separate row. Provide all the necessary Action Steps (Column D) for each component before listing the next activity. For example, if there are 4 Action Steps associated with an activity, leave columns A-C blank as shown in the example provided. If a strategy entails multiple cycles of a particular activity (i.e. Run 4 PSAs), then remember to outline the specific details for each cycle of the activity. Also, remember to clearly indicate which community the activity and subsequent action steps are associated with.
Note on B2: What do you hope to accomplish by conducting the activity?
Note on C2: T A: The activities planned for the APPROVED Strategy may target different audiences. Therefore, this column refers to the target population for the planned activity, not necessarily the overall APPROVED strategy.
Note on D2: Provide the specific Action Steps that will be necessary to complete each activity. Be mindful to align Action Steps with the specific activity. Please enter each step/task on a new row as illustrated.
Note on E2: T A: If a setting or location is required to implement this activity, Providers are asked to include this information in this column.
Note on F2: Provide the name of the person responsible for completing the aligned task. If the name is not available at this time, be sure to also include their status (i.e. APP staff title, volunteer, partner or consultant).
Note on G2: Indicate the projected start date associated with the task.
Note on H2: Indicate the projected End Date for this task. If this is an ongoing task, indicate this in space provided. For example, identifying new stakeholders to get involved is likely to be an ongoing task.
Note on I2: T A: Indicate the actual start date for each task, even if the date is the same as the projected start date.
Note on J2: TA: Indicate the actual end date for each task. Leave this column blank until the task has actually been completed.
Note on K2: TA: Use this column to provide brief comments regarding delays, challenges and concerns ONLY. For example, if estimated start differs from the actual start, include a brief comment to document the reason. Also, include notes for YELLOW and RED status codes.
Note on L2: TA: Use the status code/colors below to provide a quick at-a-glance status for each activity outlined in Column A of the Strategy DAP. Only code Column A activities. BLUE - This indicates that the activity was completed nearly/as planned. GREEN - This indicates that the activity is being implemented as planned yet still in progress during this particular reporting period. ORANGE- This indicates that the activity requires ongoing monitoring and/or engagement for successful completion of the strategy. YELLOW- This indiciates that the activity or related tasks needs to be tweaked for successful completion of the strategy. RED - This indicates that the activity has encounterd significant setbacks that may result in significant changes. Consultation with RPS and CITF and/or Evaluation is required.

## EXAMPLE Milestone Timeline
Project Activities (Milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Run 1st Alcohol Awareness Campaign PSA about Social Host Liability | bar: Nov to Dec
Host 1st Stakeholder Lunch & Learn about Social Host Liability | bar: Nov to Dec
Poll community to gather data concerning communities view of underage drinking/social hosting | bar: Mar to Aug
Present report of community poll to City Council during 2014 calendar year | bar: Jun to Jul
Recruitment of 10 families for first cycle of Family Prevention Education Program | bar: Dec to Feb
Train decoys for Shoulder Tap Operation | bar: Jan to Feb
County Police and decoys conduct first Shoulder Tap Operation | bar: Feb to Mar
Note on A1: T A: Enter the Milestone Activities chronlogically. Color-code the timeline by assigning a color for each strategy. Include a LEGENDon the side for readers to comprehend at a glance. Refer to Column A from each Strategy DAP. For each activity in this column, Providers are to fill in the cell where they anticipate the activity starting through its anticipated end date. Since the chart is set up according to months and not weeks, filling in one cell suggests that the activity will be complete within that month.

## At-A-Glance Milestone Timeline
Project Activities (Milestones) | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Note on A1: T A: Enter the Milestone Activities chronlogically. Color-code the timeline by assigning a color for each strategy. Include a the side for readers to comprehend at a glance. Refer to Column A from each Strategy DAP. For each activity in this column, Providers are to fill in the cell where they anticipate the activity starting through its anticipated end date. Since the chart is set up according to months and not weeks, filling in one cell suggests that the activity will be complete within that month.